## Current scenario Copy 21Apr
No. | Module | Target page Technology | Recieved Functional & Non Fuctional Walkthrough | Buffer In case of no KT | Module Target Start (Input) | Revised Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | Status | Remarks | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Code Freeze Date | TEST Deployment | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | Code freeze date = Release cutoff Date | Release # | Release Request Approved Date | Release Date (2-Wk Cycle) | Code freeze date = Release cutoff Date | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
1 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | 2026-04-15 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed |  | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | #VALUE! | 41 |  | 9
2 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | 2026-04-15 | page_2 | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed |  | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
3 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | 2026-04-15 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed |  | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
4 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | 2026-04-20 | page_4 | Pod 1 | Pod 1_Member1 | 2026-04-20 | 3 | 0 | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Completed |  | 3 | 2026-04-27 | 1.5 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 2 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 9
5 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | 2026-04-20 | page_5 | Pod 1 | Pod 1_Member2 | 2026-04-20 | 3 | 0 | 5 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Completed |  | 3 | 2026-04-27 | 1.5 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 3 | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 50 | #VALUE! | 9 |  |  | #VALUE!
6 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | 2026-04-22 | assessments\results\manager.aspx.cs | Pod 2 | Vijay | 2026-04-24 | 3 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 | On track | Dev in progress, PR will be raisd on 28th Apr | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
7 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | 2026-04-22 | assessments\results\listtaken.aspx.cs | Pod 2 | Sohith | 2026-04-24 | 3 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | On track | Dev in progress, PR will be raisd on 28th Apr Kept on hold on 28th Apr as we were raised PR for shared controls. | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
8 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | 2026-04-22 | assessments\reports\assessmentQuestionAnalysis.aspx.cs | Pod 2 | Anil | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  | Dev completed however facing UI issues. fix in progress. | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
9 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | 2026-05-04 | assessments\import.aspx.cs | Pod 2 | Anil | 2026-05-04 | 3 | 0 | 4 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
10 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | 2026-05-04 | assessments\assessment.aspx.cs | Pod 2 | Sohith | 2026-05-04 | 3 | 0 | 5 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
11 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | 2026-04-28 | assessments\reports\assessmentAnswersAccepted.aspx.cs | Pod 2 | Anil | 2026-04-24 | 3 | 0 | 6 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  | Dev completed however facing UI issues. fix in progress. | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
12 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | 2026-05-04 | assessments\default.aspx.cs | Pod 3 | Vijay | 2026-05-04 | 3 | 0 | 7 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
13 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | 2026-05-04 | assessments\checkMyWork\submissions.aspx.cs | Pod 3 | Sohith | 2026-05-04 | 3 | 0 | 8 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 | #VALUE! | 9 |  |  | #VALUE!
14 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | 2026-05-01 | assessments/reports/assessmentAnalysis | Pod 3 | Anil | 2026-04-23 | 3 | 0 | 9 | 2026-04-27 | 2026-04-27 | 2026-04-27 | Completed | Completed Dev testing; Connected with QE to test from local (completed) | 3 | 2026-04-30 | 1.5 | 2026-05-04 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 31 |  | 9
15 | Assessments | Complete ASP | Yes | 0 | 2026-04-29 | 2026-05-07 | page_10 | Pod 3 |  | 2026-05-07 | 3 | 0 | 10 | 2026-05-11 | 2026-05-11 | 2026-05-11 |  |  | 3 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 45 |  | 9
16 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | 2026-04-22 | expressAssetHistory.aspx | Pod 3 | Mizan | 2026-04-23 | 3 | 0 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  | Dev completed and test case in creation | 3 | 2026-04-30 | 1.5 | 2026-05-04 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 31 |  | 9
17 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | 2026-04-22 | assetvendors.aspx | Pod 3 | swarneem | 2026-04-23 | 3 | 0 | 2 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  | Dev in Progress as swarneem working on addressbook bugs and raised PR, however ETA to raise PR is on 28 APR | 3 | 2026-04-30 | 1.5 | 2026-05-04 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 31 |  | 9
18 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | 2026-04-22 | assets.aspx | Pod 3 | Mizan | 2026-04-23 | 3 | 0 | 3 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  | Dev completed and test case in creation | 3 | 2026-04-30 | 1.5 | 2026-05-04 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 31 |  | 9
19 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | 2026-04-22 | assetwarrantlytypes.aspx | Pod 3 | swarneem | 2026-04-23 | 3 | 0 | 4 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  | Dev in Progress as swarneem working on addressbook bugs and raised PR, however ETA to raise PR is on | 3 | 2026-04-30 | 1.5 | 2026-05-04 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 3 | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 45 |  | 9
20 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | 2026-04-22 | assetLeases.aspx | Pod 3 | Mizan | 2026-04-28 | 3 | 0 | 5 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | Dev in Progress as swarneem working on addressbook bugs and raised PR, however ETA to raise PR is on | 3 | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 3 | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 42 |  | 9
21 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | 2026-05-04 | assetHistory.aspx | Pod 3 | Mizan | 2026-05-04 | 3 | 0 | 6 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 3 | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #N/A | #VALUE! |  | 92299
21 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | 2026-05-05 | assetVendorAddressContact.aspx | Pod 3 | Mizan | 2026-05-05 | 3 | 0 | 7 | 2026-05-08 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 3 | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #N/A
21 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | 2026-05-05 | assetvendor.aspx | Pod 3 | Mizan | 2026-05-05 | 3 | 0 | 8 | 2026-05-08 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 3 | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #N/A
20 | Communication | Complete ASP | No | 2 | 2026-05-05 | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-07 | 3 | 0 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 |  |  | 3 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 31 |  | 9
21 | Communication | Complete ASP | No | 2 | 2026-04-29 | 2026-04-29 | page_2 | Pod 2 | Pod 2_Member2 | 2026-05-01 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
22 | Communication | Complete ASP | No | 2 | 2026-04-29 | 2026-04-29 | page_3 | Pod 2 | Pod 2_Member3 | 2026-05-01 | 3 | 0 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
23 | Communication | Complete ASP | No | 2 | 2026-05-12 | 1900-01-01 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  |  | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 3 | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 52 | #VALUE! | 9 |  |  | #VALUE!
24 | Content |  |  |  | 2026-04-15 | 2026-05-04 | content\hyperlink.aspx | Pod 3 | Ramesh | 2026-05-04 | 3 | 0 | 8802 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
25 | Content |  |  |  | 2026-04-15 | 2026-05-04 | content\sources\default.aspx.cs | Pod 3 | Amol | 2026-05-04 | 3 | 0 | 8801 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
26 | Content |  |  |  | 2026-04-15 |  | content\timeline.aspx.cs | Pod 3 | Rizwana | 2026-04-15 | 3 | 0 | 8817 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  | PR: 8817 raised on 5-May-26 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
27 | Content |  |  |  | 2026-05-07 | 2026-05-04 | content\captionedVideoItem.aspx.cs | Pod 3 | Ramesh | 2026-05-04 | 3 | 0 | 8804 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 3 | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 50 |  | 9
| Content | [5 empty] | content\elmItemInteractive.aspx | Pod 3 | Amol | 2026-05-04 | 3 | 8804 |  | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 3 | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #N/A
| Content | [5 empty] | content/grammarTool.aspx | Pod 3 | Rizwana | 2026-05-04 | 3 | 8804 |  | 2060-02-19 | 2060-02-19 | 2060-02-19 |  |  | 3 | 2060-02-24 | 1.5 | 2060-02-25 | 2060-02-25 | 3 | 2060-03-01 | 2060-03-01 | 2060-03-01 | 2060-03-02 | 2060-03-02 | 3 | 2060-03-05 | 2 | 2060-03-09 | 3 | 2060-03-12 | 2060-03-12 | 2060-03-15 | 2060-03-15 | 1 | 2060-03-16 | 2060-03-16 | 2060-03-16 | 2060-03-17 | 3 | 2060-03-22 | 0 | 2060-03-22 | 0 | 2060-03-22 | 0 | #N/A | #N/A
| Content | [5 empty] | content\sources\source.aspx.cs | Pod 3 | Ramesh | 2026-05-04 | 3 | 8804 |  | 2060-02-19 | 2060-02-19 | 2060-02-19 |  |  | 3 | 2060-02-24 | 1.5 | 2060-02-25 | 2060-02-25 | 3 | 2060-03-01 | 2060-03-01 | 2060-03-01 | 2060-03-02 | 2060-03-02 | 3 | 2060-03-05 | 2 | 2060-03-09 | 3 | 2060-03-12 | 2060-03-12 | 2060-03-15 | 2060-03-15 | 1 | 2060-03-16 | 2060-03-16 | 2060-03-16 | 2060-03-17 | 3 | 2060-03-22 | 0 | 2060-03-22 | 0 | 2060-03-22 | 0 | #N/A | #N/A
| Content | [5 empty] | content\chrome\online\footer.aspx.cs | Pod 3 | Amol | 2026-05-04 | 3 | 8804 |  | 2060-02-19 | 2060-02-19 | 2060-02-19 |  |  | 3 | 2060-02-24 | 1.5 | 2060-02-25 | 2060-02-25 | 3 | 2060-03-01 | 2060-03-01 | 2060-03-01 | 2060-03-02 | 2060-03-02 | 3 | 2060-03-05 | 2 | 2060-03-09 | 3 | 2060-03-12 | 2060-03-12 | 2060-03-15 | 2060-03-15 | 1 | 2060-03-16 | 2060-03-16 | 2060-03-16 | 2060-03-17 | 3 | 2060-03-22 | 0 | 2060-03-22 | 0 | 2060-03-22 | 0 | #N/A | #N/A
| Content | [5 empty] | content\chrome\printed\options.aspx.cs | Pod 3 | Rizwana | 2026-05-04 | 3 | 8804 |  | 2060-02-19 | 2060-02-19 | 2060-02-19 |  |  | 3 | 2060-02-24 | 1.5 | 2060-02-25 | 2060-02-25 | 3 | 2060-03-01 | 2060-03-01 | 2060-03-01 | 2060-03-02 | 2060-03-02 | 3 | 2060-03-05 | 2 | 2060-03-09 | 3 | 2060-03-12 | 2060-03-12 | 2060-03-15 | 2060-03-15 | 1 | 2060-03-16 | 2060-03-16 | 2060-03-16 | 2060-03-17 | 3 | 2060-03-22 | 0 | 2060-03-22 | 0 | 2060-03-22 | 0 | #N/A | #N/A
28 | Enrollment | Complete ASP | No | 2 | 2026-04-28 | 1900-01-01 | page_1 | Pod 1 | Pod 1_Member3 | 2026-04-30 | 3 | 0 | 1 | 2026-05-05 | 2026-05-05 | 2026-05-05 |  |  | 3 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 37 |  | 9
29 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member1 | 2026-05-12 | 3 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 |  |  | 3 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 9
30 | Enrollment | Complete ASP | No | 2 | 2026-04-28 | 1900-01-01 | page_3 | Pod 1 | Pod 1_Member2 | 2026-04-30 | 3 | 0 | 3 | 2026-05-05 | 2026-05-05 | 2026-05-05 |  |  | 3 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 37 |  | 9
31 | Enrollment | Complete ASP | No | 2 | 2026-05-06 | 1900-01-01 | page_4 | Pod 1 | Pod 1_Member3 | 2026-05-08 | 3 | 0 | 4 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
32 | Enrollment | Complete ASP | No | 2 | 2026-05-15 | 2026-05-15 | page_5 | Pod 1 | Pod 1_Member1 | 2026-05-19 | 3 | 0 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-21 |  |  | 3 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 35 |  | 9
33 | Enrollment | Complete ASP | No | 2 | 2026-05-06 | 1900-01-01 | page_6 | Pod 1 | Pod 1_Member2 | 2026-05-08 | 3 | 0 | 6 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
34 | Enrollment | Complete ASP | No | 2 | 2026-05-13 | 1900-01-01 | page_7 | Pod 1 | Pod 1_Member3 | 2026-05-15 | 3 | 0 | 7 | 2026-05-19 | 2026-05-19 | 2026-05-19 |  |  | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
35 | Enrollment | Complete ASP | No | 2 | 2026-05-22 | 2026-05-22 | page_8 | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 0 | 8 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 3 | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 9
36 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | 2026-05-18 | page_1 | Pod 1 | Pod 1_Member1 | 2026-05-18 | 3 | 0 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 9
37 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
38 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-05 | 2026-05-05 | page_3 | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
39 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-21 | 2026-05-21 | page_4 | Pod 1 | Pod 1_Member1 | 2026-05-21 | 3 | 0 | 4 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 9
40 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-13 | 2026-05-13 | page_5 | Pod 1 | Pod 1_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
41 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | 2026-05-08 | page_6 | Pod 1 | Pod 1_Member3 | 2026-05-08 | 3 | 0 | 6 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
42 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-26 | 2026-05-26 | page_7 | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 0 | 7 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 9
43 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | 2026-05-18 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 9
44 | GradeBook | Complete ASP | Yes | 0 | 2026-05-13 | 2026-05-13 | page_3 | Pod 2 | Pod 2_Member1 | 2026-05-13 | 3 | 0 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 3 | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
45 | GradeBook | Complete ASP | Yes | 0 | 2026-05-05 | 2026-05-05 | page_4 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 49 |  | 12
46 | Home | Complete ASP | No | 2 | 2026-04-20 | 2026-04-23 | home\pages\enrollment.aspx.cs | Pod 1 | Amol | 2026-04-22 | 3 | 0 | 8787 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  | Clarifications still pending with pearson, however Dev is in progress | 3 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 2 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 34 |  | 9
47 | Home | Complete ASP | No | 2 | 2026-05-07 | 1900-01-01 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-11 | 3 | 0 | 2 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  |  | 3 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 |  | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 43 |  | 9
48 | Home | Complete ASP | No | 2 | 2026-05-07 | 2026-04-23 | home/pages/overdueLessons.aspx | Pod 1 | Rizwana | 2026-05-11 | 3 | 0 | 8769 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  | Clarifications still pending with pearson, however Dev is in progress | 3 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 |  | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 43 |  | 9
49 | Home | Complete ASP | No | 2 | 2026-04-27 | 1900-01-01 | page_4 | Pod 3 | Pod 3_Member3 | 2026-04-29 | 3 | 0 | 4 | 2026-05-04 | 2026-05-04 | 2026-05-04 |  |  | 3 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 3 | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 52 | #VALUE! | 9 |  |  | #VALUE!
50 | IssueAware | Complete ASP | Yes | 0 | 2026-05-05 | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
51 | IssueAware | Complete ASP | Yes | 0 | 2026-05-18 | 2026-05-18 | page_2 | Pod 2 | Pod 2_Member1 | 2026-05-18 | 3 | 0 | 2 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 9
52 | Library_Part 2 | #N/A | Yes | 0 | 2026-04-29 | 2026-04-23 | library\category.aspx.cs | Pod 3 | Prem | 2026-04-24 | 3 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  | Expecting PR to be raised on 28th APR | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
53 | Library_Part 3 | #N/A | Yes | 0 | 2026-04-24 | 2026-05-04 | library/searchResults.aspx | Pod 3 | Prem | 2026-05-04 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
54 | Library_Part 3 | #N/A | Yes | 0 | 2026-04-29 | 2026-05-04 | library/resource.aspx | Pod 3 | Swarneem | 2026-05-04 | 3 | 0 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 3 | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 50 |  | 9
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | 2026-05-08 | page_2 | Pod 2 | Pod 2_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 3 | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 |  | 9
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | 2026-05-08 | page_2 | Pod UI | Pod UI_UI-Member1 | 2026-05-08 | 5 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 |  |  | 3 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 3 | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 9
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | 2026-05-08 | page_3 | Pod 2 | Pod 2_Member3 | 2026-05-08 | 3 | 0 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 | #VALUE! | 9
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | 2026-05-08 | page_3 | Pod UI | Pod UI_UI-Member2 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 |  |  | 3 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 | #VALUE! | 9
57 | LMU | React/ASP | Yes | 0 | 2026-05-21 | 2026-05-21 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-21 | 3 | 0 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 3 | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 3 | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 |  | 9
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | 2026-05-08 | page_3 | Pod UI | Pod UI_UI-Member3 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 |  |  | 3 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 | #VALUE! | 9
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | 2026-05-13 | page_5 | Pod 2 | Pod 2_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | 2026-05-13 | page_5 | Pod UI | Pod UI_UI-Member4 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 |  |  | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
59 | LMU | React/ASP | Yes | 0 | 2026-05-13 | 2026-05-13 | page_6 | Pod 2 | Pod 2_Member3 | 2026-05-13 | 3 | 0 | 6 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 3 | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 | #VALUE! | 9 |  |  | #VALUE!
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | 2026-05-13 | page_5 | Pod UI | Pod UI_UI-Member5 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 |  |  | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
58 | LMU | React/ASP | Yes | 0 | 2026-05-20 | 2026-05-20 | page_5 | Pod UI | Pod UI_Integration | 2026-05-20 | 5 | 0 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-26 |  |  | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
60 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | 2026-05-26 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-26 | 3 | 0 | 4 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 9
61 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | 2026-05-18 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 9
62 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | 2026-05-18 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-18 | 3 | 0 | 9 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 9
63 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | 2026-06-01 | page_7 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 49 |  | 9
64 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | 2026-05-21 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-21 | 3 | 0 | 11 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 9
65 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | 2026-05-21 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-21 | 3 | 0 | 12 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 3 | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 3 | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 |  | 9
66 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | 2026-06-05 | page_10 | Pod 2 | Pod 2_Member1 | 2026-06-05 | 3 | 0 | 10 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 9
67 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | 2026-05-26 | page_14 | Pod 2 | Pod 2_Member2 | 2026-05-26 | 3 | 0 | 14 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 3 | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 | #VALUE! | 9 |  |  | #VALUE!
68 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | 2026-05-26 | page_15 | Pod 2 | Pod 2_Member3 | 2026-05-26 | 3 | 0 | 15 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 9
69 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | 2026-06-10 | page_13 | Pod 2 | Pod 2_Member1 | 2026-06-10 | 3 | 0 | 13 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 3 | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
70 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | 2026-06-01 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 17 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
71 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | 2026-06-01 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 18 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 49 |  | 9
72 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | 2026-06-15 | page_16 | Pod 2 | Pod 2_Member1 | 2026-06-15 | 3 | 0 | 16 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 3 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 |  | 2026-07-10 | 0 | 2026-07-10 | 0 | 2026-07-10 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 9
73 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | 2026-06-05 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-05 | 3 | 0 | 20 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 3 | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 44 |  | 9
74 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | 2026-06-05 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-05 | 3 | 0 | 21 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 9
75 | LMU | Complete ASP | Yes | 0 | 2026-06-18 | 2026-06-18 | page_19 | Pod 2 | Pod 2_Member1 | 2026-06-18 | 3 | 0 | 19 | 2026-06-22 | 2026-06-22 | 2026-06-22 |  |  | 3 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 3 | 2026-07-28 | 0 | 2026-07-28 | 0 | 2026-07-28 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 45 |  | 9
76 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | 2026-06-10 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-10 | 3 | 0 | 23 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
77 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | 2026-06-10 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-10 | 3 | 0 | 24 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 3 | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
78 | LMU | Complete ASP | Yes | 0 | 2026-06-23 | 2026-06-23 | page_22 | Pod 2 | Pod 2_Member1 | 2026-06-23 | 3 | 0 | 22 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 3 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 42 | #VALUE! | 9 |  |  | #VALUE!
79 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | 2026-06-15 | page_25 | Pod 2 | Pod 2_Member3 | 2026-06-15 | 3 | 0 | 25 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 3 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 |  | 2026-07-10 | 1 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 12
80 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | 2026-06-15 | page_26 | Pod 2 | Pod 2_Member2 | 2026-06-15 | 3 | 0 | 26 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 3 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 3 | 2026-07-21 | 1 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 50 |  | 12
81 | Location | Complete ASP | Yes | 0 | 2026-05-05 | 2026-05-05 | page_1 | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
82 | Location | Complete ASP | Yes | 0 | 2026-05-05 | 2026-05-05 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 | #VALUE! | 9 |  |  | #VALUE!
83 | Location | Complete ASP | Yes | 0 | 2026-04-29 | 2026-04-29 | page_3 | Pod 3 | Pod 3_Member2 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 |  |  | 3 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 |  | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 9
84 | Location | Complete ASP | Yes | 0 | 2026-05-08 | 2026-05-08 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-08 | 3 | 0 | 4 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
85 | Location | Complete ASP | Yes | 0 | 2026-05-08 | 2026-05-08 | page_5 | Pod 3 | Pod 3_Member1 | 2026-05-08 | 3 | 0 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
86 | Location | Complete ASP | Yes | 0 | 2026-05-05 | 2026-05-05 | page_6 | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
87 | Location | Complete ASP | Yes | 0 | 2026-05-13 | 2026-05-13 | page_7 | Pod 3 | Pod 3_Member3 | 2026-05-13 | 3 | 0 | 7 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
88 | Location | Complete ASP | Yes | 0 | 2026-05-13 | 2026-05-13 | page_8 | Pod 3 | Pod 3_Member1 | 2026-05-13 | 3 | 0 | 8 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
89 | Location | Complete ASP | Yes | 0 | 2026-05-08 | 2026-05-08 | page_9 | Pod 3 | Pod 3_Member2 | 2026-05-08 | 3 | 0 | 9 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
90 | Location | Complete ASP | Yes | 0 | 2026-05-18 | 2026-05-18 | page_10 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 10 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 9
91 | Location | Complete ASP | Yes | 0 | 2026-05-18 | 2026-05-18 | page_11 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 11 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 9
92 | Log | Complete ASP | Yes | 0 | 2026-06-26 | 2026-06-26 | page_1 | Pod 2 | Pod 2_Member1 | 2026-06-26 | 3 | 0 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 3 | 2026-07-06 | 1.5 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2 | 2026-07-16 | 3 | 2026-07-21 | 2026-07-21 | 2026-07-22 | 2026-07-22 |  | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 |  | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 36 | #VALUE! | 9 |  |  | #VALUE!
93 | Log | Complete ASP | Yes | 0 | 2026-06-18 | 2026-06-18 | page_2 | Pod 2 | Pod 2_Member2 | 2026-06-18 | 3 | 0 | 2 | 2026-06-22 | 2026-06-22 | 2026-06-22 |  |  | 3 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 9
94 | Log | Complete ASP | Yes | 0 | 2026-06-18 | 2026-06-18 | page_3 | Pod 2 | Pod 2_Member3 | 2026-06-18 | 3 | 0 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 |  |  | 3 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 9
95 | Log | Complete ASP | Yes | 0 | 2026-07-02 | 2026-07-02 | page_4 | Pod 2 | Pod 2_Member1 | 2026-07-02 | 3 | 0 | 4 | 2026-07-06 | 2026-07-06 | 2026-07-06 |  |  | 3 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 2 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-03 |  | 2026-08-03 | 0 | 2026-08-03 | 0 | 2026-08-03 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 45 |  | 9
96 | Log | Complete ASP | Yes | 0 | 2026-06-23 | 2026-06-23 | page_5 | Pod 2 | Pod 2_Member2 | 2026-06-23 | 3 | 0 | 5 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 3 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 42 |  | 9
97 | Log | Complete ASP | Yes | 0 | 2026-06-23 | 2026-06-23 | page_6 | Pod 2 | Pod 2_Member3 | 2026-06-23 | 3 | 0 | 6 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 3 | 2026-07-01 | 1.5 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 |  | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 |  | 2026-07-20 | 0 | 2026-07-20 | 0 | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 42 |  | 9
98 | Log | Complete ASP | Yes | 0 | 2026-06-01 | 2026-06-01 | page_7 | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
99 | Log | Complete ASP | Yes | 0 | 2026-05-21 | 2026-05-21 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-21 | 3 | 0 | 8 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 9
100 | Log | Complete ASP | Yes | 0 | 2026-05-13 | 2026-05-13 | page_9 | Pod 1 | Pod 1_Member3 | 2026-05-13 | 3 | 0 | 9 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
101 | Log | Complete ASP | Yes | 0 | 2026-05-21 | 2026-05-21 | page_10 | Pod 3 | Pod 3_Member1 | 2026-05-21 | 3 | 0 | 10 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 3 | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 3 | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 | #VALUE! | 9 |  |  | #VALUE!
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | 2026-06-01 | page_5 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member1 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 3 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 9
103 | OrderAware | React/ASP | Yes | 0 | 2026-06-05 | 2026-06-05 | page_6 | Pod 3 | Pod 3_Member3 | 2026-06-05 | 3 | 0 | 2 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 9
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member2 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 3 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 9
104 | OrderAware | React/ASP | Yes | 0 | 2026-06-10 | 2026-06-10 | page_7 | Pod 3 | Pod 3_Member1 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member3 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 3 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 9
105 | OrderAware | React/ASP | Yes | 0 | 2026-06-05 | 2026-06-05 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-05 | 3 | 0 | 4 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 3 | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 44 |  | 9
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member4 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 3 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 9
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-08 | 2026-06-08 | page_5 | Pod UI | Pod UI_Integration | 2026-06-08 | 5 | 0 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
133 | Security | Complete ASP | No | 2 | 2026-04-15 | 2026-04-15 | security/default.aspx | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 |  | 1 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  | 3 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28
133 | Security | Complete ASP | No | 2 | 2026-03-01 | 2026-03-01 | security/permissionRoles.aspx | Pod 3 | Pod 3_Member1 | 2026-03-03 | 3 |  | 1 | 2026-03-06 | 2026-03-06 | 2026-03-06 | Completed |  | 3 | 2026-03-11 | 1.5 | 2026-03-12 | 2026-03-12 | 3 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 |  | 2026-03-18 | 2 | 2026-03-23 | 3 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-30 |  | 2026-03-30 | 0 | 2026-03-30 | 0 | 2026-03-30 | 2026-04-09 | Release 8 | #VALUE! | 2026-04-16
133 | Security | Complete ASP | No | 2 | 2026-04-15 | 2026-04-15 | security/permissionVisibility.aspx | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 |  | 1 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Completed |  | 3 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28
133 | Security | Complete ASP | No | 2 | 2026-04-15 | 2026-04-15 | security/permissionDisplayGroupPermissions.aspx | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 |  | 1 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  | 3 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28
133 | Security | Complete ASP | No | 2 | 2026-05-01 | 2026-05-01 | security/PermissionDisplayGroups.aspx | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 |  | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11
133 | Security | Complete ASP | No | 2 | 2026-03-01 | 2026-03-01 | security\permissionSectionRoles.aspx | Pod 3 | Pod 3_Member1 | 2026-03-03 | 3 |  | 1 | 2026-03-06 | 2026-03-06 | 2026-03-06 | Completed |  | 3 | 2026-03-11 | 1.5 | 2026-03-12 | 2026-03-12 | 3 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 |  | 2026-03-18 | 2 | 2026-03-23 | 3 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-30 |  | 2026-03-30 | 0 | 2026-03-30 | 0 | 2026-03-30 | 2026-04-09 | Release 8 | #VALUE! | 2026-04-16
106 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-13 | 1900-01-01 | page_1 | Pod 1 | Pod 1_Member2 | 2026-05-15 | 3 | 0 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 |  |  | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
107 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-20 | 1900-01-01 | page_2 | Pod 1 | Pod 1_Member3 | 2026-05-22 | 3 | 0 | 2 | 2026-05-26 | 2026-05-26 | 2026-05-26 |  |  | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
108 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-01 | 2026-06-01 | page_3 | Pod 1 | Pod 1_Member1 | 2026-06-03 | 3 | 0 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 |  |  | 3 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 |  | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 34 |  | 9
109 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-20 | 1900-01-01 | page_4 | Pod 1 | Pod 1_Member2 | 2026-05-22 | 3 | 0 | 4 | 2026-05-26 | 2026-05-26 | 2026-05-26 |  |  | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
110 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-27 | 1900-01-01 | page_5 | Pod 1 | Pod 1_Member3 | 2026-05-29 | 3 | 0 | 5 | 2026-06-03 | 2026-06-03 | 2026-06-03 |  |  | 3 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 36 |  | 9
111 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-08 | 2026-06-08 | page_6 | Pod 1 | Pod 1_Member1 | 2026-06-10 | 3 | 0 | 6 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 | #VALUE! | 9 |  |  | #VALUE!
112 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-27 | 1900-01-01 | page_7 | Pod 1 | Pod 1_Member2 | 2026-05-29 | 3 | 0 | 7 | 2026-06-03 | 2026-06-03 | 2026-06-03 |  |  | 3 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 3 | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 50 |  | 9
113 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-04 | 1900-01-01 | page_1 | Pod 1 | Pod 1_Member3 | 2026-06-08 | 3 | 0 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 |  |  | 3 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 29 |  | 9
114 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-15 | 2026-06-15 | page_2 | Pod 1 | Pod 1_Member1 | 2026-06-17 | 3 | 0 | 2 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 9
115 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-04 | 1900-01-01 | page_3 | Pod 1 | Pod 1_Member2 | 2026-06-08 | 3 | 0 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 |  |  | 3 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 29 |  | 9
116 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-11 | 1900-01-01 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-15 | 3 | 0 | 4 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 3 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 |  | 2026-07-10 | 0 | 2026-07-10 | 0 | 2026-07-10 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 | #VALUE! | 9 |  |  | #VALUE!
117 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-22 | 2026-06-22 | page_5 | Pod 1 | Pod 1_Member1 | 2026-06-24 | 3 | 0 | 5 | 2026-06-29 | 2026-06-29 | 2026-06-29 |  |  | 3 | 2026-07-02 | 1.5 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 3 | 2026-07-30 | 3 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 52 | #VALUE! | 12 |  |  | #VALUE!
118 | Reports | Complete ASP | No | 2 | 2026-06-11 | 1900-01-01 | page_1 | Pod 1 | Pod 1_Member2 | 2026-06-15 | 3 | 0 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 3 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 9
119 | Reports | Complete ASP | No | 2 | 2026-06-18 | 1900-01-01 | page_2 | Pod 1 | Pod 1_Member3 | 2026-06-22 | 3 | 0 | 2 | 2026-06-24 | 2026-06-24 | 2026-06-24 |  |  | 3 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 2 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 2 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 |  | 2026-07-23 | 3 | 2026-07-28 | 3 | 2026-07-31 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 57 |  | 12
120 | Reports | Complete ASP | No | 2 | 2026-06-30 | 2026-06-30 | page_3 | Pod 1 | Pod 1_Member1 | 2026-07-02 | 3 | 0 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-06 |  |  | 3 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 |  | 2026-07-30 | 0 | 2026-07-30 | 0 | 2026-07-30 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 31 |  | 9
121 | Reports | Complete ASP | No | 2 | 2026-06-25 | 1900-01-01 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-29 | 3 | 0 | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 3 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 |  | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 |  | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 |  | 2026-07-27 | 0 | 2026-07-27 | 0 | 2026-07-27 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 36 | #VALUE! | 9 |  |  | #VALUE!
122 | Reports | Complete ASP | No | 2 | 2026-06-18 | 1900-01-01 | page_5 | Pod 1 | Pod 1_Member2 | 2026-06-22 | 3 | 0 | 5 | 2026-06-24 | 2026-06-24 | 2026-06-24 |  |  | 3 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 3 | 2026-07-30 | 0 | 2026-07-30 | 0 | 2026-07-30 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 43 |  | 9
123 | Webuser | Complete ASP | No | 2 | 2026-05-14 | 1900-01-01 | page_1 | Pod 3 | Pod 3_Member2 | 2026-05-18 | 3 | 0 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 9
124 | Webuser | Complete ASP | No | 2 | 2026-05-05 | 1900-01-01 | page_2 | Pod 3 | Pod 3_Member3 | 2026-05-07 | 3 | 0 | 2 | 2026-05-11 | 2026-05-11 | 2026-05-11 |  |  | 3 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 31 | #VALUE! | 9
125 | Webuser | Complete ASP | No | 2 | 2026-05-14 | 1900-01-01 | page_3 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 | #VALUE! | 9
126 | Webuser | Complete ASP | No | 2 | 2026-05-21 | 1900-01-01 | page_4 | Pod 3 | Pod 3_Member2 | 2026-05-25 | 3 | 0 | 4 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  |  | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 43 |  | 9
127 | Webuser | Complete ASP | No | 2 | 2026-05-12 | 1900-01-01 | page_5 | Pod 3 | Pod 3_Member3 | 2026-05-14 | 3 | 0 | 5 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  |  | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 | #VALUE! | 9
128 | Webuser | Complete ASP | No | 2 | 2026-05-21 | 1900-01-01 | page_1 | Pod 3 | Pod 3_Member1 | 2026-05-25 | 3 | 0 | 6 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  |  | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 43 | #VALUE! | 9
129 | Webuser | Complete ASP | No | 2 | 2026-05-28 | 1900-01-01 | page_2 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 |  | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02
130 | Webuser | Complete ASP | No | 2 | 2026-05-19 | 1900-01-01 | page_3 | Pod 3 | Pod 3_Member3 | 2026-05-21 | 3 |  | 8 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18
131 | Webuser | Complete ASP | No | 2 | 2026-05-28 | 1900-01-01 | page_4 | Pod 3 | Pod 3_Member1 | 2026-06-01 | 3 |  | 9 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02
132 | Webuser | Complete ASP | No | 2 | 2026-06-05 | 1900-01-01 | page_5 | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 |  | 10 | 2026-06-11 | 2026-06-11 | 2026-06-11 |  |  | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 3 | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16
133 | Gradebook | Complete ASP | No | 2 | 2026-06-05 | 1900-01-01 | page_6 | Pod 3 | Pod 3_Member1 | 2026-06-09 | 3 |  | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 |  |  | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
134 | Gradebook | Complete ASP | No | 2 | 2026-06-12 | 1900-01-01 | page_7 | Pod 3 | Pod 3_Member1 | 2026-06-16 | 3 |  | 2 | 2026-06-18 | 2026-06-18 | 2026-06-18 |  |  | 3 | 2026-06-23 | 1.5 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 |  | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
135 | Gradebook | Complete ASP | No | 2 | 2026-06-12 | 1900-01-01 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-16 | 3 |  | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 |  |  | 3 | 2026-06-23 | 1.5 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 |  | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-19 | 1900-01-01 | page_9 | Pod 3 | Pod 3_Member2 | 2026-06-23 | 3 |  | 4 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 3 | 2026-07-01 | 1.5 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 |  | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 |  | 2026-07-20 | 0 | 2026-07-20 | 0 | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member1 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
137 | Gradebook | React/ASP | No | 2 | 2026-05-26 | 1900-01-01 | page_10 | Pod 3 | Pod 3_Member3 | 2026-05-28 | 3 |  | 5 | 2026-06-03 | 2026-06-03 | 2026-06-03 |  |  | 3 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member2 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
138 | Gradebook | React/ASP | No | 2 | 2026-06-04 | 1900-01-01 | page_11 | Pod 3 | Pod 3_Member3 | 2026-06-08 | 3 |  | 6 | 2026-06-10 | 2026-06-10 | 2026-06-10 |  |  | 3 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member3 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
139 | Gradebook | React/ASP | No | 2 | 2026-06-19 | 1900-01-01 | page_12 | Pod 3 | Pod 3_Member1 | 2026-06-23 | 3 |  | 7 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 3 | 2026-07-01 | 1.5 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 |  | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 |  | 2026-07-20 | 0 | 2026-07-20 | 0 | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member4 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
140 | Gradebook | React/ASP | No | 2 | 2026-06-26 | 1900-01-01 | page_13 | Pod 3 | Pod 3_Member2 | 2026-06-30 | 3 |  | 8 | 2026-07-02 | 2026-07-02 | 2026-07-02 |  |  | 3 | 2026-07-08 | 1.5 | 2026-07-09 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 |  | 2026-07-23 | 2026-07-23 | 2026-07-23 | 2026-07-24 |  | 2026-07-24 | 0 | 2026-07-24 | 0 | 2026-07-24 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | 1900-01-01 | page_9 | Pod UI | Pod UI_UI-Member1 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 3 | 2026-07-06 | 1.5 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2 | 2026-07-16 | 3 | 2026-07-21 | 2026-07-21 | 2026-07-22 | 2026-07-22 |  | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 |  | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
141 | Gradebook | React/ASP | No | 2 | 2026-06-11 | 1900-01-01 | page_14 | Pod 3 | Pod 3_Member3 | 2026-06-15 | 3 |  | 9 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 3 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 3 | 2026-07-21 | 0 | 2026-07-21 | 0 | 2026-07-21 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | 1900-01-01 | page_9 | Pod UI | Pod UI_UI-Member2 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 3 | 2026-07-06 | 1.5 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2 | 2026-07-16 | 3 | 2026-07-21 | 2026-07-21 | 2026-07-22 | 2026-07-22 |  | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 |  | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
136 | Gradebook | React/ASP | No | 0 | 2026-06-23 | 2026-06-23 | page_9 | Pod UI | Pod UI_Integration | 2026-06-23 | 5 |  | 4 | 2026-06-30 | 2026-06-30 | 2026-06-30 |  |  | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
Formulas:
Start Date = [Module Target Start (Input)]
Start Date = WORKDAY([Module Target Start (Input)],[Buffer In case of no KT])
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Review Comments Fix Days],0, IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Raised Date = WORKDAY([PR Review Comments Fix Days], [PR Issue Fix Date], IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([PR Final Approval date], 0, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
TCR Bugs Closure Date = [QE Testing Days (TCR)]
Code Freeze Date = [TCR Bugs Closure Date]
Code Freeze Date = WORKDAY([TCR Bugs Closure Date], 1, IndHolidays)
TEST Deployment = [Code Freeze Date]
TEST Deployment = WORKDAY([Code Freeze Date], 1, IndHolidays)
Pearson Regression Testing/UAT Date = WORKDAY([TEST Deployment], 1, IndHolidays)
Pearson Regression Testing/UAT Date = WORKDAY([Code Freeze Date], [TEST Deployment], IndHolidays)
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&(MAX([PR Response receive Date],[TCR Bugs Closure Date])))
Code freeze date = Release cutoff Date = WORKDAY([Release Date (2-Wk Cycle)], -5)
Release Request Approved Date = WORKDAY([Release #], 2, IndHolidays)
Release Date (2-Wk Cycle) = VLOOKUP([Release #],ReleaseTimeline!$B2:C27,2,FALSE)
PR Response Days = WORKDAY([Unit Testing Closure Date], [Remarks], IndHolidays)
PR Response Days = WORKDAY([PR Issue Fix Date], [PR Raised Date], IndHolidays)
PR Review Comments Fix Days = WORKDAY([PR Response Days], [PR Response receive Date], IndHolidays)
PR Review Comments Fix Days = WORKDAY([PR Response receive Date],0, IndHolidays)
QE Testing Days (TCR) = WORKDAY([TCR Deployment Date], [TCR QE Testing Start Date], IndHolidays)
QE Testing Days (TCR) = WORKDAY([Code Merge Date (INT Ready)], [TCR QE Testing Start Date], IndHolidays)
Issue Fix Days = WORKDAY([QE Testing Days (TCR)], [TCR QE Testing End Date], IndHolidays)
Issue Fix Days = WORKDAY([Pearson Regression Testing Day], [Pearson Regression End Date], IndHolidays)
Pearson Regression Testing Day = WORKDAY([TEST Deployment], [Pearson Regression Testing/UAT Date], IndHolidays)
Remarks = WORKDAY([Co- Pilot Comment Closure Date], [Status], IndHolidays)
Module Target Start (Input) = WORKDAY([PR raised date, row above],1)
Revised Module Target Start (Input) = WORKDAY([Status, row above],1)

## Sheet2
Count of Status | Column Labels
Row Labels | Dev Bug fix in progress | Dev PR in review | Development Inprogress | Not Started | Out of scope | Prod bug PR in Review | Prod Deployed FF OFF | Prod Deployed FF ON | TCR bug PR in Review | TCR Testing In Progress | Waiting for clarification | (blank) | Grand Total
Addressbook | [5 empty] | 1 | [6 empty] | 1
Assessment |  | 2 |  |  |  |  | 3 |  |  | 6 |  |  | 11
AssetAware |  |  |  |  | 1 |  | 1 |  |  | 3 |  |  | 5
Attendance |  |  |  | 3 | [8 empty] | 3
AVAA Agents |  |  | 1 | [9 empty] | 1
Common | [9 empty] | 4 |  |  | 4
Communication |  | 1 | [8 empty] | 1 |  | 2
Content |  |  |  |  | 4 |  | 1 |  |  | 6 |  |  | 11
Enrollment |  | 2 |  |  | 2 |  |  |  |  | 1 | 1 |  | 6
Extended Field |  | 4 |  |  | 1 |  |  |  |  | 2 |  |  | 7
External |  | 1 | [10 empty] | 1
FORUM | 3 |  | 1 | [9 empty] | 4
GradeBook | 10 | 1 | [10 empty] | 11
Home |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 3
ImportStatus |  | 1 | [10 empty] | 1
IssueAware | [7 empty] | 2 |  |  |  |  | 2
Library |  |  | 2 |  | 1 |  |  |  |  | 5 |  |  | 8
LMU |  |  | 6 | 21 | [8 empty] | 27
Location |  |  | 8 |  | 2 |  |  |  |  | 3 |  |  | 13
Log |  |  | 5 | 2 | [8 empty] | 7
ProgressionPlan |  |  | 3 | 4 | [8 empty] | 7
Registration |  |  | 1 | [9 empty] | 1
Reports | [10 empty] | 13 |  | 13
Security | [8 empty] | 1 | 6 |  |  | 7
Webuser |  |  |  | 9 | [8 empty] | 9
(blank)
Grand Total | 13 | 13 | 27 | 39 | 12 | 1 | 5 | 2 | 1 | 37 | 15 |  | 165
Status | Count | % Distribution
Not Started | 39 | 25.2%
TCR Testing In Progress | 37 | 23.9%
Development In Progress | 26 | 16.8%
Dev Bug Fix In Progress | 13 | 8.4%
Dev PR In Review | 11 | 7.1%
Waiting for Clarification | 11 | 7.1%
Prod Deployed FF OFF | 5 | 3.2%
TCR Bug PR In Review | 1 | 0.6%

## All Handson WorkShop-May-Sep
Module | Modules/ Pages | US# | Sprint | POC | PR | Status | PR Raised Date | First PR Response Date | PR Approved Date | PR Merged Date | Dependency | Planned Release Date | Code Freeze Date | Actual Release Date | Release Type | Dependency PR Number | Aging (Days) | Additional Comments | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | Copilot Usage as on 4th May | Copilot Usage as on 6th May | Copilot Usage as on 7th May | Copilot Usage as on 8th May | Copilot Usage as on 13th May | Copilot Usage as on 19h May | Copilot Usage as on 29th May | Copilot Usage as on 5th Jun
Assessment | assessments\checkMyWork\submissions.aspx.cs | 1043225 | 2.5 | Vijay | 8886 | TCR Testing In Progress | 2026-05-27 | 2026-05-29 | 2026-06-02 | 2026-06-02 | Yes | 2026-05-28 | 2026-05-21 | 2026-06-11 |  | 8846 8872 8868 |  | Delayed release because of Shared Control dependencies |  | Sohith is on leave | Dev Inprogress (70% to 75%) + out of 8 RAD controls 8 is done + fixing functionality issue | Vijay to complete this page + Raise PR + Fix CoPilot comments + Test with QE in local Dev is completed + Yet to create shared controls | Create shared controls in progress + Yet to raise PR | Dev completed for Assessment 2 pages + Yet to raise PR | PR 8886 created; not assigned to Catalyst yet | Submit to Catalyst | Yet to raise to catalsyt + Fix copilot comments + fixed merge conflicts + fixed copilot comments | reviwe is done + fixed PR comments + Testing in progress | PR in Progress | received & fixed merge conflicts + copilot comments(twice) | [5 empty] | Please resolve the merge conflicts, prioritize and complete this | Submitted to Catalyst | Received & fixed conflicts + PR comments fixed + reverted |  |  |  | bug received in TCR + fixed |  |  |  |  | 52%
Assessment | assessments\import.aspx.cs | 989551 | 2.3 | Anil | 8798 | TCR Testing In Progress | 2026-05-04 | 2026-05-29 | 2026-05-29 | 2026-05-29 | No | 2026-05-28 | 2026-05-21 | 2026-06-11 |  |  | 19 | Delayed release because of Shared Control dependencies | 2026-05-04: Rasied PR(8798) + Copilot comments fixed + Abhijit Reviwed PR; 2026-05-05: QE testing completed on local, 1 issue found related to document upload, yet to fix; 2026-05-07: Anil to resolve merge conflict and then submit to Catalyst Resolved bug + Verified with QE + Copilot comments fix in progress; 2026-05-11: waiting for PR comments; 2026-05-12: Sick Leave; 2026-05-13: PR approved by Catalyst, showing merge conflicts, Abhijit to review and merge; 2026-05-14: dependency on shared controls; 2026-05-18: dependency on shared controls; 2026-05-26: yet to fix conflicts + revert to catalyst; 2026-05-27: Please resubmit to Catalyst; 2026-05-28: Submitted to Catalyst; 2026-06-04: TCR bug received |  | 26%
Assessment | assessments\assessment.aspx.cs | 989551 | 2.3 | Vijay | 8807 | Prod Deployed FF OFF | 2026-05-05 | 2026-05-06 | 2026-05-09 | 2026-05-09 | Yes | 2026-05-28 | 2026-05-21 | 2026-05-28 | Dark | 8846 8872 8868 |  | On track - Dask release because of dependency on Shared Control | 2026-05-04: Completed development + Yet to raise PR; 2026-05-05: Raised PR(8807) + Fixed Copilot comments + PR is reviwed by abhijit and raised to catalyst; 2026-05-06: PR 8751 - PR comemnts received and fix in progress; 2026-05-07: PR 8807 - Received conflicts + PR comments(Yet to start); 2026-05-08: PR is approved + Merged; 2026-05-12: Yet to create shared control; 2026-05-13: Created shared controls + Testing is done; 2026-05-14: Merged
Assessment | assessments\checkMyWork\checkMyWork.aspx.cs | 1043225 | 2.5 | Vijay | 8886 | TCR Testing In Progress | 2026-05-27 | 2026-05-27 | 2026-06-02 | 2026-06-02 | Yes | 2026-05-28 | 2026-05-21 | 2026-06-11 |  | 9009 |  | Delayed release because of Shared Control dependencies |  | Yet to start | Dev Inprogress (70% to 75%) + out of 8 RAD controls 8 is done + fixing functionality issue | Vijay to complete this page + Raise PR + Fix CoPilot comments + Test with QE in local Dev is completed + Yet to create shared controls | Create shared controls in progress + Yet to raise PR | Dev completed for Assessment 2 pages + Yet to raise PR | PR 8886 created; not assigned to Catalyst yet | Submit to Catalyst | Yet to raise to catalsyt + Fix copilot comments + fixed merge conflicts + fixed copilot comments | review is done + fixed PR comments + Testing in progress | With catalyst | Reviewed by abhijit | Received + fixed conflicts | resovled conflicts + comments (split into 2) |  |  |  | Please resolve the merge conflicts, prioritize and complete this | Submitted to Catalyst | Received & fixed conflicts twice + PR comments fixed + reverted
Assessment | assessments\questions.aspx.cs | 989551 | 2.4 | Rizwana | 8877 | Prod Deployed FF OFF | 2026-05-11 | 2026-05-13 | 2026-05-14 | 2026-05-14 | Yes | 2026-05-28 | 2026-05-21 | 2026-05-28 | Dark | 8846 8872 8868 |  | On track - Dask release because of dependency on Shared Control | 2026-05-08: Yet to start on Dev; 2026-05-11: Dev is completed + QE testing is in progress + PR created + reveiw is done; 2026-05-13: Resolved Catalyst review comments and reverted for review; 2026-05-14: approved + fix Merge conflicts + comments; 2026-05-15: Merged; 2026-05-21: bug from TCR fixed + 8952 (PR); 2026-05-29: change look and fill - vijay is progressing in creation of PR
Assessment | assessment\manager.aspx.cs | 989551 | 2.3 | Vijay | 8751 | Prod Deployed FF OFF | 2026-04-29 | 2026-05-12 | 2026-05-14 | 2026-05-14 | Yes | 2026-05-28 | 2026-05-21 | 2026-05-28 | Dark | 8846 8872 8868 |  | On track - Dask release because of dependency on Shared Control | 2026-05-07: fix conflicts - resolve co-pilot comments - Ask catalyst's team to review (currently I requested him to pause his review as we got conflicts and co-pilot comments) Complete PR 8751, and fix the issues Resolved conflicts + Copilot comments fix in progress; 2026-05-08: Copiot comments Fixed + Conflicts fix in progress; 2026-05-11: resolved conflicts + reverted(11 May); 2026-05-12: 8751 - fixed copilot comments + fixed PR comments; 2026-05-13: Changes implemented + Ask Catalyst to approve the PR(still same); 2026-05-14: Approved; 2026-05-15: Merged; 2026-05-22: bug fix completed + yet to connect vth QE; 2026-05-29: Recieved 1 bug + Fixed + QE verified |  | 39%
Assessment | assessments\reports\assessmentAnswersAccepted.aspx.cs | 989551 | 2.4 | Sohith | 8889 | TCR Testing In Progress | 2026-05-12 | 2026-05-19 | 2026-06-01 | 2026-06-01 | No | 2026-05-28 | 2026-05-21 | 2026-06-11 |  |  | 13 | Delayed release because of Shared Control dependencies | 2026-05-12: Dev completed + internal QE is done + Yet to create PR + yet to fix copilot comments; 2026-05-13: Resolve CoPilot comments + Raise PR + review with Abhijit + submit to Catalyst; 2026-05-14: Raised to catalyst+ Fixed PR comments + Fixed conflicts Fixed merge conflicts & copilot comments; 2026-05-15: Fix Mereg conflicts; 2026-05-18: in Progress; 2026-05-19: First approval received + Fixed merge conflicts+ dependency on shared controls; 2026-05-25: fixed conflicts + Yet to raise to catalyst; 2026-05-27: Please resolve the merge conflicts, prioritize and complete this; 2026-05-28: There are existing bugs + fixed bugs + QE testing yet to be done + PR is vth ascendion; 2026-05-29: fixed bug + PR is vth catalyst + Fixed merge conflicts |  |  |  |  | 100%
Assessment | assessments\reports\assessmentQuestionAnalysis.aspx.cs | 989551 | 2.4 | Sohith | 8889 | TCR Testing In Progress | 2026-05-12 | 2026-05-19 | 2026-06-01 | 2026-06-01 | No | 2026-05-28 | 2026-05-21 | 2026-06-11 |  |  | 13 | Delayed release because of Shared Control dependencies | 2026-05-12: Dev completed + internal QE is done + Yet to create PR + yet to fix copilot comments; 2026-05-13: Resolve CoPilot comments + Raise PR + review with Abhijit + submit to Catalyst; 2026-05-14: Raised to catalyst+ Fixed PR comments + Fixed conflicts; 2026-05-15: Fix Mereg conflicts; 2026-05-18: in Progress; 2026-05-19: First approval received + Fixed merge conflicts+ dependency on shared controls; 2026-05-25: fixed conflicts + Yet to raise to catalyst; 2026-05-27: Please resolve the merge conflicts, prioritize and complete this; 2026-05-28: There are existing bugs + fixed bugs + QE testing yet to be done + PR is vth ascendion; 2026-05-29: fixed bug + PR is vth catalyst + Fixed merge conflicts; 2026-06-04: bug received in TCR
IssueAware | Bug fixes in .aspx pages |  |  | Vijay | 8842 | Prod Deployed FF ON | 2026-05-06 |  | 2026-05-08 | 2026-05-08 | No | 2026-05-14 | 2026-05-08 | 2026-05-14 | Live |  |  |  | 2026-05-07: IssueAware - IssueSystem bug fix --> check with QA --> Raise PR --> Resolve Co-pilot comments --> Post it in catalyst (CSS changes only) Fixed bug + Reverted to catalyst; 2026-05-08: 8842 + 8852 = Merged |  |  | 44%
AssetAware | assetHistory.aspx | 1042808 | 2.3 | Mizan | 8814 | Prod Deployed FF OFF | 2026-05-05 | 2026-05-19 | 2026-05-19 | 2026-05-19 | No | 2026-05-28 | 2026-05-21 | 2026-05-28 | Dark |  |  | On track - Dask release because of dependency on Shared Control | 2026-05-04: Completed development + Creation of PR in progress; 2026-05-05: Raised PR(8814) + yet to get review for the PR + Copilot comments are fixed; 2026-05-07: Complete QE testing + Raised to Catalyst; 2026-05-13: Look for Catalyst comments + Reminded for approval twice still it is not approved(2nd level); 2026-05-18: Waiting for Catalyst approval; 2026-05-19: Merged |  |  | 33%
AssetAware | assetVendorAddressContact.aspx | 1049318 | 2.3 | Swarneem | 8864 | TCR Testing In Progress | 2026-05-08 | 2026-05-25 | 2026-05-25 | 2026-05-25 | No | 2026-05-28 | 2026-05-21 | 2026-06-11 |  |  | 10 | Delayed release because of extended time taken for PR review | 2026-05-05: Swarneem to take this page on 6th May; 2026-05-07: Can Swarneem start on this page?; 2026-05-08: Dev is completed + PR reviwed + PR (8864) + internal testing is done; 2026-05-11: Working on build issues; 2026-05-12: Working on build issues; 2026-05-13: Fixed build issues because of the shared control PR; 2026-05-14: twice fixed merge conflicts; 2026-05-15: waiting for catalyst approval; 2026-05-18: dependency on shared controls; 2026-05-25: Approved & Merged | 16% |  | 38% | 53% | 95%
Library | library/searchResults.aspx |  |  | Prem | 8795 | TCR Testing in progress | 2026-05-04 |  | 2026-05-25 | 2026-05-25 |  | 2026-06-11 | 2026-06-05 | 2026-06-11 |  |  |  | On Track - TCR Testing on progress | 2026-05-04: Raised PR(8795) + Copilot comments fixed Abhijit reveiwed PR + QE testing completed; 2026-05-07: Resolve CoPilot comments for this PR Resolved copilot comments + Reverted to catalyst; 2026-05-08: 8795 - Received copilot comments + Reverted back MErge conflicts fixed; 2026-05-11: Received conflicts + Done with conflicts; 2026-05-13: Look for Catalyst comments + No updates from catalyst; 2026-05-14: fixed merge conflicts + reverted; 2026-05-18: received PR comments + copilot comments fixed & reverted; 2026-05-19: PR approved; 2026-05-20: require 2nd approval (1st approval got revoked) recieved merge cinflicts but on monday we will raise to catalyst; 2026-05-25: Merged |  |  |  | 50% | 97%
Content | content\elmItemInteractive.aspx | 1049384 | 2.3 | Ramesh | 8815 | TCR Testing in progress | 2026-05-05 |  | 2026-05-14 | 2026-05-14 | No | 2026-06-11 | 2026-06-04 | 2026-05-28 | Dark |  | 6 | On Track - TCR Testing on progress | 2026-05-05: Development completed + PR Raised(8815) + Copilot comments fixed + PR reveiwed by abhijit + internal testing is done + raised to Catalyst; 2026-05-07: Look for Catalyst review comments, resolve comments as received Recived Merge conflicts fixed + Reverted to catalyst; 2026-05-08: Received PR comments + Fixed + approved; 2026-05-11: Merge conflicts fixed + waiting for one more approval; 2026-05-12: Catalyst need to approve again 8815 - Fixed merge conflicts; 2026-05-13: Resubmit to Catalyst for approval Still with catalyst; 2026-05-14: Fixed Merge conflicts + fixed copilot comments + again received merge conflicts(fixed) +Reverted thrice recieved merge conflicts; 2026-05-15: Merged; 2026-06-04: 1 TCR bug received | 18%
Content | content\hyperlink.aspx | 989555 | 2.3 | Rizwana | 8802 | TCR Testing in progress | 2026-05-04 |  | 2026-05-11 | 2026-05-11 | No | 2026-06-11 | 2026-06-04 | 2026-05-28 | Dark |  |  | On Track - TCR Testing on progress | 2026-05-04: Raised PR(8802) + Copilot comments +Abhijit Reviwed PR + QE testing is completed + raised to Catalyst; 2026-05-07: Catalyst team approved this PR. Rizwana to resolve conflict and get approval again Resolved merge conflicts + first round is approved + Kept in on hold (merge conflicts); 2026-05-08: 8802 is approved - Yet to merge (planned for 14th May release); 2026-05-11: Approved + Merge conflicts + Merged (11th May)
Content | content\timeline.aspx.cs | 1049384 | 2.3 | Rizwana | 8817 | TCR Testing in progress | 2026-05-05 |  | 2026-05-14 | 2026-05-14 | No | 2026-06-11 | 2026-06-04 | 2026-05-28 | Dark |  | 6 | On Track - TCR Testing on progress | 2026-05-05: Development completed +PR Raised(8817) + copilot comments fixed + internal testing is done + PR review is done by abhijit + raised to Catalyst; 2026-05-07: Look for Catalyst review comments, resolve comments as received Resolved merge conflicts + Fixed copilot comments; 2026-05-11: Merge conflicts fixed on 11May; 2026-05-13: PR approved; 2026-05-14: Merged | 13%
Content | content/grammarTool.aspx | 1049384 | 2.3 | Amol | 8818 | TCR Testing in progress | 2026-05-05 |  | 2026-05-14 | 2026-05-14 | Yes | 2026-06-11 | 2026-06-04 | 2026-05-28 | Dark | 9009 | 6 | On Track - TCR Testing on progress | 2026-05-05: Dev Completed + PR Raised(8818) + Fixed Copilot comments + Abhijit reveiwed PR + internal testing is done + raised to Catalyst; 2026-05-07: Look for Catalyst review comments, resolve comments as received + Amol to resolved conflicts Fixed Copilot comments + Fixed conflicts (reverted PR to catalyst); 2026-05-11: approved + Merge conflicts; 2026-05-12: On leave; 2026-05-13: Resolve merge conflicts + re-submit for approval to Catalyst; 2026-05-14: Merged; 2026-05-19: dependency on shared control PR |  |  |  | 45% | 85%
Content | content\sources\default.aspx.cs | 989555 | 2.3 | Amol | 8801 | Prod Deployed FF OFF | 2026-05-05 | 2026-05-07 | 2026-05-08 | 2026-05-08 | No | 2026-05-28 | 2026-05-21 | 2026-05-28 | Dark |  |  | Approved on the day of cuttoff day for 14 May release | 2026-05-04: Raised PR(8801) + Copilot Comments + Abhijit Reviwed PR + Raised to Catalyst; 2026-05-07: Look for Catalyst review comments, resolve comments as received Fixed copilot comments + Resolved conflicts; 2026-05-08: Merged; 2026-05-12: On leave | 18%
Security | Ongoing PRs + CoPilot Comments + Merge Conflicts |  |  | Prem | 8784, 8781, 8782, 8783 | TCR Testing in progress | [12 empty] | 2026-05-06: Security Bug fix in progress + Copilot comments fix completed + Connected with QE and suggested few changes which is fixed. Received PR comments for 8783 fix in progress 8783, 8784, 8781 - Copilot comments fix in progress; 2026-05-07: Complete all pending works for all the open PRs 8783 , 8784, 8782, 8781 Raised to catalyst 8781 - Received PR comments + fix in progress; 2026-05-08: 8781 - Resolved copilot + PR comments + reverted back + Approved 8782 - Resolved copilot + PR comments + reverted back; 2026-05-11: 8782- Received PR comments + Merge conflicts 8783 - Merge Conflicts; 2026-05-12: Fixed merge conflicts for 8783; 2026-05-13: Complete resolving all comments 8782 & 8784 - Approved 8783 - change fixed + reverted; 2026-05-14: 8782 - is with catalyst 8783 - Fixed merge confilcts + Mizan verified; 2026-05-18: In Progress with catalyst; 2026-05-19: 8782 is with catalyst; 2026-05-22: 8782- Received PR comments; 2026-05-25: 8782 - Merged; 2026-05-26: Reverted the bugs to QE; 2026-05-28: Security bug - 9016 PR is raised(addressbook bug along vth security bug) |  | 23%
Security | [5 empty] | TCR Testing in progress
Security | [5 empty] | TCR Testing in progress
Security | [5 empty] | TCR Testing in progress
Security | [5 empty] | TCR Testing in progress
Security | [5 empty] | TCR Testing in progress
Security | QE bug in TCR |  |  | Prem | 9016 | TCR bug PR in Review | [12 empty] | 2026-06-03: Please look if any change is requested by Catalyst No update from Catalyst; 2026-06-04: Receievd review comment + Copilot comment
GradeBook | GradeBook open Issues(deatils tab) SPA page |  |  | Amol | 8793 (merged), 8789 | Dev PR in review | [14 empty] | Gradebook PR(8793) - PR comments fix in progress + POPup bug fixes in progress Home page - PR comments fixed grammar page (Content) - PR comments fixed Enrollement page (Home) - PR comments fixed | Complete all the bug fixes by 5/7, target for 5/28 deployment 8793 - PR comments + Copilot comments fixed + PR reveiwed by abhijit + Reverted PR to catalyst team 8789 - coipilot comments fixed + Unit test & API breaking chages (fix in progress) | copilot comments fix in progress | Still facing conflicts in copilot | On leave | Fix merge conflicts + submit to Catalyst 8789 - Is with catalyst | Fixed 8793 conflicts & comments 8789 - Fixed Merge conflicts + reverted | 8789 - Rizwana fixed comments(dependency on other PRs) | In Progress | 8793 - Merge conflicts + PR review with abhijit |  | Working on PR comments for gradebook 1 bug fixed & PR raised 8949 | Fixed API issues + data issues in progress | Gradebook bug fix | Gradebook bug fix |  | Submitted to Catalyst (8789) | Bug fix for open & reopen bugs
Common | Setup QA Dev Env and guide others |  |  | Rizwana | 8762 8797 | TCR Testing in progress | [12 empty] | 2026-05-06: Gradebook - PR (8762) - bug fix is completed(PR Merged) + other bug fix in progress PR(8797) - issues resolved; 2026-05-07: 8762 - Merged; 2026-05-11: PR raised by amol + received PR comments + fixed conflicts; 2026-05-13: Complete dev setup |  | 19%
Home | home\pages\overdueLessons.aspx.cs |  |  | Rizwana | 8769 | TCR Testing in progress | 2026-04-29 | 2026-04-30 | 2026-05-14 |  |  | 2026-05-28 | 2026-05-22 | 2026-05-28 |  |  |  | On Track - TCR Testing on progress | 2026-05-06: Home - PR (8769 ) - fixed Copilot comments + merge conflicts fix in progress; 2026-05-07: Rizwana to Resolve conflicts Fixed PR comments + Rverted to catalyst; 2026-05-08: Approved; 2026-05-11: Approved + Merge conflicts fixed; 2026-05-12: Approval reverted, need to resubmit; 2026-05-13: Resubmit to Catalyst for approval ( still pending); 2026-05-14: Merged
Enrollment | enrollment\placement\default.aspx.cs | 989556 | 2.4 | Rizwana | 8895 | TCR Testing in progress | 2026-05-13 |  | 2026-06-01 |  | No | 2026-06-11 | 2026-06-04 | 2026-06-11 |  |  | 17 | On Track - TCR Testing on progress | 2026-05-13: Dev completed + raised PR + Fixed copilot comments; 2026-05-14: QE testing done + Fixed Merge conflicts + fixed build issues twice recived merge conflicts + Comments; 2026-05-15: Fixed Merge conflicts; 2026-05-18: In Progress; 2026-05-19: Fixed merge conflicts recived twice; 2026-05-20: Approved; 2026-05-28: Please resolve the merge conflicts, prioritize and complete this received approval however fixed merge conflicts and reverted to catalyst |  |  | 35%
Location | location\gradebookWeightTypes.aspx.cs | 989655 |  | Prem | 8902 | TCR Testing in progress | 2026-05-14 |  | 2026-05-26 |  |  | 2026-08-06 |  | 2026-06-11 |  |  |  | On Track - TCR Testing on progress | 2026-05-04: Worked on PR's for security; 2026-05-05: Dev completed + Yet to connect with QE + Yet to raise PR + YEt to fix copilot comments + PR yet to be reiwed 8783 - Fixed Merge conflicts + Working on security PRs; 2026-05-13: Dev Completed + QE testing is completed + YEt to raise PR; 2026-05-14: Fixed Copilot comments + PR review yet to be done; 2026-05-18: In Progress with catalyst; 2026-05-19: Fixed merge conflicts; 2026-05-25: Approved; 2026-05-26: Merged
Location | location\skinProperties.aspx.cs | 989655 |  | Swarneem | 8887 | TCR Testing in progress | 2026-05-12 |  | 2026-05-25 |  |  | 2026-08-06 |  | 2026-06-11 |  |  |  | On Track - TCR Testing on progress | 2026-05-11: Worked on shared control PR(8872); 2026-05-12: Dev completed + QE testing is inprogress +Yet to raise PR+ yet to get PR review + yet to fix copilot comments 8872 - Fixed copilot comments; 2026-05-13: Resolved Catalyst comments + QA team to connected+ Created FF + Yet to review PR + Fix copilot comments; 2026-05-14: spacing issue to be fixed+ twice fixed merge conflicts; 2026-05-18: In Progress with catalyst; 2026-05-19: fixed PR comments & reverted; 2026-05-21: PR Approved; 2026-05-22: Yet to Merege(Mizan); 2026-05-25: Merged
Location | location\security\roleAccessRestrictions.aspx.cs | 989655 |  | Prem | 8902 | TCR Testing in progress | 2026-05-14 |  | 2026-05-26 |  |  | 2026-08-06 |  | 2026-06-11 |  |  |  | On Track - TCR Testing on progress | 2026-05-13: Dev Completed + QE testing is completed + YEt to raise PR; 2026-05-14: Fixed Copilot comments + PR review yet to be done; 2026-05-18: In Progress with catalyst; 2026-05-19: Fixed merge conflicts; 2026-05-25: Recieved and fixed conflicts; 2026-05-26: Merged
Location | location\createHousehold.aspx.cs |  |  | Swarneem |  | Development Inprogress | [11 empty] | Development in Progress | 2026-05-14: Yet to start dev(AVAA is down) + analysis is completed; 2026-05-15: Yet to start dev; 2026-05-18: Dev in progress; 2026-05-19: Dev completed + Yet to do internal testing; 2026-05-25: Yet to do internal testing; 2026-05-28: received issues from QE; 2026-05-29: Yet to fix issues
Extended Field | extendedField\categories.aspx | 989557 | 2.5 | Sohith | 9009 | TCR Testing in progress | 2026-05-28 |  | 2026-06-02 |  |  | 2026-06-11 | 2026-06-04 | 2026-06-11 |  |  |  | On Track - TCR Testing on progress | 2026-05-14: AVAA is down yet to start dev; 2026-05-15: AVAA is down however planned to work with copilot (Yet to start); 2026-05-18: Vijay is on leave assigned to sohith; 2026-05-19: shared control creation is in progress; 2026-05-20: Created shared controls + Yet to connect with QE; 2026-05-25: Dev completed; 2026-05-26: Yet to create PR + Yet to connect vth QE + Fix copiliot comments; 2026-05-28: PR raised to catalyst
Extended Field | extendedField\categories.aspx | 989557 | 2.5 | Sohith | 9009 | TCR Testing in progress | 2026-05-28 |  | 2026-06-02 |  |  | 2026-06-11 | 2026-06-04 | 2026-06-11 |  |  |  | On Track - TCR Testing on progress | 2026-05-19: creating new shared controls (50 - 60%); 2026-05-20: Dev is completed + Yet to connect vth QE; 2026-05-21: completed part 1 for the shared control creation + part 2 is in progress + Yet to connect with QE; 2026-05-22: Part 2 completed + Yet to connect vth QE + YEt to raise PR; 2026-05-25: code clean up is done; 2026-05-29: Shared Control
Location | addressContact / coursePlacementInformation/ createHousehold |  |  | Swarneem |  | Development Inprogress | [11 empty] | Development in Progress | 2026-05-19: Dev completed + Yet to do internal testing; 2026-05-22: coursePlacementInformation - page is not available; 2026-05-25: Yet to do internal testing; 2026-05-26: internal testing is completed for addresscontact + Received bugs for create household page; 2026-05-28: courseplacementinformation is not accessable and working with QE
Location | locations / locationCalendar / locationExtended |  |  | Amol | 8947 | Development Inprogress | [11 empty] | Development in Progress | 2026-05-20: locations = Dev completed + created PR + yet to connect with QE locationcalendar & locationextended = awating for clarifications; 2026-05-21: locationcalendar - yet to start dev; 2026-05-22: locationcalendar - analysis completed; 2026-05-25: Yet to start Dev for locationcalendar; 2026-05-28: locations - dev is completed & created PR(internally) locationCalendar - Dev in progress(50%) LocatioExtended - Dev Yet to start; 2026-06-02: Prem started to work onlocation Extended & location calendar
Location | overview |  |  | Prem |  | Development Inprogress | [11 empty] | Development in Progress | 2026-05-18: Yet to start Dev; 2026-05-26: Yet to start Dev; 2026-05-28: Analysis is done; 2026-05-29: Dev completed + QE is done + Yet to create PR
Common | Shared Control |  |  | swarneem | 8846 | TCR Testing in progress | 2026-05-12 | 2026-05-15 | 2026-05-25 |  |  | 2026-05-28 | 2026-05-21 | 2026-06-11
Common | Shared Control |  |  | swarneem | 8872 | TCR Testing in progress | 2026-05-12 | 2026-05-21 | 2026-05-21 |  |  | 2026-05-28 | 2026-05-21 | 2026-06-11
Common | Shared Control |  |  | swarneem | 8868 | TCR Testing in progress | 2026-05-12 | 2026-05-15 | 2026-05-20 |  |  | 2026-05-28 | 2026-05-21 | 2026-06-11 |  |  |  |  | 2026-05-07: Shared controls PR - added icons + fixed few issues + fixd copilot comments; 2026-05-13: Look for Catalyst comments; 2026-05-14: Fixed PR comments; 2026-05-15: Received PR comments & fixed + fixed copilot comments; 2026-05-19: PR comments fixed & reverted 8868 - Bug fix in progress; 2026-05-20: 8868 - Merged; 2026-05-21: testing + merging; 2026-05-22: 8846 - Rceived PR comments QE raised bug + Fixed + committed; 2026-05-25: 8846 - Merged
Location | permissionVisibility |  |  | Rizwana |  | Out of scope | [12 empty] | 2026-05-29: Out of scope
Location | location |  |  | Rizwana |  | Out of scope | [12 empty] | 2026-05-29: Out of scope
Extended Field | extendedField\calculationGroups.aspx | 989557 | 2.5 | Sohith | 8917 9059 | Dev PR in Review | [5 empty] | 2026-06-25 | 2026-06-19 |  |  |  |  | Development in Progress | 2026-05-11: Assessment bugs fixed + PR's creation + internal testing for bug is done; 2026-05-13: Dev is completed; 2026-05-14: connected with QE + Yet to create PR + Yet to fix copilot comments Fixed FF issue + QE raised few bugs and fixed; 2026-05-15: Dependency on shared controls unable to create PR; 2026-05-18: Dependency on shared controls unable to create PR; 2026-05-19: creating new shared controls; 2026-05-20: Created shared controls + Yet to connect with QE; 2026-05-26: Yet to create PR + Yet to connect vth QE + Fix copiliot comments; 2026-06-03: Please resolve merge conflict, complete the PR and submit to Catalyst by EOD PR yet to raise to Catalyst; 2026-06-04: testing done + dev bug fix done + yet to be reviwed by abhijit |  |  | 12% | 100%
Extended Field | extendedField\fieldHistory.aspx.cs | 989557 | 2.5 | Sohith | 8917 9059 | Dev PR in Review | [5 empty] | 2026-06-25 | 2026-06-19 |  |  |  |  | Development in progress | 2026-05-14: AVAA is down and couldnt start dev; 2026-05-15: Dev is completed; 2026-05-18: Yet to create PR + QE testing testing + Copilot comments; 2026-05-19: PR reviwed; 2026-05-20: Yet to create PR; 2026-05-21: fixed issues + connect with QE + abhijit gave review comments (fixed); 2026-06-03: Please resolve merge conflict, complete the PR and submit to Catalyst by EOD PR yet to raise to Catalyst; 2026-06-04: testing done + dev bug fix done + yet to be reviwed by abhijit
Extended Field | extendedField\default.aspx.cs | 989557 | 2.5 | Anil | 9017 | Dev PR in Review | [5 empty] | 2026-06-25 | 2026-06-19 |  |  |  |  | Development in progress | 2026-05-19: Yet to start Dev; 2026-05-20: Yet to start Dev; 2026-05-22: Yet to start Dev; 2026-05-25: Yet to start; 2026-05-26: Dev in progress(50%) + dependency on multiple shared controls; 2026-05-28: Dev completed + QE testing done + Received issues & fixed; 2026-05-29: Retesting done + Create PR(dependency on 9009); 2026-06-03: PR 9009 is merged. Please create the PR, complete QE check and internal reviewed, then submit to Catalyst by EOD; 2026-06-04: Issues fixed + Copilot comments fix in progress
Extended Field | extendedField\extendedField.aspx | 989557 | 2.5 | Sohith | 9059 | Dev PR in Review | [5 empty] | 2026-06-25 | 2026-06-19 |  |  |  |  | Development in progress | 2026-05-19: Dev completed 50% + dependency on shared control creation; 2026-05-20: Dev is completed + dependency on shared controls; 2026-05-22: yet to integrate once the shared controls is developed; 2026-05-28: default + Extended field = Yet to raise PR(dependency on 9009); 2026-06-03: Please create the PR, complete QE check and internal reviewed, then submit to Catalyst by EOD PR yet to raise to Catalyst; 2026-06-04: testing done + dev bug fix done + yet to be reviwed by abhijit
Enrollment | enrollment\placement\rejectReason.aspx.cs | 989556 | 2.4 | Amol |  | Waiting for clarification |  |  |  |  | Waiting for clarification from Pearson | [6 empty] | Waiting for clarification from Pearson | 2026-05-13: Start development; 2026-05-14: AVAA is down and couldnt start dev; 2026-05-15: Dev to start; 2026-05-18: Dev to start - awaiting for clarification from pearson; 2026-05-19: still waiting for response; 2026-05-20: still waiting for response; 2026-06-03: Please hold on to this page for now and proceed with the other pages
AssetAware | assetvendor.aspx |  |  | Swarneem |  | Out of scope | [12 empty] | 2026-05-05: As there is no RAD controls in this page(out of scope); 2026-05-20: Worked on shared controls PR
Library | library/userSelector.aspx |  |  | Prem |  | Out of scope | [12 empty] | 2026-05-05: Out of scope however prem is working on security PR's. Prem will create new PR(s) with these fixes.
Content | content\affiliate.aspx.cs |  |  | Rizwana |  | Out of scope | [12 empty] | 2026-05-08: Analysis in progress + No RAD controls(out of scope)
Content | content\affiliates.aspx.cs |  |  | Amol |  | Out of scope | [12 empty] | 2026-05-08: Analysis in progress + No RAD controls + Out of Scope; 2026-05-12: On leave | [7 empty] | 1040961(ADO)
Content | content\chrome\online\footer.aspx.cs |  |  | Ramesh |  | Out of scope | [12 empty] | 2026-05-08: to check if it falls on .ASP or React Partial pages and could see it direct (out of scope)
Content | content\chrome\printed\options.aspx.cs |  |  | Ramesh |  | Out of scope | [12 empty] | 2026-05-08: to check if it falls on .ASP or React Partial pages and could see it direct (out of scope) |  | 0.22
Home | home\caretaker.aspx.cs |  |  | Rizwana |  | Out of scope | [12 empty] | 2026-05-13: As it is migrating to SPA application marked as out of scope
Enrollment | enrollment\registration\registrationLocation.aspx.cs | 989556 |  | Sagar |  | Out of scope | [12 empty] | 2026-05-11: Yet to get access; 2026-05-12: Sick leave; 2026-05-13: Start development; 2026-05-26: Sick Leave; 2026-05-27: Sick Leave
Enrollment | enrollment\registration\registrationLocations.aspx.cs | 989556 |  | Amol |  | Out of scope | [12 empty] | 2026-05-12: On leave; 2026-05-13: Starting this today
Extended Field | extendedField\importData.aspx | 989557 |  | Swarneem |  | Out of scope | bar: 2026-05-04 to 2026-05-29
FORUM | FORUM |  |  | Anil |  | Development Inprogress | [11 empty] | Development in Progress | Sohith is on leave | As Sohith is on leave anil picked this page and dev is in progress | Anil is facing issue with laptop and working with IT team to fix | Need to be moved to someone else to start the development | Dev started | Dev started(100%) + connected with QE + identified 3 bugs | Sick Leave | out of 2 shared controls 1 is done with integration | Forum PR 33 splint into 2 PR's + Shared Controls ( 1 yet to complete) - Inprogress | Worked on FORUM | Yet to get PR review Worked on FORUM - fixed all issues | Partial issues fixed for shared control + Fixed few issues in FORUM | YEt to fix data + pagination sorting issues in FORUM | Forum | Sick Leave | Forum | [7 empty] | issues yet to fix |  |  | ` | 38% | 55% | 95%
FORUM | FORUM |  |  |  |  | Dev Bug fix in progress
FORUM | FORUM |  |  |  |  | Dev Bug fix in progress
FORUM | FORUM |  |  |  |  | Dev Bug fix in progress
Assessment | assessments\default.aspx.cs | 1043225 | 2.5 | Vijay | 9006 | TCR Testing In Progress | 2026-05-28 | 2026-06-03 | 2026-06-03 |  | Yes | 2026-05-28 | 2026-05-21 | 2026-06-11 |  | 9009 |  | Delayed release because of Shared Control dependencies | 2026-05-20: dev is completed + fixed issues + YEt to connect with QE; 2026-05-21: fixed UI issues; 2026-05-25: Sick Leave; 2026-05-26: Sick Leave; 2026-05-27: Can we come up with alternate plan? This should be prioritized asap; 2026-05-28: Complete this PR and submit to catalyst; 2026-05-29: Abhijit to review; 2026-06-03: Please look if any change is requested by Catalyst Copliot comments fixed + Fix in progress on conflicts; 2026-06-04: Approved + Merged Bug(3) received in TCR |  |  |  |  | 66%
Assessment | assessments\questionManager.aspx.cs | 1043225 | 2.5 | Rizwana | 8888 9002 | Dev PR in Review | 2026-05-28 |  |  |  | Yes | 2026-05-28 | 2026-05-21 | 2026-06-25 |  | 9009 |  | Dependency on PR 9009, which got approved on 6/2. Could not squeeze into other PRs because of PR size limitation. | 2026-05-08: Yet to start on Dev; 2026-05-11: On leave; 2026-05-12: On leave; 2026-05-13: Dev completed + QE testing is done+ raised PR + fixed copilot comments; 2026-05-14: Manish reviewed PR + Abhijit to review + Fix merge conflicts + comments; 2026-05-15: abhijit reviwed + Fixed copilot comments; 2026-05-18: PR review in progress + dependenc on shared controls; 2026-05-27: Please resolve the merge conflicts, prioritize and complete this; 2026-05-28: Submitted to Catalyst closed 8888 & merged with 9002; 2026-06-03: Please look if any change is requested by Catalyst Merge conflicts fixed |  |  |  | 52% | 87%
Assessment | assessment\analysis.aspx.cs | 1043225 | 2.5 | Sohith | 8865 9002 | Dev PR in Review | 2026-05-28 |  |  |  | Yes | 2026-05-28 | 2026-05-21 | 2026-06-25 |  | 9009 |  | Dependency on PR 9009, which got approved on 6/2. Could not squeeze into other PRs because of PR size limitation. | 2026-05-08: Dev Completed + PR Created(8865) + Copilot comments fixed; 2026-05-11: Abhijit need to review + yet to raise to catalyst; 2026-05-12: Sick Leave; 2026-05-13: Check on PR 8865, to be raised to catalyst new to be review by Abhijit; 2026-05-14: Yet to review PR by abhijit + Fix conflicts; 2026-05-18: in Progress; 2026-05-19: Yet to fix space issues; 2026-05-26: PR Yet to raise to catalyst; 2026-05-27: Please resolve the merge conflicts, prioritize and complete this; 2026-05-28: Please resolve the merge conflicts, prioritize and complete this Sohith merged along with other pages and rasied PR; 2026-05-29: authorization issues fixed + unit testing is in progress + QE is done; 2026-06-03: Please look if any change is requested by Catalyst; 2026-06-04: Received & fixed merge conflicts
IssueAware | Bug fixes in .aspx pages |  |  | Vijay | 8852 | Prod Deployed FF ON | 2026-05-07 |  | 2026-05-08 |  | No | 2026-05-14 | 2026-05-08 | 2026-05-14 | Live |  |  |  | 2026-05-07: Issue aware Bug fix is completed + Submitted to abhijit for review + Roll back for bug fixes; 2026-05-13: Completed all bug fixes; 2026-05-14: cross check on module issue aware; 2026-05-15: No FF added for demo (issueaware); 2026-05-18: No FF added for demo (issueaware)
AVAA Agents | copilot PR reviews & PR validation |  |  | Mizan |  | Development Inprogress | [12 empty] | 2026-05-13: analysis in progress; 2026-05-18: In Progress
AssetAware | assetAware\expressassesthistory.aspx | 1049318 | 2.4 | Swarneem | 8828 | TCR Testing In Progress | 2026-05-06 |  |  |  | Yes | 2026-05-28 | 2026-05-21 | 2026-06-25 |  | 8846 8872 8868 | 20 | Delayed release because of extended time taken for PR review | 2026-05-06: Dev Completed + PR Raised (8828) + Copilot comments fix in progress + internal testing is completed; 2026-05-07: Complete PR 8828 and raise to Catalyst (WIP) PR to be reveiwed with abhijit; 2026-05-11: with catalyst; 2026-05-12: Build failing because of the shared control not deployed to TCR through PR 8846; 2026-05-13: Look for Catalyst comments; 2026-05-14: dependency on shared controls; 2026-05-18: dependency on shared controls; 2026-05-27: Please resolve the merge conflicts, prioritize and complete this; 2026-05-28: Submitted to Catalyst; 2026-06-03: Please look if any change is requested by Catalyst
AssetAware | assets.aspx | 1049318 | 2.4 | Swarneem | 8828 | TCR Testing In Progress | 2026-05-06 | 2026-06-02 | 2026-06-04 |  | Yes | 2026-05-28 | 2026-05-21 | 2026-06-25 |  | 8846 8872 8868 | 20 | Delayed release because of extended time taken for PR review | 2026-05-06: Dev is completed(90%) + Yet to raise PR + QE connect is done however there are few issus found (fix inprogress); 2026-05-07: Complete this page + Raise PR + Fix CoPilot comments + Test with QE in local What is PR# for this page? Dependency on location tree and facing issues in icon loading (PR not raised); 2026-05-08: Dev Testing to be done + QE testing to be done+ Location tree model changes and date picker need to verify; 2026-05-11: Yet to raise PR; 2026-05-12: Yet to raise PR; 2026-05-13: PR to be raised; 2026-05-14: dependency on shared controls; 2026-05-18: dependency on shared controls; 2026-05-27: Please prioritize and create PR; 2026-05-28: Please prioritize and create PR assests + assethistory merged into 8828; 2026-06-03: Please look if any change is requested by Catalyst; 2026-06-04: PR approved
Library | library/resource.aspx |  |  | Swarneem | 8838 | Development Inprogress | 2026-06-03 |  |  |  |  | 2026-07-09 | [5 empty] | Merge Conflict | 2026-05-04: Completed development + Yet to raise PR; 2026-05-05: Created PR and copilot comments fix in progress; 2026-05-07: What is PR# for this page? Complete this development, raise PR, fix CoPilot comments PR comments Fix in progress; 2026-05-08: Retesting needs to be done (cross check not to break anything); 2026-05-11: yet to raise to catalyst; 2026-05-12: yet to fix build issues + PR yet to raise to catalyst; 2026-05-13: Fix build issues because of the shared control PR; 2026-05-14: dependency on shared controls; 2026-05-18: dependency on shared controls; 2026-05-27: Please resolve the merge conflicts, prioritize and complete this; 2026-05-29: Fixed merge conflicts + YEt to fix copilot comments; 2026-06-03: Please resolve merge conflict, complete the PR and submit to Catalyst by EOD. Can we merge this with 8876? 8876 is closed by prem; 2026-06-04: 8838 - commit code is done | 20% | 28%
Library | library\category.aspx.cs |  |  | Prem | 8876 8838 | Development Inprogress | 2026-06-03 |  |  |  |  | 2026-07-09 | [5 empty] | Merge Conflict | 2026-05-08: Dev completed + QE testing is done + QE raised few suggestions fix in progress; 2026-05-11: Yet to raise PR; 2026-05-12: will be on onhold until the shared control PRs are approved; 2026-05-18: dependency on shared control PR; 2026-05-26: PR Yet to raise to catalyst; 2026-05-27: Please resolve the merge conflicts, prioritize and complete this; 2026-05-28: 8876 will be closed as swarneem is working to merge on couple of pages in single PR; 2026-06-03: Please resolve merge conflict, complete the PR and submit to Catalyst by EOD Merge conflicts fixed + PR raised to catalyst
Library | [5 empty] | TCR Testing in progress | bar: 2026-05-12
Library | [5 empty] | TCR Testing in progress | bar: 2026-05-12
Library | [5 empty] | TCR Testing in progress | bar: 2026-05-12
Library | [5 empty] | TCR Testing in progress | bar: 2026-05-12
Content | content\captionedVideoItem.aspx.cs | 1049384 | 2.4 | Ramesh | 8804 | TCR testing in progress | 2026-05-04 |  |  |  | No | 2026-06-11 | 2026-06-04 | 2026-06-25 |  |  |  | Since PR is still under review, we cant release it on 11-Jun | 2026-05-04: Completed development + Yet to raise PR; 2026-05-05: Raised PR(8804) + Fixed Copilot comments; 2026-05-06: PR(8804 ) - fixed errors + QE setup still in progress.; 2026-05-07: Complete QE testing + Raise to Catalyst Received copilit comments fixed Fixed issues + Reverted to catalyst; 2026-05-08: Received Copilot comments + Merge Conflicts; 2026-05-11: Merge conflicts fixed + waiting for approval; 2026-05-13: Look for Catalyst comments still with catalyst; 2026-05-14: Fixed Merge conflicts + fix copilot comments + again received merge conflicts(in progress) thrice received Merge conflicts + Copilot comments; 2026-05-15: Fix Merge conflicts + copilot comments; 2026-05-18: Fixed issues & reverted; 2026-05-27: Please resolve the CoPilot comments, merge conflicts, prioritize and complete this; 2026-05-28: Submitted to Catalyst; 2026-06-03: Please address all the requested changes, resubmit to Catalyst by EOD Fixed merge conflicts & review comments
Content | content\sources\source.aspx.cs | 1049384 | 2.4 | Ramesh | 8804 | TCR testing in progress | 2026-05-04 |  |  |  | No | 2026-06-11 | 2026-06-04 | 2026-06-25 |  |  |  | Since PR is still under review, we cant release it on 11-Jun | 2026-05-08: Analysis in progress + Dev to start; 2026-05-11: Worked on Gradebook PR's + Content PR's; 2026-05-12: Dev completed + PR raised + yet to fix copilot comments + yet to connect with QE + Yet to get PR reviwe; 2026-05-13: 1. Review with Abhijit + submit to Catalyst 2. Start with Gradebook(SPA); 2026-05-14: Fixed Merge conflicts + fixed copilot comments + again received merge conflicts(fixed) + PR to be reviwed; 2026-05-15: Fix Merge conflicts + copilot comments; 2026-05-18: reveiew in progress with abhijit; 2026-05-27: Please resolve the CoPilot comments, merge conflicts, prioritize and complete this; 2026-05-28: Please resolve the CoPilot comments, merge conflicts, prioritize and complete this 8804 merged within this PR and closed 8881; 2026-06-03: Please address all the requested changes, resubmit to Catalyst by EOD Fixed merge conflicts & review comments
GradeBook | Bug fixes in .aspx pages |  |  | Amol |  | Dev Bug fix in progress | [11 empty] | Development in Progress | 2026-05-07: QE setup is done (Tinu); 2026-05-14: Fix all the conflicts + comments; 2026-05-18: Fixed issues & reverted; 2026-05-19: Bug fix; 2026-05-20: Gradebook bug fix; 2026-05-21: Gradebook bug fix; 2026-05-22: Ramesh - fixing defect issues + API issues in getting response 8789 - Rizwana resolvedon PR comments + copiliot comments + fixed build issues; 2026-05-25: Gradebook issues fix; 2026-05-26: Gradebook issues fix; 2026-05-27: Gradebook bug fix; 2026-05-28: Gradebook bug fix; 2026-05-29: Gradebook bug fix; 2026-06-03: Continue to work on bugfix
Home | home\pages\enrollment.aspx.cs |  |  | Amol | 8787 | Dev PR in Review | 2026-05-27 |  |  |  |  | 2026-07-09 | 2026-07-03 |  |  |  |  | On Track - PR Review in progress | 2026-05-06: Home page - PR (8787) comments fixed; 2026-05-07: Amol to Resolve conflicts Yet to work on this PR; 2026-05-08: PR reverted to catalyst; 2026-05-11: Received PR comments + Merge conflicts; 2026-05-12: On leave; 2026-05-13: New CoPilot comment from today, need to resolve (2plus copilot comments) 8787 - IS with catalyst; 2026-05-14: Still with catalyst; 2026-05-18: Still with catalyst(dependncy on shared controls); 2026-05-27: Please complete changes requested by Valeriy, resolve the merge conflicts, prioritize and complete this; 2026-05-28: Submitted to Catalyst; 2026-06-03: Please look if any change is requested by Catalyst Merge conflicts fixed & reverted
Enrollment | enrollment\placement\manager.aspx.cs | 989556 | 2.5 | Rizwana | 8932 8897 | Dev PR in Review | 2026-05-28 |  |  |  | Yes | 2026-06-11 | 2026-06-04 | 2026-06-25 |  | 1924-08-30 |  | Since the PR is inprogress cant release on 11 Jun | 2026-05-13: Emergency Leave(Ramesh); 2026-05-14: AVAA is down and couldnt start dev; 2026-05-15: Dev to start(unable to start dev); 2026-05-18: Dev completed; 2026-05-19: Yet to connect with QE + dependency in creating PR on shared controls; 2026-05-20: Yet to raise to catalyst + Yet to fix copilot comments; 2026-05-21: build is failing as their is dependency on shared controls; 2026-05-28: Please prioritize and complete this. Since Rizwana is ooo, can anyone take this up?; 2026-06-03: Please look if any change is requested by Catalyst No conflicts or comments
Enrollment | enrollment\registration\default.aspx.cs | 989556 | 2.5 | Amol | 8897 | Dev PR in Review | 2026-05-28 |  |  |  | Yes | 2026-06-11 | 2026-06-04 | 2026-06-25 |  | 1924-08-30 |  | Since the PR is inprogress cant release on 11 Jun | 2026-05-12: Sick Leave; 2026-05-13: Dev completed + Created PR + Bcoz of shared controls not raising this PR to catalyst; 2026-05-14: dependency on shared control PRs; 2026-05-18: dependency on shared control PRs; 2026-05-28: Please prioritize and complete this. Raised to catalyst; 2026-06-03: Please look if any change is requested by Catalyst Merge conflicts fixed & reverted
Location | www.connexus.com/location/dataview.aspx |  |  | Prem |  | Development Inprogress | [11 empty] | Development in Progress | 2026-05-14: AVAA is down and couldnt start dev; 2026-05-15: YEt to start Dev; 2026-05-18: Dev completed + Yet to create PR, QE, Copilot; 2026-05-19: QE team dont have test cases on this; 2026-05-20: Yet to check on test cases; 2026-05-21: Yet to check on test cases; 2026-05-22: Yet to check on test cases; 2026-05-25: Yet to check on test cases; 2026-05-29: Yet to create PR
External | Remove Feature Flag | 989650 |  | Mizan | 9045 | Dev PR in Review | 2026-06-02 |  |  |  | No | 2026-06-25 | 2026-06-19 | [5 empty] | 2026-05-11: Testing is done and good to close FF
ImportStatus | Remove Feature Flag | 989652 |  | Mizan | 9046 | Dev PR in Review | 2026-06-02 |  |  |  | No | 2026-06-25 | 2026-06-19 | [5 empty] | 2026-05-11: Testing is done and good to close FF
Location | createHouseholdLinkExistingUsers/extendedFields / |  |  | Prem |  | Development Inprogress | [11 empty] | Development in Progress | 2026-05-19: Dev compeleted (out of 2 pages 1 is done); 2026-05-20: Dev in progress + dependency on shared control PR(sohith); 2026-05-21: Complted part 1 for shared control PR Part 2 in progress; 2026-05-22: part 2 dev is completed + found a bug and fixed + yet to connect vth QE + Yet to create PR; 2026-05-25: code clean up is done; 2026-05-26: Yet to create PR + Yet to connect vth QE; 2026-05-29: Yet to create PR
Location | locationMembers |  |  | Rizwana |  | Development Inprogress | [11 empty] | Development in Progress | 2026-05-19: Dev is completed + YEt to connect with QE + Dependency on shared controls; 2026-05-22: Dev Completed + Yet to raise PR; 2026-06-04: create PR along with swarneem page
Gradebook | Bug Fix |  |  | Amol |  | Dev Bug fix in progress | [11 empty] | Development in Progress | 2026-05-22: Gradebook PR comments fixed; 2026-05-25: Gradebook PR comments; 2026-05-26: Bug fix in progress; 2026-06-03: Continue to work on bugfix
Communication | communication\webmail\webmailBox.aspx.cs | 989554 | 2.6 | Amol |  | Waiting for clarification |  |  |  |  | Waiting for clarification from Pearson | [6 empty] | Waiting for clarification from Pearson
Communication | communication\webmail\webmailBox.aspx.cs | 989554 | 2.6 | Amol | 8939 | Dev PR in Review | 2026-05-28 |  |  |  | Yes | 2026-05-28 | 2026-05-21 | 2026-06-25 |  | 9009 |  | Dependency on PR 9009, which got approved on 6/2. | 2026-05-19: Dev completed + Created PR+; 2026-05-20: Yet to connect with QE & fix copilot comments + Dependency on shared control; 2026-05-21: yet to connect vth QE; 2026-05-22: yet to connect vth QE; 2026-05-28: In Progress with Catalyst; 2026-06-03: Please look if any change is requested by Catalyst Merge conflicts fixed & reverted
Addressbook | Bug | 98963 | 2.6 | Swarneem | 9016 | Prod bug PR in Review | 2026-05-29 |  |  |  | No | 2026-06-25 | 2026-06-19 | [5 empty] | 2026-05-28: Bug received + fixed; 2026-05-29: QE connect is done; 2026-06-04: Reverted to catalyst group
Gradebook | [5 empty] | Dev Bug fix in progress
Gradebook | [5 empty] | Dev Bug fix in progress
Gradebook | [5 empty] | Dev Bug fix in progress
Gradebook | [5 empty] | Dev Bug fix in progress
Gradebook | [5 empty] | Dev Bug fix in progress
Gradebook | [5 empty] | Dev Bug fix in progress
Gradebook | [5 empty] | Dev Bug fix in progress
Gradebook | Bug Fixes |  |  | Amol |  | Dev Bug fix in progress | [11 empty] | Development in Progress | 2026-06-01: 20 bugs to fix(4 bugs fixed) + Merge branch; 2026-06-02: Resolve copilot comments + 16 bugs validate & fix; 2026-06-03: Continue to work on bugfix
Reports | reports\teacherCourseLevelExport.aspx.cs |  |  | Anil |  | Waiting for clarification | [5 empty] | 2026-09-03 | [5 empty] | Development in Progress | 2026-06-01: Dev in Progress(55%) + functionality testing is missing fix in progress; 2026-06-02: Regional holiday; 2026-06-04: shared controls is needed for this
Reports | reports\aggregateLogEntry.aspx.cs |  |  | Sagar |  | Waiting for clarification | [5 empty] | 2026-09-03 | [5 empty] | Development in Progress | 2026-06-01: Dev in Progress(85%); 2026-06-02: Dev completed + Mizan to review; 2026-06-03: As we didnt receive KT keeping on hold
Reports | reports\assessmentReport.aspx.cs |  |  | Sohith |  | Waiting for clarification | [5 empty] | 2026-09-03 | [5 empty] | Development in Progress | 2026-06-01: Waiting for clarification; 2026-06-02: Regional Holiday
Reports | reports\ceUniversitySectionReport.aspx.cs |  |  | Sohith |  | Waiting for clarification | [5 empty] | 2026-09-03 | [5 empty] | Development in Progress | 2026-06-01: Dev in progress(20%); 2026-06-04: Dev in progress(50%)
Reports | reports\sectionActivityReport.aspx.cs |  |  |  |  | Waiting for clarification | [5 empty] | 2026-09-03
Reports | reports\courseLessonObjective.aspx.cs |  |  |  |  | Waiting for clarification | [5 empty] | 2026-09-03
Reports | reports\institutionalStudentPerformanceExport.aspx.cs |  |  |  |  | Waiting for clarification | [5 empty] | 2026-09-03
Reports | reports\issueAwareDailyTime.aspx.cs |  |  |  |  | Waiting for clarification | [5 empty] | 2026-09-03
Reports | reports\resourceManagerExport.aspx.cs |  |  |  |  | Waiting for clarification | [5 empty] | 2026-09-03
Reports | reports\schoolDataReport.aspx.cs |  |  |  |  | Waiting for clarification | [5 empty] | 2026-09-03
Reports | reports\sectionLogEntryReport.aspx.cs |  |  |  |  | Waiting for clarification | [5 empty] | 2026-09-03
Reports | reports\SectionObjectivePerformance.aspx.cs |  |  |  |  | Waiting for clarification | [5 empty] | 2026-09-03
Reports | reports\teacherAssignmentReport.aspx.cs |  |  |  |  | Waiting for clarification | [5 empty] | 2026-09-03
ProgressionPlan | progressionPlan\academicRequirements.aspx.cs |  |  | Vijay |  | Development Inprogress | [11 empty] | Development in Progress | 2026-06-01: Dev in Progress(10%); 2026-06-02: Dev in Progress(30%) + 9006 fixed conflicts
ProgressionPlan | progressionPlan\academicRequirement.aspx.cs |  |  | Vijay |  | Development Inprogress | [11 empty] | Development in Progress | 2026-06-02: Dev in Progress(30%)
ProgressionPlan | progressionPlan\completionRequirements.aspx.cs |  |  | Sagar |  | Development Inprogress | [12 empty] | 2026-06-03: Dev Started; 2026-06-04: Half day leave; 2026-06-05: Sick Leave
ProgressionPlan | progressionPlan\progressionPlan.aspx.cs |  |  | Shivanshu |  | Not Started | [12 empty] | 2026-06-01: Sick leave; 2026-06-02: Sick leave + Local setup is done + PEDEV access pending; 2026-06-03: Dev Started(yes/No); 2026-06-04: Sick Leave; 2026-06-05: Sick Leave
ProgressionPlan | progressionPlan\progressionPlans.aspx.cs |  |  | Shivanshu |  | Not Started
ProgressionPlan | progressionPlan\confirmCopy.aspx.cs |  |  | Shivanshu |  | Not Started
ProgressionPlan | progressionPlan\webusers.aspx.cs |  |  | Sagar |  | Not Started
Log | log\categories.aspx |  |  | Manish | 9060 | Development Inprogress | [5 empty] | 2026-08-06 | [5 empty] | Development in progress | 2026-06-01: Sick Leave; 2026-06-02: Dev in Progress(50%); 2026-06-03: Dev Completed; 2026-06-04: QE testing is done + 2 issues raised & fixed + Copilot comments fixed
Log | log\contactTypes.aspx |  |  | Rizwana |  | Development Inprogress | [5 empty] | 2026-08-06 | [5 empty] | Development in progress | 2026-06-01: assessments\questionManager.aspx.cs - Received issues (fixed) Dev is completed &2 issues(dev) to be fixed; 2026-06-02: Regional holiday; 2026-06-04: QE is completed + 1 issue(QE) fixed
Log | log\logEntry.aspx |  |  | Ramesh |  | Development Inprogress | [5 empty] | 2026-08-06 | [5 empty] | Development in progress | 2026-06-01: Dev In Progress (20%); 2026-06-02: Regional holiday; 2026-06-04: Dev in progress(50%)
Log | log\logEntrySystems.aspx |  |  | Manish |  | Development Inprogress | [5 empty] | 2026-08-06 | [6 empty] | 2026-06-04: Dev Started
Log | log\myLogSettings.aspx |  |  | Rizwana |  | Development Inprogress | [5 empty] | 2026-08-06 | [6 empty] | 2026-06-04: Dev In Progress(55%)
Log | log\systemProperties.aspx |  |  | Ramesh |  | Not Started | [5 empty] | 2026-08-20
Log | log\areas.aspx |  |  | Manish |  | Not Started | [5 empty] | 2026-08-20
LMU | lmu\resourceResources.aspx.cs |  |  | Anil |  | Development Inprogress
LMU | lmu\resources.aspx.cs |  |  | Vijay |  | Development Inprogress
LMU | lmu\resourceSubCategory.aspx.cs |  |  | Sohith |  | Development Inprogress
LMU | lmu\resourceVersionVendor.aspx.cs |  |  | Anil |  | Development Inprogress
LMU | lmu\unit.aspx.cs |  |  | Vijay |  | Development Inprogress
LMU | lmu\unitsAndLessons.aspx.cs |  |  | Sohith |  | Development Inprogress
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | lmu\reports\sectionWithCoursesSummary.aspx.cs |  |  | Vijay |  | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
LMU | [5 empty] | Not Started
Location | locations / locationCalendar / locationExtended |  |  | Prem |  | Development Inprogress |  |  |  |  | Y |  |  |  |  | 9009 |  |  | 2026-06-01: Amol completed location calendar 50%, Prem to continue and start on location extended Prem completed Location extended + QE testing in progress Prem started dev for Location calendar - in Progress; 2026-06-02: Dev continue on Location Calendar page(In Progress) QE connect is done for Location Extended + 9009 PR comments fixed; 2026-06-03: Location calendar - issues fix in progress; 2026-06-04: Location calendar - issues fix in progress
Registration | registration.aspx.cs |  |  | Swarneem |  | Development Inprogress | [12 empty] | 2026-06-01: Library issues; 2026-06-02: Dev in progress(60%) + fixed PR comments for 8828; 2026-06-04: Dev completed + Yet to connect with QE
Attendance | editRecord.aspx |  |  | Swarneem |  | Not Started
Attendance | enterAttendance.aspx |  |  | Prem |  | Not Started
Attendance | reports/teacherAttendanceEntries.aspx |  |  | Prem |  | Not Started
Webuser | webuser\overview.aspx |  |  |  |  | Not Started
Webuser | webuser\webuser.aspx.cs |  |  |  |  | Not Started
Webuser | webuser\webusers.aspx.cs |  |  |  |  | Not Started
Webuser | webuser\roles.aspx.cs |  |  |  |  | Not Started
Webuser | webuser\reporting.aspx.cs |  |  |  |  | Not Started
Webuser | webuser\overview.aspx.cs |  |  |  |  | Not Started
Webuser | webuser\Roles_old.aspx.cs |  |  |  |  | Not Started
Webuser | webuser\sections.aspx.cs |  |  |  |  | Not Started
Webuser | webuser\webuser_old.aspx.cs |  |  |  |  | Not Started
Note on AK63: Abhijit Sil: Purnima, please check

## All Handson WorkShop-June (hidden)
Module | Modules/ Pages | US# | POC | Status | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | Copilot Usage as on 4th June
Gradebook | Bug Fixes |  | Amol | In Progress | 20 bugs to fix(4 bugs fixed) + Merge branch | Resolve copilot comments + 16 bugs validate & fix
Reports | reports\teacherCourseLevelExport.aspx.cs |  | Anil | Dev in Progress | Dev in Progress(55%) + functionality testing is missing fix in progress | Regional holiday
Reports | reports\aggregateLogEntry.aspx.cs |  | Sagar | Dev Completed | Dev in Progress(85%) | Dev completed + Mizan to review | Yet to connect with QE
Reports | reports\assessmentReport.aspx.cs |  | Sohith | Yet to Start Dev | Waiting for clarification | Regional Holiday
Reports | reports\ceUniversitySectionReport.aspx.cs |  | Sohith | Dev in progress | Dev in progress(20%)
Reports | reports\sectionActivityReport.aspx.cs
Reports | reports\courseLessonObjective.aspx.cs
Reports | reports\institutionalStudentPerformanceExport.aspx.cs
Reports | reports\issueAwareDailyTime.aspx.cs
Reports | reports\resourceManagerExport.aspx.cs
Reports | reports\schoolDataReport.aspx.cs
Reports | reports\sectionLogEntryReport.aspx.cs
Reports | reports\SectionObjectivePerformance.aspx.cs
Reports | reports\teacherAssignmentReport.aspx.cs
ProgressionPlan | progressionPlan\academicRequirements.aspx.cs |  | Vijay | Dev in Progress | Dev in Progress(10%) | Dev in Progress(30%) + 9006 fixed conflicts
ProgressionPlan | progressionPlan\academicRequirement.aspx.cs |  | Vijay | Dev in Progress |  | Dev in Progress(30%)
ProgressionPlan | progressionPlan\completionRequirements.aspx.cs |  | Sagar
ProgressionPlan | progressionPlan\progressionPlan.aspx.cs |  | Shivanshu |  | Sick leave | Sick leave + Local setup is done + PEDEV access pending
ProgressionPlan | progressionPlan\progressionPlans.aspx.cs |  | Shivanshu
ProgressionPlan | progressionPlan\confirmCopy.aspx.cs |  | Shivanshu
ProgressionPlan | progressionPlan\webusers.aspx.cs |  | Sagar
Log | log\categories.aspx |  | Manish | Yet to Start Dev | Sick Leave | Yet to start Dev
Log | log\contactTypes.aspx |  | Rizwana | Dev In Progress | assessments\questionManager.aspx.cs - Received issues (fixed) Dev is completed &2 issues to be fixed | Regional holiday
Log | log\logEntry.aspx |  | Ramesh | Dev in Progress | Dev In Progress (20%) | Regional holiday
Log | log\logEntrySystems.aspx |  | Manish
Log | log\myLogSettings.aspx |  | Rizwana
Log | log\systemProperties.aspx |  | Ramesh
Log | log\areas.aspx |  | Manish
LMU | lmu\resourceResources.aspx.cs |  | Anil
LMU | lmu\resources.aspx.cs |  | Vijay
LMU | lmu\resourceSubCategory.aspx.cs |  | Sohith
LMU | lmu\resourceVersionVendor.aspx.cs |  | Anil
LMU | lmu\unit.aspx.cs |  | Vijay
LMU | lmu\unitsAndLessons.aspx.cs |  | Sohith
LMU | lmu\reports\sectionWithCoursesSummary.aspx.cs |  | Vijay
Location | locations / locationCalendar / locationExtended |  | Prem | Dev in Progress | Amol completed location calendar 50%, Prem to continue and start on location extended Prem completed Location extended + QE testing in progress Prem started dev for Location calendar - in Progress | Dev continue on Location Calendar page(In Progress) QE connect is done for Location Extended + 9009 PR comments fixed
Registration | registration.aspx.cs |  | Swarneem | Yet to start | Library issues | Dev in progress(60%) + fixed PR comments for 8828
Attendance | editRecord.aspx |  | Swarneem
Attendance | enterAttendance.aspx |  | Prem
Attendance | reports/teacherAttendanceEntries.aspx |  | Prem
Webuser | webuser\overview.aspx
Webuser | webuser\webuser.aspx.cs
Webuser | webuser\webusers.aspx.cs
Webuser | webuser\roles.aspx.cs
Webuser | webuser\reporting.aspx.cs
Webuser | webuser\overview.aspx.cs
Webuser | webuser\Roles_old.aspx.cs
Webuser | webuser\sections.aspx.cs
Webuser | webuser\webuser_old.aspx.cs
4th June release - Forum not going & No full module
11th June - Assessment full module
Reports | reports\teacherCourseLevelExport.aspx.cs |  | Anil
Reports | reports\aggregateLogEntry.aspx.cs |  | Sagar
Reports | reports\assessmentReport.aspx.cs |  | Sohith
Reports | reports\ceUniversitySectionReport.aspx.cs |  | Sohith
Reports | reports\sectionActivityReport.aspx.cs |  | Sagar
Reports | reports\courseLessonObjective.aspx.cs |  | Anil
Reports | reports\institutionalStudentPerformanceExport.aspx.cs |  | Sagar
Reports | reports\issueAwareDailyTime.aspx.cs |  | Sohith
Reports | reports\resourceManagerExport.aspx.cs |  | Sohith
Reports | reports\schoolDataReport.aspx.cs |  | Sagar
Reports | reports\sectionActivityReport.aspx.cs |  | Anil
Reports | reports\sectionLogEntryReport.aspx.cs
Reports | reports\SectionObjectivePerformance.aspx.cs
Reports | reports\teacherAssignmentReport.aspx.cs
ProgressionPlan | progressionPlan\academicRequirements.aspx.cs |  | Vijay
ProgressionPlan | progressionPlan\academicRequirement.aspx.cs |  | Vijay
ProgressionPlan | progressionPlan\completionRequirements.aspx.cs |  | Vijay
ProgressionPlan | progressionPlan\progressionPlan.aspx.cs |  | Vijay
ProgressionPlan | progressionPlan\progressionPlans.aspx.cs |  | Vijay
ProgressionPlan | progressionPlan\confirmCopy.aspx.cs
ProgressionPlan | progressionPlan\webusers.aspx.cs
Log | log\categories.aspx |  | Amol
Log | log\contactTypes.aspx |  | Rizwana
Log | log\logEntry.aspx |  | Ramesh
Log | log\logEntrySystems.aspx |  | Amol
Log | log\myLogSettings.aspx |  | Rizwana
Log | log\systemProperties.aspx |  | Ramesh
LMU | lmu\resourceResources.aspx.cs |  | Amol
LMU | lmu\resources.aspx.cs |  | Rizwana
LMU | lmu\resourceSubCategory.aspx.cs |  | Ramesh
LMU | lmu\resourceVersionVendor.aspx.cs |  | Amol
LMU | lmu\unit.aspx.cs |  | Rizwana
LMU | lmu\unitsAndLessons.aspx.cs |  | Ramesh
LMU | lmu\reports\sectionWithCoursesSummary.aspx.cs

## Current scenario(PR-3)
No. | Module | Target page Technology | Recieved Functional & Non Fuctional Walkthrough | Buffer In case of no KT | Module Target Start (Input) | Page | Sprint | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | Status | Remarks | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Code Freeze Date | TEST Deployment | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | Code freeze date = Release cutoff Date | Release # | Release Request Approved Date | Release Date (2-Wk Cycle) | Code freeze date = Release cutoff Date | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce? | Actual Release Date
1 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | addressBook\addressBook.aspx.cs |  | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed |  | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | #VALUE! | 41 |  | 9
2 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | addressBook\default.aspx.cs |  | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed |  | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
3 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | addressBook\automatedRoleAssignment.aspx.cs |  | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed |  | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
4 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | addressBook\mailboxes.aspx.cs |  | Pod 1 | Pod 1_Member1 | 2026-04-20 | 3 | 0 | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Completed |  | 3 | 2026-04-27 | 1.5 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 2 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 9
5 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | assessments\reports\assessmentQuestionAnalysis.aspx.cs |  | Pod 1 | Pod 1_Member2 | 2026-04-20 | 3 | 0 | 8889 | 2026-04-22 | 2026-04-22 | 2026-04-22 | PR with Catalyst |  | 3 | 2026-04-27 | 1.5 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 3 | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 50 | #VALUE! | 9 |  |  | #VALUE!
6 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | assessments\default.aspx.cs | Sprint 2.5 | Pod 3 | Mizan | 2026-04-15 | 3 | 0 | 9006 | 2026-04-17 | 2026-04-17 | 2026-04-17 | PR with Catalyst | Havent Received KT and pearson team is working to schedule | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
7 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | assessments\checkMyWork\submissions.aspx.cs | Sprint 2.5 | Pod 3 | Swarneem | 2026-04-15 | 3 | 0 | 8886 | 2026-04-17 | 2026-04-17 | 2026-04-17 | PR with Catalyst |  | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
8 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | assessments\import.aspx.cs |  | Pod 3 | Prem | 2026-04-15 | 3 | 0 | 8798 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Merged |  | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
9 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | assessments\assessment.aspx.cs | Sprint 2.5 | Pod 3 | Mizan | 2026-04-20 | 3 | 0 | 8807 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Merged |  | 3 | 2026-04-27 | 1.5 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 2 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 9 | [5 empty] | 2026-05-28
10 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | assessments\checkMyWork\checkMyWork.aspx.cs | Sprint 2.5 | Pod 3 | Swarneem | 2026-04-20 | 3 | 0 | 8886 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Merged |  | 3 | 2026-04-27 | 1.5 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 2 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 9
11 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | assessments\questionManager.aspx.cs | Sprint 2.5 | Pod 3 | Prem | 2026-04-20 | 3 | 0 | 9002 | 2026-04-22 | 2026-04-22 | 2026-04-22 | PR with Catalyst |  | 3 | 2026-04-27 | 1.5 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 2 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 9
12 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | assessments\questions.aspx.cs |  | Pod 3 | Mizan | 2026-04-24 | 3 | 0 | 8877 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Merged |  | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
13 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | assessment\analysis.aspx.cs | Sprint 2.5 | Pod 3 | Swarneem | 2026-04-24 | 3 | 0 | 8865 | 2026-04-28 | 2026-04-28 | 2026-04-28 | PR with Catalyst |  | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 | #VALUE! | 9 |  |  | #VALUE!
14 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | assessment\manager.aspx.cs |  | Pod 3 | Prem | 2026-04-24 | 3 | 0 | 8751 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Merged |  | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
15 | Assessments | Complete ASP | Yes | 0 | 2026-04-29 | assessments\reports\assessmentAnswersAccepted.aspx.cs |  | Pod 3 | Mizan | 2026-04-29 | 3 | 0 | 8889 | 2026-05-04 | 2026-05-04 | 2026-05-04 | Merged |  | 3 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 3 | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 52 |  | 9
16 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | assetHistory.aspx |  | Pod 1 | Pod 1_Member1 | 2026-04-28 | 3 | 0 | 8814 | 2026-04-30 | 2026-04-30 | 2026-04-30 | PR Merged on 19 May | Release 5/28 | 3 | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 42 |  | 9
17 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | assetVendorAddressContact.aspx |  | Pod 3 | Pod 1_Member2 | 2026-04-28 | 3 | 0 | 8864 | 2026-04-30 | 2026-04-30 | 2026-04-30 | PR Merged on 25 May | Release 6/11 | 3 | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 42 |  | 9
18 | AssetAware | Complete ASP | No | 2 | 2026-04-20 | assetvendor.aspx |  | Pod 1 | Pod 1_Member3 | 2026-04-22 | 3 | 0 |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | Out Of Scope |  | 3 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 2 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 34 |  | 9
19 | AssetAware | Complete ASP | No | 2 | 2026-05-01 | assetAware\assetVendorAddressContact.aspx |  | Pod 1 | Pod 1_Member1 | 2026-05-05 | 3 | 0 | 8864 | 2026-05-07 | 2026-05-07 | 2026-05-07 | PR Merged on 25 May | Release 6/11 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 49 |  | 9
20 | Communication | Complete ASP | No | 2 | 2026-05-05 | communication\webmail\webmailBoxConfirmations.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member1 | 2026-05-07 | 3 | 0 | 8939 | 2026-05-11 | 2026-05-11 | 2026-05-11 | PR with Catalyst |  | 3 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 31 |  | 9
21 | Communication | Complete ASP | No | 2 | 2026-04-29 | communication\webmail\webmailBox.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member2 | 2026-05-01 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 | Waiting for clarification |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
22 | AssetAware | Complete ASP | No | 2 | 2026-04-29 | assetAware\expressassesthistory/px |  | Pod 2 | Pod 2_Member3 | 2026-05-01 | 3 | 0 | 8828 | 2026-05-06 | 2026-05-06 | 2026-05-06 | PR with Catalyst |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
23 | AssetAware | Complete ASP | No | 2 | 2026-05-12 | assets.aspx | Sprint 2.5 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 8828 | 2026-05-18 | 2026-05-18 | 2026-05-18 | PR with Catalyst |  | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 3 | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 52 | #VALUE! | 9 |  |  | #VALUE!
24 | Content | Complete ASP | No | 2 | 2026-04-15 | content\captionedVideoItem.aspx.cs |  | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 | 0 | 8804 | 2026-04-21 | 2026-04-21 | 2026-04-21 | PR with Catalyst |  | 3 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 37 |  | 9
25 | Content | Complete ASP | No | 2 | 2026-04-15 | content\elmItemInteractive.aspx |  | Pod 3 | Pod 3_Member2 | 2026-04-17 | 3 | 0 | 8815 | 2026-04-21 | 2026-04-21 | 2026-04-21 | PR Merged on 14 May | Release 5/28 | 3 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 37 |  | 9
26 | Content | Complete ASP | No | 2 | 2026-04-15 | content\hyperlink.aspx |  | Pod 3 | Pod 3_Member3 | 2026-04-17 | 3 | 0 | 8802 | 2026-04-21 | 2026-04-21 | 2026-04-21 | PR Merged on 11 May | Release 5/28 | 3 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 37 |  | 9
27 | Content | Complete ASP | No | 2 | 2026-04-22 | content\timeline.aspx.cs |  | Pod 3 | Pod 3_Member1 | 2026-04-24 | 3 | 0 | 8817 | 2026-04-28 | 2026-04-28 | 2026-04-28 | PR Merged on 14 May | Release 5/28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 3 | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 9
28 | Enrollment | Complete ASP | No | 2 | 2026-04-27 | enrollment\placement\default.aspx.cs |  | Pod 1 | Pod 1_Member3 | 2026-04-29 | 3 | 0 | 8895 | 2026-05-04 | 2026-05-04 | 2026-05-04 | PR with Catalyst |  | 3 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 |  | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 9
29 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | enrollment\placement\manager.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member1 | 2026-05-12 | 3 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Yet to raise Catalyst |  | 3 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 9
30 | Enrollment | Complete ASP | No | 2 | 2026-05-01 | enrollment\placement\rejectReason.aspx.cs |  | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Waiting for clarification from Pearson SME |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
31 | Enrollment | Complete ASP | No | 2 | 2026-05-05 | enrollment\registration\default.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member3 | 2026-05-07 | 3 | 0 | 8897 | 2026-05-11 | 2026-05-11 | 2026-05-11 | Yet to raise Catalyst |  | 3 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 31 |  | 9
32 | Enrollment | Complete ASP | No | 2 | 2026-05-15 | enrollment\registration\registrationLocation.aspx.cs |  | Pod 1 | Pod 1_Member1 | 2026-05-19 | 3 | 0 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-21 | Out of Scope |  | 3 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 35 |  | 9
33 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | enrollment\registration\registrationLocations.aspx.cs |  | Pod 1 | Pod 1_Member2 | 2026-05-12 | 3 | 0 | 6 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Out of Scope |  | 3 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 9
34 | Content | Complete ASP | No | 2 | 2026-05-12 | content/grammarTool.aspx |  | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 8818 | 2026-05-18 | 2026-05-18 | 2026-05-18 | PR Merged on 14 May | Release 5/28 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
35 | Content | Complete ASP | No | 2 | 2026-05-22 | content\sources\default.aspx.cs |  | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 0 | 8801 | 2026-05-29 | 2026-05-29 | 2026-05-29 | PR Merged on 9 May | Release 5/28 | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 3 | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 9
36 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | extendedField\default.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member1 | 2026-05-18 | 3 | 0 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | Dev In Progress |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 9
37 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | extendedField\extendedField.aspx | Sprint 2.5 | Pod 1 | Pod 1_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Yet to raise Catalyst |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
38 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-05 | extendedField\extendedFieldBulk.aspx | Sprint 2.5 | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Yet to raise Catalyst |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
39 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-21 | extendedField\categories.aspx | Sprint 2.5 | Pod 1 | Pod 1_Member1 | 2026-05-21 | 3 | 0 | 4 | 2026-05-25 | 2026-05-25 | 2026-05-25 | Yet to raise Catalyst |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 9
40 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-13 | extendedField\calculationGroups.aspx | Sprint 2.5 | Pod 1 | Pod 1_Member2 | 2026-05-13 | 3 | 0 | Yet to raise PR | 2026-05-15 | 2026-05-15 | 2026-05-15 | Yet to raise Catalyst |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
41 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | extendedField\importData.aspx |  | Pod 1 | Pod 1_Member3 | 2026-05-08 | 3 | 0 | 6 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Out of Scope |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
42 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-26 | extendedField\fieldHistory.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 0 | Yet to raise PR | 2026-05-29 | 2026-05-29 | 2026-05-29 | Yet to raise Catalyst |  | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 9
43 | Content | Complete ASP | Yes | 0 | 2026-05-18 | content\affiliate.aspx.cs |  | Pod 1 | Pod 1_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 | Out Of Scope |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 9
44 | GradeBook | Complete ASP | Yes | 0 | 2026-05-13 | gradebook\default.aspx.cs |  | Pod 2 | Pod 2_Member1 | 2026-05-13 | 3 | 0 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | Completed |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 3 | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
45 | GradeBook | Complete ASP | Yes | 0 | 2026-05-05 | gradebook\objectivePerformance.aspx.cs |  | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Completed |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 49 |  | 12
46 | Home | Complete ASP | No | 2 | 2026-04-22 | home\pages\overdueLessons.aspx.cs |  | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 8769 | 2026-04-28 | 2026-04-28 | 2026-04-28 | PR Merged on 14 May |  | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
47 | Home | Complete ASP | No | 2 | 2026-04-29 | home\pages\enrollment.aspx.cs |  | Pod 3 | Pod 3_Member1 | 2026-05-01 | 3 | 0 | 8787 | 2026-05-06 | 2026-05-06 | 2026-05-06 | InProgress with Catalyst |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
48 | Home | Complete ASP | No | 2 | 2026-04-22 | home1.aspx | Sprint 2.5 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Completed |  | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
49 | Home | Complete ASP | No | 2 | 2026-04-29 | home2.aspx | Sprint 2.5 | Pod 3 | Pod 3_Member3 | 2026-05-01 | 3 | 0 | 4 | 2026-05-06 | 2026-05-06 | 2026-05-06 | Completed |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 3 | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 50 | #VALUE! | 9 |  |  | #VALUE!
50 | IssueAware | Complete ASP | Yes | 0 | 2026-05-05 | issueAware/search.aspx |  | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Completed |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
51 | IssueAware | Complete ASP | Yes | 0 | 2026-05-18 | issueAware\automaticStakeholderRules.aspx.cs |  | Pod 2 | Pod 2_Member1 | 2026-05-18 | 3 | 0 | 2 | 2026-05-20 | 2026-05-20 | 2026-05-20 | Completed |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 9
52 | Library | Complete ASP | Yes | 0 | 2026-04-29 | library/resource.aspx |  | Pod 3 | Pod 3_Member1 | 2026-04-29 | 3 | 0 | 8838 | 2026-05-04 | 2026-05-04 | 2026-05-04 | Yet to raise Catalyst |  | 3 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 |  | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 9
53 | Library | Complete ASP | Yes | 0 | 2026-04-24 | library/searchResults.aspx |  | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 8795 | 2026-04-28 | 2026-04-28 | 2026-04-28 | PR Merged on 25 May |  | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
54 | Library | Complete ASP | Yes | 0 | 2026-04-29 | library/userSelector.aspx |  | Pod 3 | Pod 3_Member3 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | Out of scope |  | 3 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 3 | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 52 |  | 9
55 | Library | Complete ASP | Yes | 0 | 2026-05-08 | library\category.aspx.cs |  | Pod 2 | Pod 2_Member2 | 2026-05-08 | 3 | 0 | 8876 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Yet to raise Catalyst |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 3 | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 |  | 9
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | lmu\copyCourse.aspx.cs |  | Pod UI | Pod UI_UI-Member1 | 2026-05-08 | 5 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Completed |  | 3 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 3 | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 9
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | lmu\course.aspx.cs |  | Pod 2 | Pod 2_Member3 | 2026-05-08 | 3 | 0 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Completed |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 | #VALUE! | 9
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | lmu\courseCostBySectionRole.aspx.cs |  | Pod UI | Pod UI_UI-Member2 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Completed |  | 3 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 | #VALUE! | 9
57 | LMU | React/ASP | Yes | 0 | 2026-05-21 | lmu\courseResources.aspx.cs |  | Pod 2 | Pod 2_Member1 | 2026-05-21 | 3 | 0 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | Completed |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 3 | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 3 | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 |  | 9
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | lmu\courses.aspx.cs |  | Pod UI | Pod UI_UI-Member3 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Completed |  | 3 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 | #VALUE! | 9
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | lmu\importResources.aspx.cs |  | Pod 2 | Pod 2_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 | Completed |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | lmu\lessonContent.aspx |  | Pod UI | Pod UI_UI-Member4 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | Completed |  | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
59 | LMU | React/ASP | Yes | 0 | 2026-05-13 | lmu\lessonExternalContent.aspx |  | Pod 2 | Pod 2_Member3 | 2026-05-13 | 3 | 0 | 6 | 2026-05-15 | 2026-05-15 | 2026-05-15 | Completed |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 3 | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 | #VALUE! | 9 |  |  | #VALUE!
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | lmu\resource.aspx |  | Pod UI | Pod UI_UI-Member5 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | Completed |  | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
58 | LMU | React/ASP | Yes | 0 | 2026-05-20 | lmu\resourceCostDetail.aspx.cs |  | Pod UI | Pod UI_Integration | 2026-05-20 | 5 | 0 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | Completed |  | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
60 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | lmu\resourceResources.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member1 | 2026-05-26 | 3 | 0 | 4 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 9
61 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | lmu\resources.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 9
62 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | lmu\resourceSubCategory.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member3 | 2026-05-18 | 3 | 0 | 9 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 9
63 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | lmu\resourceVersion.aspx.cs | Sprint 3.2 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 49 |  | 9
64 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | lmu\resourceVersionVendor.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member2 | 2026-05-21 | 3 | 0 | 11 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 9
65 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | lmu\unit.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member3 | 2026-05-21 | 3 | 0 | 12 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 3 | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 3 | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 |  | 9
66 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | lmu\units.aspx.cs | Sprint 3.2 | Pod 2 | Pod 2_Member1 | 2026-06-05 | 3 | 0 | 10 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 9
67 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | lmu\unitsAndLessons.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member2 | 2026-05-26 | 3 | 0 | 14 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 3 | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 | #VALUE! | 9 |  |  | #VALUE!
68 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | lmu\reports\sectionWithCoursesSummary.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member3 | 2026-05-26 | 3 | 0 | 15 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 9
69 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | lmu\sections\courses.aspx.cs | Sprint 3.2 | Pod 2 | Pod 2_Member1 | 2026-06-10 | 3 | 0 | 13 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 3 | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
70 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | lmu\sections\section.aspx.cs | Sprint 3.2 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 17 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
71 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | lmu\sections\sectionRole.aspx.cs | Sprint 3.2 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 18 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 49 |  | 9
72 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | lmu\sections\sectionRoleStageRules.aspx.cs | Sprint 3.2 | Pod 2 | Pod 2_Member1 | 2026-06-15 | 3 | 0 | 16 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 3 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 |  | 2026-07-10 | 0 | 2026-07-10 | 0 | 2026-07-10 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 9
73 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | lmu\sections\sectionRoleStages.aspx.cs | Sprint 3.2 | Pod 2 | Pod 2_Member2 | 2026-06-05 | 3 | 0 | 20 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 3 | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 44 |  | 9
74 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | lmu\sections\sections.aspx.cs | Sprint 3.2 | Pod 2 | Pod 2_Member3 | 2026-06-05 | 3 | 0 | 21 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 9
75 | LMU | Complete ASP | Yes | 0 | 2026-06-18 | lmu\sections\webusers.aspx.cs | Sprint 3.2 | Pod 2 | Pod 2_Member1 | 2026-06-18 | 3 | 0 | 19 | 2026-06-22 | 2026-06-22 | 2026-06-22 |  |  | 3 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 3 | 2026-07-28 | 0 | 2026-07-28 | 0 | 2026-07-28 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 45 |  | 9
76 | Reports | Complete ASP | Yes | 0 | 2026-06-10 | reports\teacherCourseLevelExport.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member2 | 2026-06-10 | 3 | 0 | 23 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
77 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_24 | Sprint 3.2 | Pod 2 | Pod 2_Member3 | 2026-06-10 | 3 | 0 | 24 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 3 | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
78 | LMU | Complete ASP | Yes | 0 | 2026-06-23 | page_22 | Sprint 3.2 | Pod 2 | Pod 2_Member1 | 2026-06-23 | 3 | 0 | 22 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 3 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 42 | #VALUE! | 9 |  |  | #VALUE!
79 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_25 | Sprint 3.2 | Pod 2 | Pod 2_Member3 | 2026-06-15 | 3 | 0 | 25 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 3 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 |  | 2026-07-10 | 1 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 12
80 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_26 | Sprint 3.2 | Pod 2 | Pod 2_Member2 | 2026-06-15 | 3 | 0 | 26 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 3 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 3 | 2026-07-21 | 1 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 50 |  | 12
81 | Location | Complete ASP | Yes | 0 | 2026-05-05 | library/resource.aspx | Sprint 2.5 | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 8838 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Yet to raise Catalyst |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
82 | Location | Complete ASP | Yes | 0 | 2026-05-05 | library/searchResults.aspx | Sprint 2.5 | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 8795 | 2026-05-07 | 2026-05-07 | 2026-05-07 | PR Merged on 25 May |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 | #VALUE! | 9 |  |  | #VALUE!
83 | Location | Complete ASP | Yes | 0 | 2026-04-29 | library/userSelector.aspx | Sprint 2.5 | Pod 3 | Pod 3_Member2 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | Out Of Scope |  | 3 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 |  | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 9
84 | Location | Complete ASP | Yes | 0 | 2026-05-08 | library\category.aspx.cs | Sprint 2.5 | Pod 3 | Pod 3_Member3 | 2026-05-08 | 3 | 0 | 8876 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Yet to raise Catalyst |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
85 | Location | Complete ASP | Yes | 0 | 2026-05-08 | location\createHousehold_old.aspx.cs | Sprint 2.5 | Pod 3 | Pod 3_Member1 | 2026-05-08 | 3 | 0 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Completed |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
86 | Location | Complete ASP | Yes | 0 | 2026-05-05 | location\gradebookWeightTypes.aspx.cs | Sprint 2.5 | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Completed |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
87 | Location | Complete ASP | Yes | 0 | 2026-05-13 | location\skinProperties.aspx.cs | Sprint 2.5 | Pod 3 | Pod 3_Member3 | 2026-05-13 | 3 | 0 | 7 | 2026-05-15 | 2026-05-15 | 2026-05-15 | Completed |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
88 | Location | Complete ASP | Yes | 0 | 2026-05-13 | location\security\roleAccessRestrictions.aspx.cs | Sprint 2.5 | Pod 3 | Pod 3_Member1 | 2026-05-13 | 3 | 0 | 8 | 2026-05-15 | 2026-05-15 | 2026-05-15 | Completed |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
89 | Reports | Complete ASP | Yes | 0 | 2026-05-08 | reports\aggregateLogEntry.aspx.cs | Sprint 2.5 | Pod 3 | Pod 3_Member2 | 2026-05-08 | 3 | 0 | 9 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 9
90 | Reports | Complete ASP | Yes | 0 | 2026-05-18 | reports\assessmentReport.aspx.cs | Sprint 2.5 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 10 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 9
91 | Reports | Complete ASP | Yes | 0 | 2026-05-18 | reports\ceUniversitySectionReport.aspx.cs | Sprint 2.5 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 11 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 9
92 | Reports | Complete ASP | Yes | 0 | 2026-06-26 | reports\sectionActivityReport.aspx.cs | Sprint 2.5 | Pod 2 | Pod 2_Member1 | 2026-06-26 | 3 | 0 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 3 | 2026-07-06 | 1.5 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2 | 2026-07-16 | 3 | 2026-07-21 | 2026-07-21 | 2026-07-22 | 2026-07-22 |  | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 |  | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 36 | #VALUE! | 9 |  |  | #VALUE!
93 | Log | Complete ASP | Yes | 0 | 2026-06-18 | log\categories.aspx | Sprint 2.5 | Pod 2 | Pod 2_Member2 | 2026-06-18 | 3 | 0 | 2 | 2026-06-22 | 2026-06-22 | 2026-06-22 |  |  | 3 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 9
94 | Log | Complete ASP | Yes | 0 | 2026-06-18 | log\contactTypes.aspx | Sprint 2.5 | Pod 2 | Pod 2_Member3 | 2026-06-18 | 3 | 0 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 |  |  | 3 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 9
95 | Log | Complete ASP | Yes | 0 | 2026-07-02 | log\logEntry.aspx | Sprint 2.5 | Pod 2 | Pod 2_Member1 | 2026-07-02 | 3 | 0 | 4 | 2026-07-06 | 2026-07-06 | 2026-07-06 |  |  | 3 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 2 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-03 |  | 2026-08-03 | 0 | 2026-08-03 | 0 | 2026-08-03 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 45 |  | 9
96 | Log | Complete ASP | Yes | 0 | 2026-06-23 | log\logEntrySystems.aspx | Sprint 2.5 | Pod 2 | Pod 2_Member2 | 2026-06-23 | 3 | 0 | 5 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 3 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 42 |  | 9
97 | Log | Complete ASP | Yes | 0 | 2026-06-23 | log\myLogSettings.aspx | Sprint 2.5 | Pod 2 | Pod 2_Member3 | 2026-06-23 | 3 | 0 | 6 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 3 | 2026-07-01 | 1.5 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 |  | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 |  | 2026-07-20 | 0 | 2026-07-20 | 0 | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 42 |  | 9
98 | Log | Complete ASP | Yes | 0 | 2026-06-01 | log\systemProperties.aspx | Sprint 2.5 | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
99 | Reports | Complete ASP | Yes | 0 | 2026-05-21 | reports\courseLessonObjective.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member2 | 2026-05-21 | 3 | 0 | 8 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 9
100 | Reports | Complete ASP | Yes | 0 | 2026-05-13 | reports\institutionalStudentPerformanceExport.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member3 | 2026-05-13 | 3 | 0 | 9 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 9
101 | Reports | Complete ASP | Yes | 0 | 2026-05-21 | reports\issueAwareDailyTime.aspx.cs | Sprint 2.5 | Pod 3 | Pod 3_Member1 | 2026-05-21 | 3 | 0 | 10 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 3 | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 3 | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 | #VALUE! | 9 |  |  | #VALUE!
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | orderAware\default.aspx.cs | Sprint 2.6 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | orderAware\automatedOrders.aspx | Sprint 2.6 | Pod UI | Pod UI_UI-Member1 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 3 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 9
103 | OrderAware | React/ASP | Yes | 0 | 2026-06-05 | orderAware\automatedOrdersConfig.aspx.cs | Sprint 2.6 | Pod 3 | Pod 3_Member3 | 2026-06-05 | 3 | 0 | 2 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 9
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | orderAware\importShippingInformation.aspx.cs | Sprint 2.6 | Pod UI | Pod UI_UI-Member2 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 3 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 9
104 | OrderAware | React/ASP | Yes | 0 | 2026-06-10 | orderAware\orderexports.aspx | Sprint 2.6 | Pod 3 | Pod 3_Member1 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | orderAware\shipmentInformation.aspx.cs | Sprint 2.6 | Pod UI | Pod UI_UI-Member3 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 3 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 9
105 | OrderAware | React/ASP | Yes | 0 | 2026-06-05 | orderAware\userSelector.aspx | Sprint 2.6 | Pod 3 | Pod 3_Member2 | 2026-06-05 | 3 | 0 | 4 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 3 | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 44 |  | 9
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | orderAware\weborder.aspx.cs | Sprint 2.6 | Pod UI | Pod UI_UI-Member4 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 3 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 9
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-08 | orderAware\import\importShippingInformation.aspx.cs | Sprint 2.6 | Pod UI | Pod UI_Integration | 2026-06-08 | 5 | 0 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
106 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-15 | progressionPlan\academicRequirements.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member2 | 2026-05-19 | 3 | 0 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 |  |  | 3 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 35 |  | 9
107 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-19 | progressionPlan\academicRequirement.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member3 | 2026-05-21 | 3 | 0 | 2 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 3 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 9
108 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-01 | progressionPlan\completionRequirements.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member1 | 2026-06-03 | 3 | 0 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 |  |  | 3 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 |  | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 34 |  | 9
109 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-22 | progressionPlan\progressionPlan.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member2 | 2026-05-26 | 3 | 0 | 4 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 3 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 9
110 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-26 | progressionPlan\progressionPlans.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member3 | 2026-05-28 | 3 | 0 | 5 | 2026-06-03 | 2026-06-03 | 2026-06-03 |  |  | 3 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 36 |  | 9
111 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-08 | progressionPlan\confirmCopy.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member1 | 2026-06-10 | 3 | 0 | 6 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 | #VALUE! | 9 |  |  | #VALUE!
112 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-01 | progressionPlan\webusers.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member2 | 2026-06-03 | 3 | 0 | 7 | 2026-06-05 | 2026-06-05 | 2026-06-05 |  |  | 3 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 3 | 2026-07-09 | 0 | 2026-07-09 | 0 | 2026-07-09 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 48 |  | 9
113 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-04 | registration.aspx.cs | Sprint 3.1 | Pod 1 | Pod 1_Member3 | 2026-06-08 | 3 | 0 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 |  |  | 3 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 29 |  | 9
114 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-15 | editRecord.aspx | Sprint 3.1 | Pod 1 | Pod 1_Member1 | 2026-06-17 | 3 | 0 | 2 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 9
115 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-08 | enterAttendance.aspx | Sprint 3.1 | Pod 1 | Pod 1_Member2 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
116 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-11 | reports/teacherAttendanceEntries.aspx | Sprint 3.1 | Pod 1 | Pod 1_Member3 | 2026-06-15 | 3 | 0 | 4 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 3 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 |  | 2026-07-10 | 0 | 2026-07-10 | 0 | 2026-07-10 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 | #VALUE! | 9 |  |  | #VALUE!
117 | Reports | Complete ASP | No | 2 | 2026-06-22 | reports\resourceManagerExport.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member1 | 2026-06-24 | 3 | 0 | 5 | 2026-06-29 | 2026-06-29 | 2026-06-29 |  |  | 3 | 2026-07-02 | 1.5 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 3 | 2026-07-30 | 3 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 52 | #VALUE! | 12 |  |  | #VALUE!
118 | Reports | Complete ASP | No | 2 | 2026-06-15 | reports\schoolDataReport.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member2 | 2026-06-17 | 3 | 0 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 3 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 2 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 |  | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 9
119 | Reports | Complete ASP | No | 2 | 2026-06-18 | reports\sectionActivityReport.aspx.cs | Sprint 2.5 | Pod 1 | Pod 1_Member3 | 2026-06-22 | 3 | 0 | 2 | 2026-06-24 | 2026-06-24 | 2026-06-24 |  |  | 3 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 2 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 2 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 |  | 2026-07-23 | 3 | 2026-07-28 | 3 | 2026-07-31 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 57 |  | 12
120 | Reports | Complete ASP | No | 2 | 2026-06-30 | reports\sectionLogEntryReport.aspx.cs | Sprint 2.6 | Pod 1 | Pod 1_Member1 | 2026-07-02 | 3 | 0 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-06 |  |  | 3 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 |  | 2026-07-30 | 0 | 2026-07-30 | 0 | 2026-07-30 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 31 |  | 9
121 | Reports | Complete ASP | No | 2 | 2026-06-25 | reports\SectionObjectivePerformance.aspx.cs | Sprint 2.6 | Pod 1 | Pod 1_Member3 | 2026-06-29 | 3 | 0 | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 3 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 |  | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 |  | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 |  | 2026-07-27 | 0 | 2026-07-27 | 0 | 2026-07-27 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 36 | #VALUE! | 9 |  |  | #VALUE!
122 | Reports | Complete ASP | No | 2 | 2026-06-22 | reports\teacherAssignmentReport.aspx.cs | Sprint 2.6 | Pod 1 | Pod 1_Member2 | 2026-06-24 | 3 | 0 | 5 | 2026-06-29 | 2026-06-29 | 2026-06-29 |  |  | 3 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 3 | 2026-08-03 | 0 | 2026-08-03 | 0 | 2026-08-03 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 52 |  | 9
123 | Webuser | Complete ASP | No | 2 | 2026-04-29 | webuser\overview.aspx | Sprint 3.1 | Pod 3 | Pod 3_Member2 | 2026-05-01 | 3 | 0 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 3 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 9
124 | Webuser | Complete ASP | No | 2 | 2026-05-07 | webuser\webuser.aspx.cs | Sprint 3.1 | Pod 3 | Pod 3_Member3 | 2026-05-11 | 3 | 0 | 2 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  |  | 3 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 |  | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 43 | #VALUE! | 9
125 | Webuser | Complete ASP | No | 2 | 2026-05-07 | webuser\webusers.aspx.cs | Sprint 3.1 | Pod 3 | Pod 3_Member1 | 2026-05-11 | 3 | 0 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  |  | 3 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 |  | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 43 | #VALUE! | 9
126 | Webuser | Complete ASP | No | 2 | 2026-05-07 | webuser\webuserextended.aspx.cs | Sprint 3.1 | Pod 3 | Pod 3_Member2 | 2026-05-11 | 3 | 0 | 4 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  |  | 3 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 |  | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 43 |  | 9
127 | Webuser | Complete ASP | No | 2 | 2026-05-14 | webuser\roles.aspx.cs | Sprint 3.1 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 5 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 | #VALUE! | 9
128 | Webuser | Complete ASP | No | 2 | 2026-05-14 | webuser\reporting.aspx.cs | Sprint 3.1 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 6 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 | #VALUE! | 9
129 | Webuser | Complete ASP | No | 2 | 2026-05-14 | webuser\overview.aspx.cs | Sprint 3.1 | Pod 3 | Pod 3_Member2 | 2026-05-18 | 3 |  | 7 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18
130 | Webuser | Complete ASP | No | 2 | 2026-05-21 | webuser\Roles_old.aspx.cs | Sprint 3.1 | Pod 3 | Pod 3_Member3 | 2026-05-25 | 3 |  | 8 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  |  | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02
131 | Webuser | Complete ASP | No | 2 | 2026-05-21 | webuser\sections.aspx.cs | Sprint 3.1 | Pod 3 | Pod 3_Member1 | 2026-05-25 | 3 |  | 9 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  |  | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02
132 | Webuser | Complete ASP | No | 2 | 2026-05-21 | webuser\webuser_old.aspx.cs | Sprint 3.1 | Pod 3 | Pod 3_Member2 | 2026-05-25 | 3 |  | 10 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  |  | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 3 | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02
133 | Security | Complete ASP | No | 2 | 2026-04-15 | security/default.aspx | Sprint 2.5 | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 |  | 1 | 2026-04-21 | 2026-04-21 | 2026-04-21 | In Progress |  | 3 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28
133 | Security | Complete ASP | No | 2 | 2026-03-01 | security/permissionRoles.aspx |  | Pod 3 | Pod 3_Member1 | 2026-03-03 | 3 |  | 1 | 2026-03-06 | 2026-03-06 | 2026-03-06 | Completed |  | 3 | 2026-03-11 | 1.5 | 2026-03-12 | 2026-03-12 | 3 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 |  | 2026-03-18 | 2 | 2026-03-23 | 3 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-30 |  | 2026-03-30 | 0 | 2026-03-30 | 0 | 2026-03-30 | 2026-04-09 | Release 8 | #VALUE! | 2026-04-16
133 | Security | Complete ASP | No | 2 | 2026-04-15 | security/permissionVisibility.aspx |  | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 |  | 1 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Completed |  | 3 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28
133 | Security | Complete ASP | No | 2 | 2026-04-15 | security/permissionDisplayGroupPermissions.aspx | Sprint 2.5 | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 |  | 1 | 2026-04-21 | 2026-04-21 | 2026-04-21 | In Progress |  | 3 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28
133 | Security | Complete ASP | No | 2 | 2026-05-01 | security/PermissionDisplayGroups.aspx | Sprint 2.5 | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 |  | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | In Progress |  | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11
133 | Security | Complete ASP | No | 2 | 2026-03-01 | security\permissionSectionRoles.aspx |  | Pod 3 | Pod 3_Member1 | 2026-03-03 | 3 |  | 1 | 2026-03-06 | 2026-03-06 | 2026-03-06 | Completed |  | 3 | 2026-03-11 | 1.5 | 2026-03-12 | 2026-03-12 | 3 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 |  | 2026-03-18 | 2 | 2026-03-23 | 3 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-30 |  | 2026-03-30 | 0 | 2026-03-30 | 0 | 2026-03-30 | 2026-04-09 | Release 8 | #VALUE! | 2026-04-16
133 | Gradebook | Complete ASP | No | 2 | 2026-05-28 | gradebook\progressReport\default.aspx |  | Pod 3 | Pod 3_Member1 | 2026-06-01 | 3 |  | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | Completed |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
134 | Gradebook | Complete ASP | No | 2 | 2026-06-05 | gradebook\progressReport\progressReport.aspx.cs |  | Pod 3 | Pod 3_Member1 | 2026-06-09 | 3 |  | 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | Completed |  | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
135 | Gradebook | Complete ASP | No | 2 | 2026-05-28 | gradebook\section\* - all pages |  | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 |  | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | Completed |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-05 | gradebook\progressReport\transcript\createExternalCourses.aspx.cs |  | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 |  | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | Completed |  | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | gradeBook/progressReport/transcript/externalCourses.aspx |  | Pod UI | Pod UI_UI-Member1 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | Completed |  | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
137 | Gradebook | React/ASP | No | 2 | 2026-05-28 | gradebook\progressReport\transcript\externalCourse.aspx.cs |  | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 |  | 5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | Completed |  | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Sprint 2.5 | Pod UI | Pod UI_UI-Member2 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
138 | Content | Complete ASP | No | 2 | 2026-06-05 | content\affiliates.aspx.cs |  | Pod 3 | Pod 3_Member3 | 2026-06-09 | 3 |  | 6 | 2026-06-11 | 2026-06-11 | 2026-06-11 | Out Of Scope |  | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Sprint 2.5 | Pod UI | Pod UI_UI-Member3 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
139 | Content | Complete ASP | No | 2 | 2026-06-12 | content\sources\source.aspx.cs | Sprint 2.5 | Pod 3 | Pod 3_Member1 | 2026-06-16 | 3 |  | 8804 | 2026-06-18 | 2026-06-18 | 2026-06-18 | PR with Catalyst |  | 3 | 2026-06-23 | 1.5 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 |  | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Sprint 2.5 | Pod UI | Pod UI_UI-Member4 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
140 | Content | Complete ASP | No | 2 | 2026-06-12 | content\chrome\online\footer.aspx.cs |  | Pod 3 | Pod 3_Member2 | 2026-06-16 | 3 |  | 8 | 2026-06-18 | 2026-06-18 | 2026-06-18 | Out Of Scope |  | 3 | 2026-06-23 | 1.5 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 |  | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_9 | Sprint 2.5 | Pod UI | Pod UI_UI-Member1 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 3 | 2026-07-06 | 1.5 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2 | 2026-07-16 | 3 | 2026-07-21 | 2026-07-21 | 2026-07-22 | 2026-07-22 |  | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 |  | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
141 | Content | Complete ASP | No | 2 | 2026-06-12 | content\chrome\printed\options.aspx.cs |  | Pod 3 | Pod 3_Member3 | 2026-06-16 | 3 |  | 9 | 2026-06-18 | 2026-06-18 | 2026-06-18 | Out Of Scope |  | 3 | 2026-06-23 | 1.5 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 3 | 2026-07-06 | 2 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 3 | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_9 | Sprint 2.5 | Pod UI | Pod UI_UI-Member2 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 3 | 2026-07-06 | 1.5 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2 | 2026-07-16 | 3 | 2026-07-21 | 2026-07-21 | 2026-07-22 | 2026-07-22 |  | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 |  | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
136 | Gradebook | React/ASP | No | 0 | 2026-06-23 | page_9 | Sprint 2.5 | Pod UI | Pod UI_Integration | 2026-06-23 | 5 |  | 4 | 2026-06-30 | 2026-06-30 | 2026-06-30 |  |  | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
Formulas:
Start Date = [Module Target Start (Input)]
Start Date = WORKDAY([Module Target Start (Input)],[Buffer In case of no KT])
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([PR Final Approval date], 0, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Code Freeze Date = [TCR Bugs Closure Date]
TEST Deployment = [Code Freeze Date]
Pearson Regression Testing/UAT Date = WORKDAY([TEST Deployment], 1, IndHolidays)
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&(MAX([PR Response receive Date],[TCR Bugs Closure Date])))
Code freeze date = Release cutoff Date = WORKDAY([Release Date (2-Wk Cycle)], -5)
Release Request Approved Date = WORKDAY([Release #], 2, IndHolidays)
Release Date (2-Wk Cycle) = VLOOKUP([Release #],ReleaseTimeline!$B2:C27,2,FALSE)
Module Target Start (Input) = WORKDAY([PR raised date, row above],1)

## Sep Release Plan
Module | Sprint 2.4 | Sprint 2.5 | Sprint 2.6 | Sprint 3.1 | Sprint 3.2 | Sprint 3.3 | Sprint 3.4 | Sprint 3.5 | Sprint 3.6 | Total Pages | Status | PR Raised Date | PR Aging
Start Date | 2026-05-11 | 2026-05-25 | 2026-06-08 | 2026-06-22 | 2026-07-06 | 2026-07-20 | 2026-08-03 | 2026-08-17 | 2026-08-31
End Date | 2026-05-22 | 2026-06-05 | 2026-06-19 | 2026-07-03 | 2026-07-17 | 2026-07-31 | 2026-08-14 | 2026-08-28 | 2026-09-11
Release Date | 2026-05-28 | 2026-06-11 | 2026-06-25 | 2026-07-09 | 2026-07-23 | 2026-08-06 | 2026-08-20 | 2026-09-03 | 2026-09-17
Assessments | 2026-05-28: 10 | 10 | Dev Completed + PR's in progress with Catalyst 4 Pages deployed + 7 Pages Inprogress with Catalyst | 9006 - 28th May 8886 - 27th May 9002 - 28th May 8889 - 27th May | 3 days
AssetAware | 2026-05-28: 5 | 5 | Dev Completed + PR's in progress with Catalyst 3 Pages deployed+ 2 pages PR's Inprogress with Catalyst | 8828 - 27th May | 3 days
Communication | 2026-05-28: 2 | 2 | Dev Completed(80%) + PR's in progress with Catalyst 1 page PR in progress with Catalyst 1 Page clarification is pending | 8939 - 27th May | 3 days
Content | 2026-05-28: 1; 2026-06-11: 8 | 9 | Dev Completed + PR's in progress with Catalyst 5 Pages deployed+ 2 pages PR in progress with Catalyst | 8804 - 27th May | 3 days
Enrollment | 2026-06-11: 8 | 8 | Dev Completed(80%) + PR's in progress with Catalyst 3 Pages PR in progress with Catalyst | 8895 - 28th May 8897 - 28th May | 2 days
ExtendedField | 2026-06-11: 4; 2026-06-25: 4 | 8 | Dev Completed + 50% PR's in progress with Catalyst 2 pages PR in progress with Catalyst + 4 Pages PR's not raised as we have limitation | 9009 - 28th May | 2 days
GradeBook | 2026-06-25: 16; 2026-07-09: 2 | 18 | Dev Completed + Bug Fix in Progress(16 bugs yet to fix)
Home | 2026-07-09: 4 | 4 | Dev Completed + PR's in progress with Catalyst 1 Page deployed+ 1 Page in progress with Catalyst | 8787 - 27th May | 3 days
Library | 2026-07-09: 3 | 3 | Dev Completed + 70% PR's in progress with Catalyst 1 Page deployed + 2 pages PR's not raised as we have limitation | 8838 8876
LMU | 2026-07-09: 11; 2026-07-23: 20; 2026-08-06: 1 | 32 | Dev In Progress
Location | 2026-08-06: 11 | 11 | Dev In Progress 90% 3 Pages deployed + 7 Pages PR's not raised as we have limitation
Log | 2026-08-06: 8; 2026-08-20: 2 | 10 | Dev Started
OrderAware | 2026-08-20: 9 | 9 | Yet to start
ProgressionPlan | 2026-08-20: 7 | 7 | Dev Started
Reg+Attendance | 2026-08-20: 2; 2026-09-03: 3 | 5 | Dev Started
Reports | 2026-09-03: 5 | 5 | Waiting for KT from customer
Security | 2026-09-03: 4 | 4 | Delivered + Deployed to prod + TCR bugs fixed + Bug PR's inprogress with Catalyst
Webuser | 2026-09-03: 8; 2026-09-17: 2 | 10 | Yet to start
TOTAL PAGES | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2 | 162
TOTAL PRS | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 108

## All Handson Workshop May 11-15 (hidden)
Module | Modules/ Pages | US# | POC | Status | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | PR | Copilot Usage as on 11th May | Copilot Usage as on 12th May | Copilot Usage as on 13th May | Copilot Usage as on 14th May | Copilot Usage as on 15th May
Assessment | assessments\default.aspx.cs | 1043225 | Anil | In Progress | Dev started(100%) + connected with QE + identified 3 bugs | Sick Leave | Raise PR for the bug fix + check on 8865 raised to catalyst | Forum
Assessment | assessments\questionManager.aspx.cs | 1043225 | Rizwana | Yet to raise to catalyst |  | Dev completed + QE testing is pending + yet to raise PR + PR to be reviwed + Yet to fix copilot comments
Assessment | assessments\questions.aspx.cs | 1043225 | Rizwana | Raised to Catalyst | Dev is completed + QE testing is in progress + PR created + reveiw is done |  |  |  |  | 8877
Content | content\sources\source.aspx.cs | 989555 | Ramesh | Yet to raise PR to catalyst | Worked on Gradebook PR's + Content PR's | Dev completed + PR raised + yet to fix copilot comments + yet to connect with QE + Yet to get PR reviwe 8815 - Fixed merge conflicts | Gradebook(P1) |  |  | 8881
Enrollment | enrollment\placement\default.aspx.cs | 989556 | Rizwana | Yet to start |  | Enrollment
Enrollment | enrollment\placement\manager.aspx.cs | 989556 | Ramesh | Yet to start |  | Enrollment(P2)
Enrollment | enrollment\placement\rejectReason.aspx.cs | 989556 | Vijay | Yet to start | Dev completed for Assessment 2 pages + Yet to raise PR | 8751 - fixed copilot comments + fixed PR comments check my work & submission - 8886
Enrollment | enrollment\registration\default.aspx.cs | 989556 | Anil | Yet to start |  | Enrollment |  | Forum
Enrollment | enrollment\registration\registrationLocation.aspx.cs | 989556 | Sagar | Yet to start | Yet to get access | Enrollment | Enrollmnt
Enrollment | enrollment\registration\registrationLocations.aspx.cs | 989556 | Amol | Yet to start |  | Enrollment
Location | location\gradebookWeightTypes.aspx.cs | 989655 | Prem | In Progress | Worked on PR's for security | Dev completed + Yet to connect with QE + Yet to raise PR + YEt to fix copilot comments + PR yet to be reiwed 8783 - Fixed Merge conflicts + Working on security PRs
Location | location\skinProperties.aspx.cs | 989655 | Swarneem | Yet to raise PR to catalyst | Worked on shared control PR(8872) | Dev completed + QE testing is inprogress +Yet to raise PR+ yet to get PR review + yet to fix copilot comments 8872 - Fixed copilot comments
Location | location\security\roleAccessRestrictions.aspx.cs | 989655 | Prem | Yet to start |  |  | Location
Extended Feild | extendedField\categories.aspx | 989557 | Vijay | Yet to start |  |  | Extended Feild(yet to start dev)
Extended Feild | extendedField\calculationGroups.aspx | 989557 | Sohith | Yet to start | Assessment bugs fixed + PR's creation + internal testing for bug is done | Extended Feild
Extended Feild | extendedField\importData.aspx | 989557 | Swarneem | Yet to start |  |  | Extended Feild
Extended Feild | extendedField\fieldHistory.aspx.cs | 989557 | Sohith | Yet to start |  |  | Extended Feild
External | Remove Feature Flag | 989650 | Mizan | Completed | Testing is done and good to close FF
ImportStatus | Remove Feature Flag | 989652 | Mizan | Completed | Testing is done and good to close FF
Assessment | assessments\reports\assessmentAnswersAccepted.aspx.cs |  | Sohith | Yet to raise PR |  | Dev completed + internal QE is done + Yet to create PR + yet to fix copilot comments
Assessment | assessments\reports\assessmentQuestionAnalysis.aspx.cs |  | Sohith | Yet to raise PR |  | Dev completed + internal QE is done + Yet to create PR + yet to fix copilot comments

## All Handson WorkShop-May4-8 (hidden)
Module | Modules/ Pages | POC | Status | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | Current status as on 11 May | Current status as on 12 May | PR | Copilot Usage as on 4th May | Copilot Usage as on 6th May | Copilot Usage as on 7th May | Copilot Usage as on 8th May
Assessment | assessments\default.aspx.cs | Anil | Not started | Sohith is on leave | As Sohith is on leave anil picked this page and dev is in progress | Anil is facing issue with laptop and working with IT team to fix | Need to be moved to someone else to start the development | Dev started | [6 empty] | `
Assessment | assessments\checkMyWork\submissions.aspx.cs | Vijay | In Progress |  | Sohith is on leave | Dev Inprogress (70% to 75%) + out of 8 RAD controls 8 is done + fixing functionality issue | Vijay to complete this page + Raise PR + Fix CoPilot comments + Test with QE in local Dev is completed + Yet to create shared controls | Create shared controls in progress + Yet to raise PR
Assessment | assessments\import.aspx.cs | Anil | In Progress | Rasied PR(8798) + Copilot comments fixed + Abhijit Reviwed PR | QE testing completed on local, 1 issue found related to document upload, yet to fix |  | Anil to resolve merge conflict and then submit to Catalyst Resolved bug + Verified with QE + Copilot comments fix in progress |  | waiting for PR comments |  | 8798 | 8% |  |  | 26%
Assessment | assessments\assessment.aspx.cs | Vijay | Merged | Completed development + Yet to raise PR | Raised PR(8807) + Fixed Copilot comments + PR is reviwed by abhijit and raised to catalyst | PR 8751 - PR comemnts received and fix in progress | PR 8807 - Received conflicts + PR comments(Yet to start) | PR is approved + Merged |  | Yet to create shared control | 8807 | 18%
Assessment | assessments\checkMyWork\checkMyWork.aspx.cs | Vijay | In Progress |  | Yet to start | Dev Inprogress (70% to 75%) + out of 8 RAD controls 8 is done + fixing functionality issue | Vijay to complete this page + Raise PR + Fix CoPilot comments + Test with QE in local Dev is completed + Yet to create shared controls | Create shared controls in progress + Yet to raise PR |  |  |  |  | 32%
Assessment | assessments\questionManager.aspx.cs | Amol | Yet to start |  |  |  |  | Yet to start on Dev
Assessment | assessments\questions.aspx.cs | Rizwana | Yet to start |  |  |  |  | Yet to start on Dev
Assessment | assessment\analysis.aspx.cs | Anil | In Progress |  |  |  |  | Dev Completed + PR Created(8865) + Copilot comments fixed | abhijit need to review + yet to raise to catalyst |  | 8865
Issue aware Bug fix is completed + Submitted to abhijit for review + Roll back for bug fixes
IssueAware |  | Vijay | Merged |  |  |  | IssueAware - IssueSystem bug fix --> check with QA --> Raise PR --> Resolve Co-pilot comments --> Post it in catalyst (CSS changes only) Fixed bug + Reverted to catalyst | 8842 + 8852 = Merged
Assessment | assessment\manager.aspx.cs | Vijay | In Progress |  |  |  | fix conflicts - resolve co-pilot comments - Ask catalyst's team to review (currently I requested him to pause his review as we got conflicts and co-pilot comments) Complete PR 8751, and fix the issues Resolved conflicts + Copilot comments fix in progress | Copiot comments Fixed + Conflicts fix in progress | resolved conflicts + reverted(11 May) |  | 8751 |  |  |  | 39%
Vijay was working PR 8751 as we received PR comments and fix in progress
Asset Aware | assetHistory.aspx | Mizan | In Progress | Completed development + Creation of PR in progress | Raised PR(8814) + yet to get review for the PR + Copilot comments are fixed |  | Complete QE testing + Raise to Catalyst |  |  |  | 8814 | 4%
Asset Aware | assetVendorAddressContact.aspx | swarneem | With Catalyst |  | Swarneem to take this page on 6th May |  | Can Swarneem start on this page? | Dev is completed + PR reviwed + PR (8864) + internal testing is done |  |  | 8864 |  | 14% | 16%
Asset Aware | assetvendor.aspx | Swarneem | Out of scope |  | As there is no RAD controls in this page(out of scope)
Asset Aware | assetAware\assetVendorAddressContact.aspx | Swarneem | In Progress |  |  | Yet to start | Dev started | Dev completed + PR (8864) raised + QE internal testing is done + copilot comments need to fix |  |  | 8864
Asset Aware | assetAware\expressassesthistory/px | Swarneem | Waiting for Catalyst Comments |  |  | Dev Completed + PR Raised (8828) + Copilot comments fix in progress + internal testing is completed | Complete PR 8828 and raise to Catalyst (WIP) PR to be reveiwed with abhijit |  | with catalyst |  | 8828
Asset Aware | assets.aspx | Swarneem | in Progress |  |  | Dev is completed(90%) + Yet to raise PR + QE connect is done however there are few issus found (fix inprogress) | Complete this page + Raise PR + Fix CoPilot comments + Test with QE in local What is PR# for this page? Dependency on location tree and facing issues in icon loading (PR not raised) | Dev Testing to be done + QE testing to be done+ Location tree model changes and date picker ned to verify | Yet to raise PR | Yet to raise PR
Library | library/resource.aspx | Swarneem | In Progress | Completed development + Yet to raise PR | Created PR and copilot comments fix in progress |  | What is PR# for this page? Complete this development, raise PR, fix CoPilot comments PR comments Fix in progress | Retesting needs to be done (cross check not to break anything) | yet to raise to catalyst | yet to fix build issues + PR yet to raise to catalyst | 8838 | 14% |  | 20% | 28%
[7 empty] | Shared controls PR - added icons + fixed few issues + fixd copilot comments |  |  |  | 8846
Library | library/searchResults.aspx | Prem | Waiting for Catalyst Comments | Raised PR(8795) + Copilot comments fixed Abhijit reveiwed PR + QE testing completed |  |  | Resolve CoPilot comments for this PR Resolved copilot comments + Reverted to catalyst | 8795 - Received copilot comments + Reverted back MErge conflicts fixed | Received conflicts + Done with conflicts |  | 8795
Library | library/userSelector.aspx | Prem | Out of scope |  | Out of scope however prem is working on security PR's. Prem will create new PR(s) with these fixes.
Library - 2 | library\category.aspx.cs | Prem | In Progress |  |  |  |  | Dev completed + QE testing is done + QE raised few suggestions fix in progress | Yet to raise PR | will be on onhold until the shared control PR's approve
Content | content\captionedVideoItem.aspx.cs | Ramesh | Waiting for Catalyst Comments | Completed development + Yet to raise PR | Raised PR(8804) + Fixed Copilot comments | PR(8804 ) - fixed errors + QE setup still in progress. | Complete QE testing + Raise to Catalyst Received copilit comments fixed Fixed issues + Reverted to catalyst | Received Copilot comments + Merge Conflicts | Merge conflicts fixed + waiting for approval |  | 8804 | 3%
Content | content\elmItemInteractive.aspx | Ramesh | Approved |  | Development completed + PR Raised(8815) + Copilot comments fixed + PR reveiwed by abhijit + internal testing is done + raised to Catalyst |  | Look for Catalyst review comments, resolve comments as received Recived Merge conflicts fixed + Reverted to catalyst | Received PR comments + Fixed + approved | Merge conflicts fixed + waiting for one more approval |  | 8815 |  | 8% | 18%
Content | content\hyperlink.aspx | Rizwana | Approved | Raised PR(8802) + Copilot comments +Abhijit Reviwed PR + QE testing is completed + raised to Catalyst |  |  | Catalyst team approved this PR. Rizwana to resolve conflict and get approval again Resolved merge conflicts + first round is approved + Kept in on hold (merge conflicts) | 8802 is approved - Yet to merge (planned for 14th May release) | Approved + Merge conflicts + Merged (11th May) |  | 8802 | 7%
Content | content\timeline.aspx.cs | Rizwana | Waiting for Catalyst Comments |  | Development completed +PR Raised(8817) + copilot comments fixed + internal testing is done + PR review is done by abhijit + raised to Catalyst |  | Look for Catalyst review comments, resolve comments as received Resolved merge conflicts + Fixed copilot comments |  | Merge conflicts fixed on 11May |  | 8817 |  |  | 13%
Content | content/grammarTool.aspx | Amol | Waiting for Catalyst Comments |  | Dev Completed + PR Raised(8818) + Fixed Copilot comments + Abhijit reveiwed PR + internal testing is done + raised to Catalyst |  | Look for Catalyst review comments, resolve comments as received + Amol to resolved conflicts Fixed Copilot comments + Fixed conflicts (reverted PR to catalyst) |  | approved + Merge conflicts |  | 8818
Content | content\sources\default.aspx.cs | Amol | Waiting for Catalyst Comments | Raised PR(8801) + Copilot Comments + Abhijit Reviwed PR + Raised to Catalyst |  |  | Look for Catalyst review comments, resolve comments as received Fixed copilot comments + Resolved conflicts | Merged |  |  | 8801 | 10% |  | 18%
Content | content\affiliate.aspx.cs | Rizwana | [5 empty] | Analysis in progress + No RAD controls(out of scope)
Content | content\affiliates.aspx.cs | Amol | [5 empty] | Analysis in progress + No RAD controls + Out of Scope |  |  | 1040961(ADO)
Content | content\sources\source.aspx.cs | Ramesh | [5 empty] | Analysis in progress + Dev to start
Content | content\chrome\online\footer.aspx.cs | Ramesh | [5 empty] | to check if it falls on .ASP or React Partial pages and could see it direct (out of scope)
Content | content\chrome\printed\options.aspx.cs | Ramesh | [5 empty] | to check if it falls on .ASP or React Partial pages and could see it direct (out of scope) | [6 empty] | 22%
Security | content\chrome\online\footer.aspx.cs | Prem | Waiting for Catalyst Comments |  |  | Security Bug fix in progress + Copilot comments fix completed + Connected with QE and suggested few changes which is fixed. Received PR comments for 8783 fix in progress 8783, 8784, 8781 - Copilot comments fix in progress | Complete all pending works for all the open PRs 8783 , 8784, 8782, 8781 Raised to catalyst 8781 - Received PR comments + fix in progress | 8781 - Resolved copilot + PR comments + reverted back + Approved 8782 - Resolved copilot + PR comments + reverted back | 8782- Received PR comments + Merge conflicts 8783 - Merge Conflicts | Fixed merge conflicts for 8783 | 8783, 8784, 8781, 8782 |  | 19% |  | 23%
GradeBook | content\chrome\printed\options.aspx.cs | Ramesh | In Progress |  |  |  | QE setup is done (Tinu)
GradeBook | GradeBook open Issues(deatils tab) SPA page | Amol | Waiting for Catalyst Comments |  |  | Gradebook PR(8793) - PR comments fix in progress + POPup bug fixes in progress Home page - PR comments fixed grammar page (Content) - PR comments fixed Enrollement page (Home) - PR comments fixed | Complete all the bug fixes by 5/7, target for 5/28 deployment 8793 - PR comments + Copilot comments fixed + PR reveiwed by abhijit + Reverted PR to catalyst team | copilot comments fix in progress | Still facing conflicts in copilot | Still facing conflicts in copilot | 8793
Common | Setup QA Dev Env and guide others | Rizwana | In Progress |  |  | Gradebook - PR (8762) - bug fix is completed(PR Merged) + other bug fix in progress PR(8797) - issues resolved | 8762 - Merged | 8789 - coipilot comments fixed + Unit test & API breaking chages (fix in progress) | PR raised by amol + received PR comments + fixed conflicts |  | 8787 |  |  |  | 19%
Home | home\pages\overdueLessons.aspx.cs | Rizwana | Approved |  |  | Home - PR (8769 ) - fixed Copilot comments + merge conflicts fix in progress | Rizwana to Resolve conflicts Fixed PR comments + Rverted to catalyst | Approved | Approved + Merge conflicts fixed |  | 8769
Home | home\pages\enrollment.aspx.cs | Amol | Waiting for Catalyst Comments |  |  | Home page - PR (8787) comments fixed | Amol to Resolve conflicts Yet to work on this PR | PR reverted to catalyst | Received PR comments + Merge conflicts |  | 8787

## Target Tech
Feature | Overall Module | Count of pages | Total Estimate (SP) | Release# | Planned Release Date | Status | Internal Release Date | Target | Actual Release Date | Remarks
1 | external | 2 | 8 | Release 3 | 2026-02-05 | Completed | 2026-02-05 | Complete ASP | 2026-02-19
2 | importStatus | 1 | 13 | Release 3 | 2026-02-05 | Completed | 2026-02-05 | Complete ASP | 2026-02-19
3 | security | 3 | 7 | Release 4 | 2026-03-19 | In Progress | 2026-03-19 | Complete ASP |  | PR reviews are getting delayed
4 | library | 5 | 20 | Release 6 | 2026-03-19 | In Progress | 2026-03-19 | Complete ASP |  | Verifying with business teams if these pages are being used
5 | issueAware | 10 | 76 | Release 6 | 2026-03-19 | In Progress | 2026-03-19 | Complete ASP
6 | forum | 4 | 13 | Release 7 | 2026-04-02 | In Progress | 2026-03-19 | Complete React
7 | timeline | 2 | 20 | Release 7 | 2026-04-02 | On Hold | 2026-04-02 | N/A |  | Verifying with business teams if these pages are being used. Working with Pearson for an alternative for the "wysiwyg" editor.
8 | gradebook | 7 | 46 | Release 7 | 2026-04-02 | In Progress | 2026-04-02 | React/ASP
9 | planner | 8 | 33 | Release 7 | 2026-04-02 | On Hold | 2026-04-02 | ?? |  | Verifying with technical teams if changes are already completed, Also, are these being used?
10 | enrollment | 6 | 30 | Release 9 | 2026-04-30 | Yet to start | 2026-04-30 | Complete ASP
11 | addressBook | 9 | 34 | Release 9 | 2026-04-30 | In Progress | 2026-04-30 | Complete ASP
12 | progressionPlan | 4 | 40 | Release 9 | 2026-04-30 | Yet to start | 2026-04-16 | Complete ASP
13 | orderAware | 9 | 93 | Release 9 | 2026-04-30 | Yet to start | 2026-04-16 | React/ASP
14 | extendedField | 7 | 46 | Release 11 | 2026-05-28 | Yet to start | 2026-05-14 | Complete ASP
15 | content | 9 | 49 | Release 11 | 2026-05-28 | Yet to start | 2026-05-14 | Complete ASP |  | To work with Pearson for an alternative for the "wysiwyg" editor. 2 pages do not have navigation options - content\chrome\online\footer.aspx.cs and enrollment\placement\default.aspx.cs
16 | log | 7 | 91 | Release 11 | 2026-05-28 | Yet to start | 2026-05-14 | Complete ASP
17 | assessments | 12 | 118 | Release 11 | 2026-05-28 | Yet to start | 2026-05-14 | Complete ASP
18 | assetAware | 9 | 48 | Release 11 | 2026-05-28 | Yet to start | 2026-05-14 | Complete ASP
19 | attandance | 3 | 33 | Release 12 | 2026-06-11 | Yet to start | 2026-06-11 | Complete ASP
20 | webuser | 10 | 13 | Release 12 | 2026-06-11 | Yet to start | 2026-06-11 | Complete ASP
21 | communication | 6 | 26 | Release 12 | 2026-06-11 | Yet to start | 2026-06-11 | Complete ASP
22 | location | 6 | 27 | Release 12 | 2026-06-11 | In Progress | 2026-06-11 | Complete ASP
23 | registration.aspx.cs | 5 | 13 | Release 12 | 2026-06-11 | Yet to start | 2026-06-11 | Complete ASP
24 | reports | 13 | 100 | Release 12 | 2026-06-11 | Yet to start | 2026-06-11 | Complete ASP
25 | lmu | 26 | 224 | Release 13 | 2026-06-25 | In Progress | 2026-06-11 | React/ASP |  | High level analysis completed. Working with Pearson for an alternative for the "wysiwyg" editor.
26 | home | 6 | 13 | Release 13 | 2026-06-25 | Yet to start | 2026-06-11 | Complete ASP
[8 empty] | Overall Module | Release# | Planned Release Date
Feature | Overall Module | Old Release# | Old Planned Release Date | New Release# | New Planned Release Date | Status |  | Overall Module | Release# | Planned Release Date
1 | external | Release 3 | 2026-02-05 | Release 3 | 2026-02-05 | Completed |  | external | Release 3 | 2026-02-05 | same
2 | importStatus | Release 3 | 2026-02-05 | Release 3 | 2026-02-05 | Completed |  | importStatus | Release 3 | 2026-02-05 | same
3 | security | Release 4 | 2026-03-05 | Release 4 | 2026-03-19 | In Progress |  | security | Release 4 | 2026-03-05 | same
4 | library | Release 6 | 2026-03-19 | Release 6 | 2026-03-19 | In Progress |  | forum | Release 4 | 2026-03-05 | diff
5 | issueAware | Release 6 | 2026-03-19 | Release 6 | 2026-03-19 | In Progress |  | timeline | Release 5 | 2026-03-05 | diff
6 | forum | Release 4 | 2026-03-05 | Release 7 | 2026-04-02 | In Progress |  | gradebook | Release 5 | 2026-03-05 | diff
7 | timeline | Release 5 | 2026-03-05 | Release 7 | 2026-04-02 | On Hold |  | library | Release 6 | 2026-03-19 | diff
8 | gradebook | Release 5 | 2026-03-05 | Release 7 | 2026-04-02 | In Progress |  | issueAware | Release 6 | 2026-03-19 | diff
9 | planner | Release 6 | 2026-03-19 | Release 7 | 2026-04-02 | On Hold |  | planner | Release 6 | 2026-03-19 | same
10 | enrollment | Release 8 | 2026-04-16 | Release 9 | 2026-04-30 | Yet to start |  | lmu | Release 7 | 2026-04-02 | diff
11 | addressBook | Release 8 | 2026-04-16 | Release 9 | 2026-04-30 | Yet to start |  | enrollment | Release 8 | 2026-04-16 | diff
12 | progressionPlan | Release 8 | 2026-04-16 | Release 9 | 2026-04-30 | Yet to start |  | addressBook | Release 8 | 2026-04-16 | diff
13 | orderAware | Release 10 | 2026-05-14 | Release 9 | 2026-04-30 | Yet to start |  | progressionPlan | Release 8 | 2026-04-16 | diff
14 | extendedField | Release 8 | 2026-04-16 | Release 11 | 2026-05-28 | Yet to start |  | extendedField | Release 8 | 2026-04-16 | same
15 | content | Release 9 | 2026-04-30 | Release 11 | 2026-05-28 | Yet to start |  | content | Release 9 | 2026-04-30 | same
16 | log | Release 9 | 2026-04-30 | Release 11 | 2026-05-28 | Yet to start |  | log | Release 9 | 2026-04-30 | same
17 | assessments | Release 9 | 2026-04-30 | Release 11 | 2026-05-28 | Yet to start |  | assessments | Release 9 | 2026-04-30 | same
18 | assetAware | Release 10 | 2026-05-14 | Release 11 | 2026-05-28 | Yet to start |  | assetAware | Release 10 | 2026-05-14 | same
19 | attandance | Release 10 | 2026-05-14 | Release 12 | 2026-06-11 | Yet to start |  | attandance | Release 10 | 2026-05-14 | same
20 | webuser | Release 11 | 2026-05-28 | Release 12 | 2026-06-11 | Yet to start |  | orderAware | Release 10 | 2026-05-14 | diff
21 | communication | Release 11 | 2026-05-28 | Release 12 | 2026-06-11 | Yet to start |  | webuser | Release 11 | 2026-05-28 | diff
22 | location | Release 11 | 2026-05-28 | Release 12 | 2026-06-11 | Yet to start |  | communication | Release 11 | 2026-05-28 | diff
23 | registration.aspx.cs | Release 12 | 2026-06-11 | Release 12 | 2026-06-11 | Yet to start |  | location | Release 11 | 2026-05-28 | diff
24 | reports | Release 12 | 2026-06-11 | Release 12 | 2026-06-11 | Yet to start |  | home | Release 12 | 2026-06-11 | diff
25 | lmu | Release 7 | 2026-04-02 | Release 13 | 2026-06-25 | On Hold |  | registration.aspx.cs | Release 12 | 2026-06-11 | diff
26 | home | Release 12 | 2026-06-11 | Release 13 | 2026-06-25 | Yet to start |  | reports | Release 12 | 2026-06-11 | diff
Formulas:
Total Estimate (SP) = VLOOKUP([Overall Module],J41:L67,3,FALSE)

## Resources
Current POD Structures |  |  |  |  | Current POD Structures
Track | Client role | Employee Type | POD# | Names | Track | Client role | Employee Type | POD# | Names
Backend | BE Dev Sr - 1 | Offshore - Employee | POD-1 | Anil Reddy | Backend | BE Dev Sr - 1 | Offshore - Employee | POD-1 | Anil Reddy
Backend | BE Dev Jr - 2 | Offshore - Employee |  | Sohith Reddy | Backend | BE Dev Jr - 2 | Offshore - Employee |  | Sohith Reddy
Backend | BE Dev Sr - 3 | Offshore - Employee |  | Vijaya Agavendran | Backend | BE Dev Sr - 3 | Offshore - Employee |  | Vijaya Agavendran
Frontend | FE Dev Jr - 4 | Offshore - Employee |  | Krishna Gautham | Frontend | FE Dev Jr - 4 | Offshore - Employee |  | Krishna Gautham
Frontend | FE Dev Sr - 4 | Offshore - Employee |  | Pardeep Singh | Backend | BE Dev Sr | Offshore - Employee | POD-2 | Ramesh C
Frontend | FE ELT | Offshore - Employee |  | Shruti Madoti | Backend | BE Dev Sr - 2 | Offshore - Employee |  | Amol Patil
Backend | BE Dev Sr | Offshore - Employee | POD-2 | Ravi Ranjan | Backend | BE Dev Jr - 5 | Offshore - Employee |  | Rizwana
Backend | BE Dev Sr | Offshore - Employee |  | Ramesh C | Frontend | FE Dev Sr - 1 | Offshore - Employee |  | Manikadan G
Backend | BE Dev Sr - 2 | Offshore - Employee |  | Amol Patil | Frontend | FE Dev Sr - 2 | Offshore - Employee |  | Tushar B
Backend | BE Dev Jr - 5 | Offshore - Employee |  | Rizwana | Backend | BE ELT | Offshore - Employee | POD -3 | Prem khandelwal
Frontend | FE Dev Jr - 1 | Offshore - Employee |  | Varshini Edara | Backend | BE ELT | Offshore - Employee |  | Swarneem Nandanwar
Frontend | FE Dev Sr - 1 | Offshore - Employee |  | Manikadan G | Backend | FS Lead | Offshore - Employee |  | Mizan Shaikh
Frontend | FE Dev Sr - 2 | Offshore - Employee |  | Tushar B | Frontend | FE Dev Jr - 2 | Offshore - Employee |  | Vishnu Bagde
Backend | BE ELT | Offshore - Employee | POD -3 | Prem khandelwal | Frontend | FE Dev Jr - 3 | Offshore - Employee |  | Gaurav Vilas Barde
Backend | BE ELT | Offshore - Employee |  | Swarneem Nandanwar | Backend | BE Dev -1 | Offshore - Employee | POD - 4 | TBD
Backend | FS Lead | Offshore - Employee |  | Mizan Shaikh | Backend | BE Dev -2 | Offshore - Employee |  | TBD
Frontend | FE Dev Jr - 2 | Offshore - Employee |  | Vishnu Bagde | Backend | BE Dev - 3 | Offshore - Employee |  | TBD
Frontend | FE Dev Jr - 3 | Offshore - Employee |  | Gaurav Vilas Barde | QA | Agentic AI Dev | Offshore - Employee | POD-QE | Balamurugan Vasudevan
Frontend | FE Dev Sr - 2 | Offshore - Employee |  | Rajnath | QA | QA ELT - 1 | Offshore - Employee |  | Shuti Katapally
Backend | BE Dev Sr | Offshore - Employee | POD - 4 | TBD | QA | QA ELT - 2 | Offshore - Employee |  | Pavitra Rajendran
Backend | BE Dev Sr | Offshore - Employee |  | TBD | QA | QA Jr - 1 | Offshore - Employee |  | Tinu Tony
Backend | BE Dev Sr - 2 | Offshore - Employee |  | TBD | QA | QA Jr - 2 | Offshore - Employee |  | Karthik Muthuswammy
QA | Agentic AI Dev | Offshore - Employee | POD-QE | Balamurugan Vasudevan | QA | QA Jr Add'l | Offshore - Employee |  | Prabhu Krishnamurthy
QA | QA ELT - 1 | Offshore - Employee |  | Shuti Katapally | QA | QA Sr - 1 | Offshore - Employee |  | Thanu S
QA | QA ELT - 2 | Offshore - Employee |  | Pavitra Rajendran | QA | QA Sr - 2 | Offshore - Employee |  | Suryaprakash V
QA | QA Jr - 1 | Offshore - Employee |  | Tinu Tony | QA | QE ELT | Offshore - Employee |  | Ajay Chevuri
QA | QA Jr - 2 | Offshore - Employee |  | Karthik Muthuswammy | QA | QE - Assessibility Testing | Offshore - Employee |  | Hemapriya P
QA | QA Jr Add'l | Offshore - Employee |  | Prabhu Krishnamurthy | QA | QE - Perf Testing | Offshore - Employee |  | Satish
QA | QA Sr - 1 | Offshore - Employee |  | Thanu S | QA | QE - Perf Testing | Offshore - Employee |  | Vidhyashree
QA | QA Sr - 2 | Offshore - Employee |  | Suryaprakash V
QA | QE ELT | Offshore - Employee |  | Ajay Chevuri
QA | QE - Assessibility Testing | Offshore - Employee |  | Hemapriya P
QA | QE - Perf Testing | Offshore - Employee |  | Satish
QA | QE - Perf Testing | Offshore - Employee |  | Vidhyashree

## Holidays
Holiday Name | Date
Republic Day | 2026-01-26
Holi | 2026-03-04
Ugadi/Gudi padvo | 2026-03-19
Good Friday | 2026-04-03
Tamil New Year's Day | 2026-04-14
May Day | 2026-05-01
Bakrid | 2026-05-28
Telangana State Formation Day | 2026-06-02
Muharram | 2026-06-26
Vinayaka Chaturdhi | 2026-09-14
Eid ul-Adha | 2026-07-07
Varamahalakshmi Vrata | 2026-08-21
Eid-Milad/Onam | 2026-08-26
Gandhi Jayanti | 2026-10-02
Vinayaka Chaturdh | 2026-09-14
Ayudh Pooja/Dushera | 2026-10-20
Vijayadasami | 2026-10-21
Deepavali/Diwali | 2026-11-10
Christmas | 2026-12-25

## April
No. | Module | Target page Technology | Recieved Functional & Non Fuctional Walkthrough | Buffer In case of no KT | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Code Freeze Date | TEST Deployment | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | Code freeze date = Release cutoff Date | Release # | Release Date (2-Wk Cycle) | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
1 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | default.aspx | Pod 3 | Pod 3_Swarneem | 2026-03-23 | 3 | 1 | 2026-03-25 | 2026-03-25 | 2026-03-23 | 3 | 2026-04-03 | 1.5 | 2026-04-06 | 2026-04-06 | 3 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 |  | 2026-04-10 | 2 | 2026-04-15 | 3 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-22 |  | 2026-04-22 | 0 | 2026-04-22 | 0 | 2026-04-22 | 2026-04-23 | Release 9 | 2026-04-30 | 36 |  | 9
2 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | addressBook.aspx | Pod 3 | Pod 3_Swarneem/Mizan | 2026-03-19 | 3 | 2 | 2026-03-20 | 2026-03-24 | 2026-03-23 | 3 | 2026-04-03 | 1.5 | 2026-04-06 | 2026-04-06 | 3 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 |  | 2026-04-10 | 2 | 2026-04-15 | 3 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-22 |  | 2026-04-22 | 0 | 2026-04-22 | 0 | 2026-04-22 | 2026-04-23 | Release 9 | 2026-04-30 | 37 |  | 9
3 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | automatedRoleAssignment | Pod 3 | Pod 3_Mizan | 2026-03-27 | 3 | 3 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3 | 2026-04-03 | 1.5 | 2026-04-06 | 2026-04-06 | 3 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 |  | 2026-04-10 | 2 | 2026-04-15 | 3 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-22 |  | 2026-04-22 | 0 | 2026-04-22 | 0 | 2026-04-22 | 2026-04-23 | Release 9 | 2026-04-30 | 30 |  | 9
4 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | mailboxes.aspx | Pod 3 | Pod 3_Swarneem | 2026-03-16 | 3 | 4 | 2026-03-18 | 2026-03-18 | 2026-03-23 | 3 | 2026-04-03 | 1.5 | 2026-04-06 | 2026-04-06 | 3 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 |  | 2026-04-10 | 2 | 2026-04-15 | 3 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-22 |  | 2026-04-22 | 0 | 2026-04-22 | 0 | 2026-04-22 | 2026-04-23 | Release 9 | 2026-04-30 | 43 |  | 9
5 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | page_5 | Pod 3 | Pod 3_Swarneem/Mizan | 2026-04-20 | 3 | 5 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 3 | 2026-04-27 | 1.5 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 3 | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | 2026-06-11 | 50 | #VALUE! | 9 |  |  | #VALUE!
6 | OrderAware |  | Yes | 0 | 2026-06-01 | page_5 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | 2026-07-09 | 35 |  | 92362
7 | OrderAware |  | No | 0 | 2026-04-08 | orderAware\default.aspx - form | Pod UI | Manikandan | 2026-04-20 | 5 | 1 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 3 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 2 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | 2026-05-28 | 34 |  | 92280
8 | OrderAware |  | Yes | 0 | 2026-06-05 | page_6 | Pod 3 | Pod 3_Member3 | 2026-06-05 | 3 | 2 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | 2026-07-09 | 30 |  | 92372
9 | OrderAware |  | No | 0 | 2026-04-08 | orderAware\default.aspx - search result table | Pod UI | Gaurav | 2026-04-08 | 5 | 1 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 3 | 2026-04-20 | 1.5 | 2026-04-21 | 2026-04-21 | 3 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 |  | 2026-04-27 | 2 | 2026-04-29 | 3 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 |  | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 |  | 2026-05-07 | 0 | 2026-05-07 | 0 | 2026-05-07 | 2026-05-07 | Release 10 | 2026-05-14 | 29 |  | 92262
10 | OrderAware |  | Yes | 0 | 2026-06-10 | page_7 | Pod 3 | Pod 3_Member1 | 2026-06-10 | 3 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | 2026-07-23 | 41 |  | 92378
11 | OrderAware |  | No | 0 | 2026-04-08 | orderAware\shippingInformation.aspx | Pod UI | Goutham | 2026-04-08 | 1.5 | 1 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 3 | 2026-04-13 | 1.5 | 2026-04-15 | 2026-04-15 | 3 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 |  | 2026-04-21 | 2 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 |  | 2026-04-30 | 0 | 2026-04-30 | 0 | 2026-04-30 | 2026-05-07 | Release 10 | 2026-05-14 | 36 |  | 92249
12 | OrderAware |  | Yes | 0 | 2026-06-05 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-05 | 3 | 4 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 3 | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | 2026-07-23 | 44 |  | 92372
13 | OrderAware |  | No | 0 | 2026-04-08 | orderAware\orderExport.aspx | Pod UI | Manikandan | 2026-04-08 | 2.5 | 1 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 3 | 2026-04-15 | 1.5 | 2026-04-16 | 2026-04-16 | 3 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-22 | 2026-04-22 |  | 2026-04-22 | 2 | 2026-04-24 | 3 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 |  | 2026-05-04 | 0 | 2026-05-04 | 0 | 2026-05-04 | 2026-05-07 | Release 10 | 2026-05-14 | 35 |  | 92251
14 | OrderAware |  | No | 0 | 2026-06-01 | orderAware\automatedOrders.aspx | Pod UI | Gaurav | 2026-06-01 | 5 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 3 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | 2026-07-09 | 31 |  | 92368
15 | Location | Complete ASP | Yes | 0 | 2026-04-13 | page_1 | Pod 2 | Pod 3_Member3 | 2026-04-13 | 3 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | 2026-06-11 | #VALUE! |  | 92306
16 | Location | Complete ASP | Yes | 0 | 2026-04-13 | page_2 | Pod 2 | Pod 3_Member1 | 2026-04-13 | 3 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | 2026-06-11 | #VALUE! | #VALUE! | 92306 |  |  | #VALUE!
17 | Location | Complete ASP | Yes | 0 | 2026-04-13 | page_3 | Pod 2 | Pod 3_Member2 | 2026-04-13 | 3 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 3 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 |  | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | 2026-06-11 | #VALUE! |  | 92298
18 | Location | Complete ASP | Yes | 0 | 2026-04-16 | page_4 | Pod 3 | Pod 3_Member3 | 2026-04-16 | 3 | 4 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | 2026-06-11 | #VALUE! |  | 92316
19 | Location | Complete ASP | Yes | 0 | 2026-04-16 | page_5 | Pod 3 | Pod 3_Member1 | 2026-04-16 | 3 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | 2026-06-11 | #VALUE! |  | 92316
20 | Location | Complete ASP | Yes | 0 | 2026-04-16 | page_6 | Pod 3 | Pod 3_Member2 | 2026-04-16 | 3 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | 2026-06-11 | #VALUE! |  | 92306
21 | Location | Complete ASP | Yes | 0 | 2026-05-13 | page_7 | Pod 3 | Pod 3_Member3 | 2026-05-13 | 3 | 7 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | 2026-06-25 | #VALUE! |  | 92322
22 | Location | Complete ASP | Yes | 0 | 2026-05-13 | page_8 | Pod 3 | Pod 3_Member1 | 2026-05-13 | 3 | 8 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | 2026-06-25 | #VALUE! |  | 92322
23 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_9 | Pod 3 | Pod 3_Member2 | 2026-05-08 | 3 | 9 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | 2026-06-11 | #VALUE! |  | 92316
24 | Location | Complete ASP | Yes | 0 | 2026-05-18 | page_10 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 10 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | 2026-06-25 | #VALUE! |  | 92332
25 | Location | Complete ASP | Yes | 0 | 2026-05-18 | page_11 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 11 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | 2026-07-09 | #VALUE! |  | 92332
26 | Library | Complete ASP | Yes | 0 | 2026-04-20 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-20 | 3 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 3 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 |  | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | 2026-06-11 | #VALUE! |  | 92298
27 | Library | Complete ASP | Yes | 0 | 2026-04-24 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | 2026-05-28 | #VALUE! |  | 92289
28 | Library | Complete ASP | Yes | 0 | 2026-04-29 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-29 | 3 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 3 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 3 | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | 2026-06-25 | #VALUE! |  | 92298
36 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | page_1 | Pod 1 | Pod 1_Member1 | 2026-05-18 | 3 | 1 | #VALUE! | #VALUE! | #VALUE! | 3 | #VALUE! | 1.5 | #VALUE! | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 2 | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #N/A | #N/A | #N/A |  | #VALUE!
37 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member2 | 2026-05-08 | 3 | 2 | #VALUE! | #VALUE! | #VALUE! | 3 | #VALUE! | 1.5 | #VALUE! | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 2 | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #N/A | #N/A | #N/A |  | #VALUE!
38 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-05 | page_3 | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 3 | #VALUE! | #VALUE! | #VALUE! | 3 | #VALUE! | 1.5 | #VALUE! | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 2 | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #N/A | #N/A | #N/A |  | #VALUE!
39 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-21 | page_4 | Pod 1 | Pod 1_Member1 | 2026-05-21 | 3 | 4 | #VALUE! | #VALUE! | #VALUE! | 3 | #VALUE! | 1.5 | #VALUE! | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 2 | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #N/A | #N/A | #N/A |  | #VALUE!
40 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-13 | page_5 | Pod 1 | Pod 1_Member2 | 2026-05-13 | 3 | 5 | #VALUE! | #VALUE! | #VALUE! | 3 | #VALUE! | 1.5 | #VALUE! | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 2 | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #N/A | #N/A | #N/A |  | #VALUE!
41 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | page_6 | Pod 1 | Pod 1_Member3 | 2026-05-08 | 3 | 6 | #VALUE! | #VALUE! | #VALUE! | 3 | #VALUE! | 1.5 | #VALUE! | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 2 | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #N/A | #N/A | #N/A |  | #VALUE!
42 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-26 | page_7 | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 7 | #VALUE! | #VALUE! | #VALUE! | 3 | #VALUE! | 1.5 | #VALUE! | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 2 | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #N/A | #N/A | #N/A |  | #VALUE!
43 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-18 | 3 | 8 | #VALUE! | #VALUE! | #VALUE! | 3 | #VALUE! | 1.5 | #VALUE! | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3 | #VALUE! | 2 | #VALUE! | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3 | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #N/A | #N/A | #N/A |  | #VALUE!
Gradebook
LMU
Formulas:
Start Date = [Module Target Start (Input)]
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Code Freeze Date = [TCR Bugs Closure Date]
Pearson Regression Testing/UAT Date = WORKDAY([TEST Deployment], 1, IndHolidays)
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR raised date = WORKDAY([Developer]-1, [Start Date]+[Dev Efforts], IndHolidays)
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&(MAX([PR Response receive Date],[TCR Bugs Closure Date])))
Co- Pilot Comment Closure Date = WORKDAY([Developer]-1, [Start Date]+[Dev Efforts], IndHolidays)
Unit Testing Closure Date = WORKDAY([Developer]-1, [Start Date]+[Dev Efforts], IndHolidays)

## Pivot
Count of Page | Column Labels
| Apr | Apr Total | May |  | May Total | Jun |  | Jun Total | Jul |  | Jul Total | Aug |  | Aug Total | Grand Total
| 16-Apr |  | 28-May | 28-May Total |  | 11-Jun | 25-Jun |  | 9-Jul | 23-Jul |  | 6-Aug | 20-Aug
Row Labels |  |  | 2026-05-28
AddressBook |  |  | 4 | 4 | 4 | [9 empty] | 4 |  | Modules | 28-May | 11-Jun | 25-Jun | 9-Jul | 23-Jul | 6-Aug | 20-Aug | Total
Assessments |  |  | 9 | 9 | 9 | 1 | 1 | 2 | [6 empty] | 11 |  | Assessments | 9 | 1 | 1 |  |  |  |  | 11
AssetAware |  |  | 1 | 1 | 1 | 3 | 1 | 4 | 1 |  | 1 |  |  |  | 6 |  | AssetAware | 1 | 3 | 1 | 1 |  |  |  | 6
Communication | [5 empty] | 2 |  | 2 | [6 empty] | 2 |  | Communication |  | 2 | [5 empty] | 2
Content |  |  | 3 | 3 | 3 | 1 | 1 | 2 | 2 | 3 | 5 | 1 |  | 1 | 11 |  | Content | 3 | 1 | 1 | 2 | 3 | 1 |  | 11
Enrollment | [5 empty] | 3 | 3 | 6 | [6 empty] | 6 |  | Enrollment |  | 3 | 3 |  |  |  |  | 6
ExtendedField | [5 empty] | 3 | 3 | 6 | 1 |  | 1 |  |  |  | 7 |  | ExtendedField |  | 3 | 3 | 1 |  |  |  | 7
GradeBook | [6 empty] | 2 | 2 | 3 | 6 | 9 | 3 |  | 3 | 14 |  | GradeBook | 3 |  | 2 | 3 | 3 | 3 |  | 14
Home |  |  | 2 | 2 | 2 | 1 | 1 | 2 | [6 empty] | 4 |  | Home | 2 | 1 | 1 |  |  |  |  | 4
IssueAware | [5 empty] | 1 |  | 1 | 1 |  | 1 |  |  |  | 2 |  | Library | 1 | 1 | 2 |  |  |  |  | 4
Library |  |  | 1 | 1 | 1 | 1 | 2 | 3 | [6 empty] | 4 |  | LMU |  | 1 | 5 | 4 | 7 | 3 | 10 | 30
LMU | [5 empty] | 1 | 10 | 11 | 9 | 7 | 16 | 3 |  | 3 | 30 |  | Location |  | 6 | 2 |  |  |  |  | 8
Location | [5 empty] | 6 | 2 | 8 | [6 empty] | 8 |  | Log |  |  |  | 1 | 2 | 3 | 1 | 7
Log | [8 empty] | 1 | 2 | 3 | 2 | 1 | 3 | 6 |  | OrderAware |  |  |  | 6 | 3 |  |  | 9
OrderAware | [8 empty] | 6 | 3 | 9 |  |  |  | 9 |  | ProgressionPlan |  |  | 2 | 3 | 2 |  |  | 7
ProgressionPlan | [6 empty] | 2 | 2 | 3 | 2 | 5 |  |  |  | 7 |  | Reg+Attendance |  |  |  | 1 | 3 |  |  | 4
Reg+Attendance | [8 empty] | 1 | 3 | 4 |  |  |  | 4 |  | Reports |  |  | 3 | 2 | 2 | 3 | 3 | 13
Reports | [5 empty] | 1 | 3 | 4 | 2 | 2 | 4 | 3 | 3 | 6 | 14 |  | Webuser |  | 1 | 6 | 3 |  |  |  | 10
Webuser | [5 empty] | 1 | 6 | 7 | 3 |  | 3 |  |  |  | 10 |  | Security | 3 | 1 | [5 empty] | 4
Security | 2 | 2 | 3 | 3 | 3 | 1 |  | 1 | [6 empty] | 6 |  | Total | 22 | 24 | 32 | 27 | 25 | 13 | 14 | 157
Grand Total | 2 | 2 | 23 | 23 | 23 | 26 | 37 | 63 | 33 | 28 | 61 | 12 | 4 | 16 | 165
External | Deployed
ImportStatus | Deployed
Forum | Delayed
Planner | Deferred
Timeline | Out of scope
Count of Page | Column Labels
| <4/16/26 | <4/16/26 Total | Apr |  | Apr Total | May |  | May Total | Jun |  | Jun Total | Jul |  | Jul Total | Aug |  | Aug Total | Grand Total
| <4/16/26 |  | 16-Apr | 16-Apr Total |  | 28-May | 28-May Total |  | 11-Jun | 25-Jun |  | 9-Jul | 23-Jul |  | 6-Aug | 20-Aug
Row Labels |  |  | 2026-04-16 |  |  | 2026-05-28
AddressBook | [5 empty] | 4 | 4 | 4 | 1 |  | 1 | [6 empty] | 5
Assessments | [5 empty] | 5 | 5 | 5 | 4 | 1 | 5 | [6 empty] | 10 |  | Modules vs. No. of pages | 28-May | 11-Jun | 25-Jun | 9-Jul | 23-Jul | 6-Aug | 20-Aug | Total | Modules vs. No. of pages | 28-May | 11-Jun | 25-Jun | 9-Jul | 23-Jul | 6-Aug | 20-Aug | Total
AssetAware | 3 | 3 |  |  |  | 3 | 3 | 3 | 2 |  | 2 | [6 empty] | 8 |  | Assessments | 5 | 4 | 1 |  |  |  |  | 10 | Assessments | 5 | 4 | 1 |  |  |  |  | 10
Communication | [8 empty] | 3 |  | 3 | 1 |  | 1 |  |  |  | 4 |  | AssetAware | 3 | 2 | [5 empty] | 5 | AssetAware | 3 | 2 | [5 empty] | 5
Content | 5 | 5 |  |  |  | 1 | 1 | 1 | 2 | 1 | 3 | [6 empty] | 9 |  | Communication |  | 3 |  | 1 |  |  |  | 4 | Communication |  | 3 |  | 1 |  |  |  | 4
Enrollment | [8 empty] | 4 | 3 | 7 | 1 |  | 1 |  |  |  | 8 |  | Content | 6 | 2 | 1 |  |  |  |  | 9 | Content | 6 | 2 | 1 |  |  |  |  | 9
ExtendedField | [8 empty] | 3 | 3 | 6 | 2 |  | 2 |  |  |  | 8 |  | Enrollment |  | 4 | 3 | 1 |  |  |  | 8 | Enrollment |  | 4 | 3 | 1 |  |  |  | 8
GradeBook | [9 empty] | 2 | 2 | 2 | 7 | 9 | 7 |  | 7 | 18 |  | ExtendedField |  | 3 | 3 | 2 |  |  |  | 8 | ExtendedField |  | 3 | 3 | 2 |  |  |  | 8
Home | [5 empty] | 1 | 1 | 1 |  | 3 | 3 | [6 empty] | 4 |  | GradeBook |  |  | 2 | 2 | 7 | 7 |  | 18 | GradeBook |  |  | 2 | 2 | 7 | 7 |  | 18
IssueAware | [8 empty] | 1 |  | 1 | 1 |  | 1 |  |  |  | 2 |  | Home | 1 |  | 3 |  |  |  |  | 4 | Home | 1 |  | 3 |  |  |  |  | 4
Library_Part 2 | [5 empty] | 1 | 1 | 1 | [9 empty] | 1 |  | Library | 1 | 1 | 1 |  |  |  |  | 3 | Library | 1 | 1 | 1 |  |  |  |  | 3
Library_Part 3 | [8 empty] | 1 | 1 | 2 | [6 empty] | 2 |  | LMU |  | 1 | 11 | 9 | 8 | 3 |  | 32 | LMU |  | 1 | 11 | 9 | 8 | 3 |  | 32
LMU | [8 empty] | 1 | 11 | 12 | 9 | 8 | 17 | 3 |  | 3 | 32 |  | Location |  | 7 | 3 | 1 |  |  |  | 11 | Location |  | 7 | 3 | 1 |  |  |  | 11
Location | [8 empty] | 7 | 3 | 10 | 1 |  | 1 |  |  |  | 11 |  | Log |  |  | 2 | 2 | 2 | 3 | 1 | 10 | Log |  |  | 2 | 2 | 2 | 3 | 1 | 10
Log | [9 empty] | 2 | 2 | 2 | 2 | 4 | 3 | 1 | 4 | 10 |  | OrderAware |  |  |  | 6 | 3 |  |  | 9 | OrderAware |  |  |  | 6 | 3 |  |  | 9
OrderAware | [11 empty] | 6 | 3 | 9 |  |  |  | 9 |  | ProgressionPlan |  |  | 3 | 2 | 2 |  |  | 7 | ProgressionPlan |  |  | 3 | 2 | 2 |  |  | 7
ProgressionPlan | [9 empty] | 3 | 3 | 2 | 2 | 4 |  |  |  | 7 |  | Reg+Attendance |  |  |  | 2 | 2 |  | 1 | 5 | Reg+Attendance |  |  |  | 2 | 2 |  | 1 | 5
Reg+Attendance | [11 empty] | 2 | 2 | 4 |  | 1 | 1 | 5 |  | Reports |  |  |  |  | 1 | 3 | 1 | 5 | Reports |  |  |  |  | 1 | 3 | 1 | 5
Reports | [12 empty] | 1 | 1 | 3 | 1 | 4 | 5 |  | Security | 3 | 1 | [5 empty] | 4 | Security | 3 | 1 | [5 empty] | 4
Security |  |  | 2 | 2 | 2 | 3 | 3 | 3 | 1 |  | 1 | [6 empty] | 6 |  | Webuser |  | 1 | 4 | 4 | 1 |  |  | 10 | Webuser |  | 1 | 4 | 4 | 1 |  |  | 10
Webuser | [8 empty] | 1 | 4 | 5 | 4 | 1 | 5 |  |  |  | 10 |  | Total Pages | 19 | 29 | 37 | 32 | 26 | 16 | 3 | 162 | Total Pages | 19 | 29 | 37 | 32 | 26 | 16 | 3 | 162
Grand Total | 8 | 8 | 2 | 2 | 2 | 18 | 18 | 18 | 31 | 37 | 68 | 33 | 26 | 59 | 16 | 3 | 19 | 174 |  | Minimum Number of PRs | 19 | 29 | 37 | 32 | 26 | 16 | 3 | 162 | Total PRs | 20.9 | 31.9 | 40.7 | 35.2 | 28.6 | 17.6 | 3.3 | 178.2
[20 empty] | Including Additional PRs | 20.9 | 31.9 | 40.7 | 35.2 | 28.6 | 17.6 | 3.3 | 178.2
[20 empty] | Buffer | 10% | 10% | 10% | 10% | 10% | 10% | 10% |  | Limit | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 178
[30 empty] | 28-May | 11-Jun | 25-Jun | 9-Jul | 23-Jul | 6-Aug | 20-Aug | 2026-09-03 | 2026-09-17 | 2026-10-01 | 2026-10-15 | 2026-10-29 | 2026-11-12 | 2026-11-26 | 2026-12-10
[20 empty] | AddressBook | Planned for 5/14
[20 empty] | IssueAware | Planned for 5/14
[20 empty] | External | Deployed
[20 empty] | ImportStatus | Deployed
[20 empty] | Forum | Delayed
[20 empty] | Planner | Deferred
[20 empty] | Timeline | Out of scope

## Optimization#1(PR-1)
No. | Module | Target page Technology | Recieved Functional & Non Fuctional Walkthrough | Buffer In case of no KT | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Code Freeze Date | TEST Deployment | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | Code freeze date = Release cutoff Date | Release # | Release Request Approved Date | Release Date (2-Wk Cycle) | Code freeze date = Release cutoff Date | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
1 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-20 | 1.5 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | #VALUE! | 27 |  | 3
2 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_2 | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-20 | 1.5 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 27 |  | 3
3 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-20 | 1.5 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 27 |  | 3
4 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | page_4 | Pod 1 | Pod 1_Member1 | 2026-04-20 | 3 | 0 | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 1.5 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 |  | 2026-05-05 | 0 | 2026-05-05 | 0 | 2026-05-05 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 22 |  | 3
5 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | page_5 | Pod 1 | Pod 1_Member2 | 2026-04-20 | 3 | 0 | 5 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 1.5 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 3 | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 | #VALUE! | 3 |  |  | #VALUE!
6 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_1 | Pod 2 | Pod 2_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-20 | 1.5 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 27 |  | 3
7 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_2 | Pod 2 | Pod 2_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-20 | 1.5 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 27 |  | 3
8 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_3 | Pod 2 | Pod 2_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-20 | 1.5 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 27 |  | 3
9 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_4 | Pod 2 | Pod 2_Member1 | 2026-04-20 | 3 | 0 | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 1.5 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 |  | 2026-05-05 | 0 | 2026-05-05 | 0 | 2026-05-05 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 22 |  | 3
10 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_5 | Pod 2 | Pod 2_Member2 | 2026-04-20 | 3 | 0 | 5 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 1.5 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 |  | 2026-05-05 | 0 | 2026-05-05 | 0 | 2026-05-05 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 22 |  | 3
11 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_6 | Pod 2 | Pod 2_Member3 | 2026-04-20 | 3 | 0 | 6 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 1.5 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 |  | 2026-05-05 | 0 | 2026-05-05 | 0 | 2026-05-05 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 22 |  | 3
12 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_7 | Pod 2 | Pod 2_Member1 | 2026-04-24 | 3 | 0 | 7 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
13 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_8 | Pod 2 | Pod 2_Member2 | 2026-04-24 | 3 | 0 | 8 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 | #VALUE! | 3 |  |  | #VALUE!
14 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_9 | Pod 2 | Pod 2_Member3 | 2026-04-24 | 3 | 0 | 9 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
15 | Assessments | Complete ASP | Yes | 0 | 2026-04-29 | page_10 | Pod 2 | Pod 2_Member1 | 2026-04-29 | 3 | 0 | 10 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 1 | 2026-05-05 | 1.5 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 3 | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 3
16 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-28 | 3 | 0 | 1 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 28 |  | 3
17 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | page_2 | Pod 3 | Pod 1_Member2 | 2026-04-28 | 3 | 0 | 2 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 28 |  | 3
18 | AssetAware | Complete ASP | No | 2 | 2026-04-20 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-22 | 3 | 0 | 3 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 1.5 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | 1 | 2026-05-04 | 1 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 |  | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 |  | 2026-05-07 | 0 | 2026-05-07 | 0 | 2026-05-07 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 20 |  | 3
19 | AssetAware | Complete ASP | No | 2 | 2026-05-01 | page_4 | Pod 1 | Pod 1_Member1 | 2026-05-05 | 3 | 0 | 4 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 3 | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 3
20 | Communication | Complete ASP | No | 2 | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-07 | 3 | 0 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 |  | 2026-05-21 | 0 | 2026-05-21 | 0 | 2026-05-21 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 17 |  | 3
21 | Communication | Complete ASP | No | 2 | 2026-04-29 | page_2 | Pod 2 | Pod 2_Member2 | 2026-05-01 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 22 |  | 3
22 | Communication | Complete ASP | No | 2 | 2026-04-29 | page_3 | Pod 2 | Pod 2_Member3 | 2026-05-01 | 3 | 0 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 22 |  | 3
23 | Communication | Complete ASP | No | 2 | 2026-05-12 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 1 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 | #VALUE! | 3 |  |  | #VALUE!
24 | Content | Complete ASP | No | 2 | 2026-04-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 | 0 | 1 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 |  | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 |  | 2026-05-04 | 0 | 2026-05-04 | 0 | 2026-05-04 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 23 |  | 3
25 | Content | Complete ASP | No | 2 | 2026-04-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-17 | 3 | 0 | 2 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 |  | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 |  | 2026-05-04 | 0 | 2026-05-04 | 0 | 2026-05-04 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 23 |  | 3
26 | Content | Complete ASP | No | 2 | 2026-04-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-17 | 3 | 0 | 3 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 |  | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 |  | 2026-05-04 | 0 | 2026-05-04 | 0 | 2026-05-04 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 23 |  | 3
27 | Content | Complete ASP | No | 2 | 2026-04-22 | page_4 | Pod 3 | Pod 3_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 1 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 3 | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
28 | Enrollment | Complete ASP | No | 2 | 2026-04-27 | page_1 | Pod 1 | Pod 1_Member3 | 2026-04-29 | 3 | 0 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 1 | 2026-05-05 | 1.5 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 1 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 24 |  | 3
29 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member1 | 2026-05-12 | 3 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 28 |  | 3
30 | Enrollment | Complete ASP | No | 2 | 2026-05-01 | page_3 | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 |  | 3
31 | Enrollment | Complete ASP | No | 2 | 2026-05-05 | page_4 | Pod 1 | Pod 1_Member3 | 2026-05-07 | 3 | 0 | 4 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 |  | 2026-05-21 | 0 | 2026-05-21 | 0 | 2026-05-21 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 17 |  | 3
32 | Enrollment | Complete ASP | No | 2 | 2026-05-15 | page_5 | Pod 1 | Pod 1_Member1 | 2026-05-19 | 3 | 0 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 1 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 21 |  | 3
33 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | page_6 | Pod 1 | Pod 1_Member2 | 2026-05-12 | 3 | 0 | 6 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 28 |  | 3
34 | Enrollment | Complete ASP | No | 2 | 2026-05-12 | page_7 | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 7 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 24 |  | 3
35 | Enrollment | Complete ASP | No | 2 | 2026-05-22 | page_8 | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 0 | 8 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 3 | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 3
36 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | page_1 | Pod 1 | Pod 1_Member1 | 2026-05-18 | 3 | 0 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 22 |  | 3
37 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 1 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
38 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-05 | page_3 | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 |  | 3
39 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-21 | page_4 | Pod 1 | Pod 1_Member1 | 2026-05-21 | 3 | 0 | 4 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
40 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-13 | page_5 | Pod 1 | Pod 1_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 27 |  | 3
41 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | page_6 | Pod 1 | Pod 1_Member3 | 2026-05-08 | 3 | 0 | 6 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 1 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
42 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-26 | page_7 | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 0 | 7 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 27 |  | 3
43 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 3
44 | GradeBook | Complete ASP | Yes | 0 | 2026-05-13 | page_3 | Pod 2 | Pod 2_Member1 | 2026-05-13 | 3 | 0 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 3 | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 3
45 | GradeBook | Complete ASP | Yes | 0 | 2026-05-05 | page_4 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 3 | 2026-05-29 | 1 | 2026-06-01 | 2 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 5
46 | Home | Complete ASP | No | 2 | 2026-04-22 | page_1 | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
47 | Home | Complete ASP | No | 2 | 2026-04-29 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-01 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 22 |  | 3
48 | Home | Complete ASP | No | 2 | 2026-04-22 | page_3 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
49 | Home | Complete ASP | No | 2 | 2026-04-29 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-01 | 3 | 0 | 4 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 3 | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 | #VALUE! | 3 |  |  | #VALUE!
50 | IssueAware | Complete ASP | Yes | 0 | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 |  | 3
51 | IssueAware | Complete ASP | Yes | 0 | 2026-05-18 | page_2 | Pod 2 | Pod 2_Member1 | 2026-05-18 | 3 | 0 | 2 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 3
52 | Library | Complete ASP | Yes | 0 | 2026-04-29 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-29 | 3 | 0 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 1 | 2026-05-05 | 1.5 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 1 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 24 |  | 3
53 | Library | Complete ASP | Yes | 0 | 2026-04-24 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
54 | Library | Complete ASP | Yes | 0 | 2026-04-29 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 1 | 2026-05-05 | 1.5 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 3 | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 3
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_2 | Pod 2 | Pod 2_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 1 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 3 | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_2 | Pod UI | Pod UI_UI-Member1 | 2026-05-08 | 5 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 3 | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 3
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod 2 | Pod 2_Member3 | 2026-05-08 | 3 | 0 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 1 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 | #VALUE! | 3
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod UI | Pod UI_UI-Member2 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 28 | #VALUE! | 3
57 | LMU | React/ASP | Yes | 0 | 2026-05-21 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-21 | 3 | 0 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 3 | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod UI | Pod UI_UI-Member3 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1.5 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 28 | #VALUE! | 3
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod 2 | Pod 2_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 27 |  | 3
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod UI | Pod UI_UI-Member4 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 23 |  | 3
59 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_6 | Pod 2 | Pod 2_Member3 | 2026-05-13 | 3 | 0 | 6 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 3 | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 | #VALUE! | 3 |  |  | #VALUE!
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod UI | Pod UI_UI-Member5 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 23 |  | 3
58 | LMU | React/ASP | Yes | 0 | 2026-05-20 | page_5 | Pod UI | Pod UI_Integration | 2026-05-20 | 5 | 0 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 3
60 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-26 | 3 | 0 | 4 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 27 |  | 3
61 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 3
62 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-18 | 3 | 0 | 9 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 22 |  | 3
63 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_7 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 3 | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 3
64 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-21 | 3 | 0 | 11 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
65 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-21 | 3 | 0 | 12 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 3 | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
66 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_10 | Pod 2 | Pod 2_Member1 | 2026-06-05 | 3 | 0 | 10 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 3
67 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_14 | Pod 2 | Pod 2_Member2 | 2026-05-26 | 3 | 0 | 14 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 3 | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 | #VALUE! | 3 |  |  | #VALUE!
68 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_15 | Pod 2 | Pod 2_Member3 | 2026-05-26 | 3 | 0 | 15 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 27 |  | 3
69 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_13 | Pod 2 | Pod 2_Member1 | 2026-06-10 | 3 | 0 | 13 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 3 | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 3
70 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 17 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 21 |  | 3
71 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 18 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 3 | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 3
72 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_16 | Pod 2 | Pod 2_Member1 | 2026-06-15 | 3 | 0 | 16 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1.5 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 22 |  | 3
73 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-05 | 3 | 0 | 20 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 3 | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 3
74 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-05 | 3 | 0 | 21 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 3
75 | LMU | Complete ASP | Yes | 0 | 2026-06-18 | page_19 | Pod 2 | Pod 2_Member1 | 2026-06-18 | 3 | 0 | 19 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 3 | 2026-07-06 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 3 | 2026-07-17 | 0 | 2026-07-17 | 0 | 2026-07-17 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 45 |  | 3
76 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-10 | 3 | 0 | 23 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 27 |  | 3
77 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-10 | 3 | 0 | 24 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 3 | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 3
78 | LMU | Complete ASP | Yes | 0 | 2026-06-23 | page_22 | Pod 2 | Pod 2_Member1 | 2026-06-23 | 3 | 0 | 22 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 |  | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 28 | #VALUE! | 3 |  |  | #VALUE!
79 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_25 | Pod 2 | Pod 2_Member3 | 2026-06-15 | 3 | 0 | 25 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1.5 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 1 | 2026-07-01 | 2 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 5
80 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_26 | Pod 2 | Pod 2_Member2 | 2026-06-15 | 3 | 0 | 26 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1.5 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 3 | 2026-07-10 | 1 | 2026-07-13 | 2 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 5
81 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_1 | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 |  | 3
82 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 | #VALUE! | 3 |  |  | #VALUE!
83 | Location | Complete ASP | Yes | 0 | 2026-04-29 | page_3 | Pod 3 | Pod 3_Member2 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 1 | 2026-05-05 | 1.5 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 1 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 24 |  | 3
84 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-08 | 3 | 0 | 4 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 1 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
85 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_5 | Pod 3 | Pod 3_Member1 | 2026-05-08 | 3 | 0 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 1 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
86 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_6 | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 |  | 3
87 | Location | Complete ASP | Yes | 0 | 2026-05-13 | page_7 | Pod 3 | Pod 3_Member3 | 2026-05-13 | 3 | 0 | 7 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 27 |  | 3
88 | Location | Complete ASP | Yes | 0 | 2026-05-13 | page_8 | Pod 3 | Pod 3_Member1 | 2026-05-13 | 3 | 0 | 8 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 27 |  | 3
89 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_9 | Pod 3 | Pod 3_Member2 | 2026-05-08 | 3 | 0 | 9 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 1 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
90 | Location | Complete ASP | Yes | 0 | 2026-05-18 | page_10 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 10 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 22 |  | 3
91 | Location | Complete ASP | Yes | 0 | 2026-05-18 | page_11 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 11 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 3
92 | Log | Complete ASP | Yes | 0 | 2026-06-26 | page_1 | Pod 2 | Pod 2_Member1 | 2026-06-26 | 3 | 0 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 1.5 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 22 | #VALUE! | 3 |  |  | #VALUE!
93 | Log | Complete ASP | Yes | 0 | 2026-06-18 | page_2 | Pod 2 | Pod 2_Member2 | 2026-06-18 | 3 | 0 | 2 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 1.5 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 3
94 | Log | Complete ASP | Yes | 0 | 2026-06-18 | page_3 | Pod 2 | Pod 2_Member3 | 2026-06-18 | 3 | 0 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 1.5 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 3
95 | Log | Complete ASP | Yes | 0 | 2026-07-02 | page_4 | Pod 2 | Pod 2_Member1 | 2026-07-02 | 3 | 0 | 4 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 1 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 2 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 |  | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 31 |  | 3
96 | Log | Complete ASP | Yes | 0 | 2026-06-23 | page_5 | Pod 2 | Pod 2_Member2 | 2026-06-23 | 3 | 0 | 5 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 |  | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 28 |  | 3
97 | Log | Complete ASP | Yes | 0 | 2026-06-23 | page_6 | Pod 2 | Pod 2_Member3 | 2026-06-23 | 3 | 0 | 6 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-29 | 1.5 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 1 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 |  | 2026-07-09 | 0 | 2026-07-09 | 0 | 2026-07-09 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 28 |  | 3
98 | Log | Complete ASP | Yes | 0 | 2026-06-01 | page_7 | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 21 |  | 3
99 | Log | Complete ASP | Yes | 0 | 2026-05-21 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-21 | 3 | 0 | 8 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
100 | Log | Complete ASP | Yes | 0 | 2026-05-13 | page_9 | Pod 1 | Pod 1_Member3 | 2026-05-13 | 3 | 0 | 9 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 27 |  | 3
101 | Log | Complete ASP | Yes | 0 | 2026-05-21 | page_10 | Pod 3 | Pod 3_Member1 | 2026-05-21 | 3 | 0 | 10 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 3 | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 | #VALUE! | 3 |  |  | #VALUE!
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 21 |  | 3
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member1 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 17 |  | 3
103 | OrderAware | React/ASP | Yes | 0 | 2026-06-05 | page_6 | Pod 3 | Pod 3_Member3 | 2026-06-05 | 3 | 0 | 2 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 3
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member2 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 17 |  | 3
104 | OrderAware | React/ASP | Yes | 0 | 2026-06-10 | page_7 | Pod 3 | Pod 3_Member1 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 27 |  | 3
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member3 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 17 |  | 3
105 | OrderAware | React/ASP | Yes | 0 | 2026-06-05 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-05 | 3 | 0 | 4 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 3 | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 3
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member4 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 17 |  | 3
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-08 | page_5 | Pod UI | Pod UI_Integration | 2026-06-08 | 5 | 0 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 27 |  | 3
106 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-15 | page_1 | Pod 1 | Pod 1_Member2 | 2026-05-19 | 3 | 0 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 1 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 21 |  | 3
107 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-19 | page_2 | Pod 1 | Pod 1_Member3 | 2026-05-21 | 3 | 0 | 2 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
108 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-01 | page_3 | Pod 1 | Pod 1_Member1 | 2026-06-03 | 3 | 0 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 20 |  | 3
109 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-22 | page_4 | Pod 1 | Pod 1_Member2 | 2026-05-26 | 3 | 0 | 4 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 27 |  | 3
110 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-26 | page_5 | Pod 1 | Pod 1_Member3 | 2026-05-28 | 3 | 0 | 5 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 22 |  | 3
111 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-08 | page_6 | Pod 1 | Pod 1_Member1 | 2026-06-10 | 3 | 0 | 6 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 27 | #VALUE! | 3 |  |  | #VALUE!
112 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-01 | page_7 | Pod 1 | Pod 1_Member2 | 2026-06-03 | 3 | 0 | 7 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 3 | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 34 |  | 3
113 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-04 | page_1 | Pod 1 | Pod 1_Member3 | 2026-06-08 | 3 | 0 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 1 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 29 |  | 3
114 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-15 | page_2 | Pod 1 | Pod 1_Member1 | 2026-06-17 | 3 | 0 | 2 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 20 |  | 3
115 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-08 | page_3 | Pod 1 | Pod 1_Member2 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 27 |  | 3
116 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-11 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-15 | 3 | 0 | 4 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1.5 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 22 | #VALUE! | 3 |  |  | #VALUE!
117 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-22 | page_5 | Pod 1 | Pod 1_Member1 | 2026-06-24 | 3 | 0 | 5 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 1.5 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 3 | 2026-07-21 | 1 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 38 | #VALUE! | 5 |  |  | #VALUE!
118 | Reports | Complete ASP | No | 2 | 2026-06-15 | page_1 | Pod 1 | Pod 1_Member2 | 2026-06-17 | 3 | 0 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 1 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 3
119 | Reports | Complete ASP | No | 2 | 2026-06-18 | page_2 | Pod 1 | Pod 1_Member3 | 2026-06-22 | 3 | 0 | 2 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 1 | 2026-07-06 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 2 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 1 | 2026-07-15 | 2 | 2026-07-17 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 43 |  | 5
120 | Reports | Complete ASP | No | 2 | 2026-06-30 | page_3 | Pod 1 | Pod 1_Member1 | 2026-07-02 | 3 | 0 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 1 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 |  | 2026-07-21 | 0 | 2026-07-21 | 0 | 2026-07-21 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 31 |  | 3
121 | Reports | Complete ASP | No | 2 | 2026-06-25 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-29 | 3 | 0 | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 1 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 |  | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 22 | #VALUE! | 3 |  |  | #VALUE!
122 | Reports | Complete ASP | No | 2 | 2026-06-22 | page_5 | Pod 1 | Pod 1_Member2 | 2026-06-24 | 3 | 0 | 5 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1 | 2026-07-14 | 1 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 3 | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 38 |  | 3
123 | Webuser | Complete ASP | No | 2 | 2026-04-29 | page_1 | Pod 3 | Pod 3_Member2 | 2026-05-01 | 3 | 0 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 1.5 | 2026-05-08 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 22 |  | 3
124 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_2 | Pod 3 | Pod 3_Member3 | 2026-05-11 | 3 | 0 | 2 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 29 | #VALUE! | 3
125 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_3 | Pod 3 | Pod 3_Member1 | 2026-05-11 | 3 | 0 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 29 | #VALUE! | 3
126 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_4 | Pod 3 | Pod 3_Member2 | 2026-05-11 | 3 | 0 | 4 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 29 |  | 3
127 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_5 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 5 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 22 | #VALUE! | 3
128 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_1 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 6 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 22 | #VALUE! | 3
129 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_2 | Pod 3 | Pod 3_Member2 | 2026-05-18 | 3 |  | 7 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04
130 | Webuser | Complete ASP | No | 2 | 2026-05-21 | page_3 | Pod 3 | Pod 3_Member3 | 2026-05-25 | 3 |  | 8 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18
131 | Webuser | Complete ASP | No | 2 | 2026-05-21 | page_4 | Pod 3 | Pod 3_Member1 | 2026-05-25 | 3 |  | 9 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18
132 | Webuser | Complete ASP | No | 2 | 2026-05-21 | page_5 | Pod 3 | Pod 3_Member2 | 2026-05-25 | 3 |  | 10 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 3 | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02
133 | Gradebook | Complete ASP | No | 2 | 2026-05-28 | page_6 | Pod 3 | Pod 3_Member1 | 2026-06-01 | 3 |  | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25
134 | Gradebook | Complete ASP | No | 2 | 2026-06-05 | page_7 | Pod 3 | Pod 3_Member1 | 2026-06-09 | 3 |  | 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 |  | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
135 | Gradebook | Complete ASP | No | 2 | 2026-05-28 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 |  | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25
136 | Gradebook | React/ASP | No | 2 | 2026-06-05 | page_9 | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 |  | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 |  | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member1 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
137 | Gradebook | React/ASP | No | 2 | 2026-05-28 | page_10 | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 |  | 5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member2 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
138 | Gradebook | React/ASP | No | 2 | 2026-06-05 | page_11 | Pod 3 | Pod 3_Member3 | 2026-06-09 | 3 |  | 6 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 |  | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member3 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
139 | Gradebook | React/ASP | No | 2 | 2026-06-12 | page_12 | Pod 3 | Pod 3_Member1 | 2026-06-16 | 3 |  | 7 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 1.5 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 1 | 2026-06-25 | 1 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member4 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1.5 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
140 | Gradebook | React/ASP | No | 2 | 2026-06-12 | page_13 | Pod 3 | Pod 3_Member2 | 2026-06-16 | 3 |  | 8 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 1.5 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 1 | 2026-06-25 | 1 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_9 | Pod UI | Pod UI_UI-Member1 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 1.5 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
141 | Gradebook | React/ASP | No | 2 | 2026-06-12 | page_14 | Pod 3 | Pod 3_Member3 | 2026-06-16 | 3 |  | 9 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 1.5 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 1 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 3 | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_9 | Pod UI | Pod UI_UI-Member2 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 1.5 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 0 | 2026-06-23 | page_9 | Pod UI | Pod UI_Integration | 2026-06-23 | 5 |  | 4 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 1.5 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 |  | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
Formulas:
Start Date = [Module Target Start (Input)]
Start Date = WORKDAY([Module Target Start (Input)],[Buffer In case of no KT])
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Code Freeze Date = [TCR Bugs Closure Date]
TEST Deployment = [Code Freeze Date]
Pearson Regression Testing/UAT Date = WORKDAY([TEST Deployment], 1, IndHolidays)
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&(MAX([PR Response receive Date],[TCR Bugs Closure Date])))
Code freeze date = Release cutoff Date = WORKDAY([Release Date (2-Wk Cycle)], -5)
Release Request Approved Date = WORKDAY([Release #], 2, IndHolidays)
Release Date (2-Wk Cycle) = VLOOKUP([Release #],ReleaseTimeline!$B2:C27,2,FALSE)
Module Target Start (Input) = WORKDAY([PR raised date, row above],1)

## New PR process
No. | Module | Target page Technology | Recieved Functional & Non Fuctional Walkthrough | Buffer In case of no KT | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Code Freeze Date | TEST Deployment | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | Code freeze date = Release cutoff Date | Release # | Release Request Approved Date | Release Date (2-Wk Cycle) | Code freeze date = Release cutoff Date | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
1 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 5 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 1 | 2026-05-05 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | #VALUE! | 41 |  | 13
2 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_2 | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 5 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 1 | 2026-05-05 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 13
3 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 5 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 1 | 2026-05-05 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 13
4 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | page_4 | Pod 1 | Pod 1_Member1 | 2026-04-20 | 3 | 0 | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 5 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 1 | 2026-05-08 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 |  | 2026-05-19 |  | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 13
5 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | page_5 | Pod 1 | Pod 1_Member2 | 2026-04-20 | 3 | 0 | 5 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 5 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1 | 2026-05-13 | 5 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 3 | 2026-05-29 | 1 | 2026-06-01 | 5 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 64 | #VALUE! | 18 |  |  | #VALUE!
6 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_1 | Pod 2 | Pod 2_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 5 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 1 | 2026-05-05 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 13
7 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_2 | Pod 2 | Pod 2_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 5 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 1 | 2026-05-05 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 13
8 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_3 | Pod 2 | Pod 2_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 5 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 1 | 2026-05-05 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 |  | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 13
9 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_4 | Pod 2 | Pod 2_Member1 | 2026-04-20 | 3 | 0 | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 5 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 1 | 2026-05-08 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 |  | 2026-05-19 |  | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 13
10 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_5 | Pod 2 | Pod 2_Member2 | 2026-04-20 | 3 | 0 | 5 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 5 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 1 | 2026-05-08 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 |  | 2026-05-19 |  | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 13
11 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_6 | Pod 2 | Pod 2_Member3 | 2026-04-20 | 3 | 0 | 6 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 5 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 1 | 2026-05-08 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 |  | 2026-05-19 |  | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 13
12 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_7 | Pod 2 | Pod 2_Member1 | 2026-04-24 | 3 | 0 | 7 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 5 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 13
13 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_8 | Pod 2 | Pod 2_Member2 | 2026-04-24 | 3 | 0 | 8 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 5 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 | #VALUE! | 13 |  |  | #VALUE!
14 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_9 | Pod 2 | Pod 2_Member3 | 2026-04-24 | 3 | 0 | 9 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 5 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 13
15 | Assessments | Complete ASP | Yes | 0 | 2026-04-29 | page_10 | Pod 2 | Pod 2_Member1 | 2026-04-29 | 3 | 0 | 10 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 5 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1 | 2026-05-22 | 5 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 5 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 52 |  | 18
16 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-28 | 3 | 0 | 1 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 5 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 1 | 2026-05-18 | 5 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 42 |  | 13
17 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | page_2 | Pod 1 | Pod 1_Member2 | 2026-04-28 | 3 | 0 | 2 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 5 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 1 | 2026-05-18 | 5 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 42 |  | 13
18 | AssetAware | Complete ASP | No | 2 | 2026-04-20 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-22 | 3 | 0 | 3 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 5 | 2026-05-04 | 1 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 1 | 2026-05-12 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 |  | 2026-05-21 |  | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 34 |  | 13
19 | AssetAware | Complete ASP | No | 2 | 2026-05-01 | page_4 | Pod 1 | Pod 1_Member1 | 2026-05-05 | 3 | 0 | 4 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 5 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 1 | 2026-05-27 | 5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 3 | 2026-06-15 | 1 | 2026-06-16 | 5 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 63 |  | 18
20 | Communication | Complete ASP | No | 2 | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-07 | 3 | 0 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 5 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 1 | 2026-05-26 | 5 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 |  | 2026-06-08 |  | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 45 |  | 13
21 | Communication | Complete ASP | No | 2 | 2026-04-29 | page_2 | Pod 2 | Pod 2_Member2 | 2026-05-01 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 5 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 5 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 |  | 2026-06-03 |  | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 13
22 | Communication | Complete ASP | No | 2 | 2026-04-29 | page_3 | Pod 2 | Pod 2_Member3 | 2026-05-01 | 3 | 0 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 5 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 5 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 |  | 2026-06-03 |  | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 13
23 | Communication | Complete ASP | No | 2 | 2026-05-12 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 5 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 1 | 2026-06-09 | 5 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 3 | 2026-06-24 | 1 | 2026-06-25 | 5 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 66 | #VALUE! | 18 |  |  | #VALUE!
24 | Content | Complete ASP | No | 2 | 2026-04-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 | 0 | 1 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 5 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 |  | 2026-05-06 | 1 | 2026-05-07 | 5 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 37 |  | 13
25 | Content | Complete ASP | No | 2 | 2026-04-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-17 | 3 | 0 | 2 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 5 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 |  | 2026-05-06 | 1 | 2026-05-07 | 5 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 37 |  | 13
26 | Content | Complete ASP | No | 2 | 2026-04-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-17 | 3 | 0 | 3 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 5 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 |  | 2026-05-06 | 1 | 2026-05-07 | 5 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 37 |  | 13
27 | Content | Complete ASP | No | 2 | 2026-04-22 | page_4 | Pod 3 | Pod 3_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 5 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 1 | 2026-05-19 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 3 | 2026-06-05 | 1 | 2026-06-08 | 5 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 58 |  | 18
28 | Enrollment | Complete ASP | No | 2 | 2026-04-27 | page_1 | Pod 1 | Pod 1_Member3 | 2026-04-29 | 3 | 0 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 5 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 |  | 2026-05-29 |  | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 13
29 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member1 | 2026-05-12 | 3 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 5 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 1 | 2026-06-01 | 5 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 |  | 2026-06-11 |  | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 13
30 | Enrollment | Complete ASP | No | 2 | 2026-05-01 | page_3 | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 5 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 5 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 |  | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 13
31 | Enrollment | Complete ASP | No | 2 | 2026-05-05 | page_4 | Pod 1 | Pod 1_Member3 | 2026-05-07 | 3 | 0 | 4 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 5 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 1 | 2026-05-26 | 5 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 |  | 2026-06-08 |  | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 45 |  | 13
32 | Enrollment | Complete ASP | No | 2 | 2026-05-15 | page_5 | Pod 1 | Pod 1_Member1 | 2026-05-19 | 3 | 0 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 5 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 1 | 2026-06-09 | 5 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 |  | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 35 |  | 13
33 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | page_6 | Pod 1 | Pod 1_Member2 | 2026-05-12 | 3 | 0 | 6 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 5 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 1 | 2026-06-01 | 5 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 |  | 2026-06-11 |  | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 13
34 | Enrollment | Complete ASP | No | 2 | 2026-05-12 | page_7 | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 7 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 5 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 1 | 2026-06-04 | 5 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 |  | 2026-06-15 |  | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 13
35 | Enrollment | Complete ASP | No | 2 | 2026-05-22 | page_8 | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 0 | 8 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 5 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 1 | 2026-06-19 | 5 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 5 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 55 |  | 18
36 | ExtendedField | Complete ASP | Yes | 0 | 2026-06-01 | page_1 | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 95 | 2026-10-27 | 1 | 2026-10-28 | 2026-10-28 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-03 | 2026-11-03 |  | 2026-11-03 | 1 | 2026-11-04 | 5 | 2026-11-12 | 2026-11-12 | 2026-11-13 | 2026-11-13 |  | 2026-11-13 | 2026-11-13 | 2026-11-13 | 2026-11-16 |  | 2026-11-16 |  | 2026-11-16 |  | 2026-11-16 | 2026-11-19 | Release 24 | #VALUE! | 2026-11-26 | 2026-11-19 | 175 |  | 103
37 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 5 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 |  | 2026-06-09 |  | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 |  | 13
38 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-05 | page_3 | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 5 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 5 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 |  | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 13
39 | ExtendedField | Complete ASP | Yes | 0 | 2026-06-05 | page_4 | Pod 1 | Pod 1_Member1 | 2026-06-05 | 3 | 0 | 4 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 95 | 2026-10-30 | 1 | 2026-11-02 | 2026-11-02 | 3 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-06 | 2026-11-06 |  | 2026-11-06 | 1 | 2026-11-09 | 5 | 2026-11-17 | 2026-11-17 | 2026-11-18 | 2026-11-18 |  | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-19 |  | 2026-11-19 |  | 2026-11-19 |  | 2026-11-19 | 2026-11-19 | Release 24 | #VALUE! | 2026-11-26 | 2026-11-19 | 170 |  | 103
40 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-13 | page_5 | Pod 1 | Pod 1_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 5 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 1 | 2026-06-03 | 5 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 13
41 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | page_6 | Pod 1 | Pod 1_Member3 | 2026-05-08 | 3 | 0 | 6 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 5 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 |  | 2026-06-09 |  | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 |  | 13
42 | ExtendedField | Complete ASP | Yes | 0 | 2026-06-10 | page_7 | Pod 1 | Pod 1_Member1 | 2026-06-10 | 3 | 0 | 7 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 95 | 2026-11-04 | 1 | 2026-11-05 | 2026-11-05 | 3 | 2026-11-11 | 2026-11-11 | 2026-11-11 | 2026-11-12 | 2026-11-12 |  | 2026-11-12 | 1 | 2026-11-13 | 5 | 2026-11-20 | 2026-11-20 | 2026-11-23 | 2026-11-23 |  | 2026-11-23 | 2026-11-23 | 2026-11-23 | 2026-11-24 |  | 2026-11-24 |  | 2026-11-24 |  | 2026-11-24 | 2026-12-03 | Release 25 | #VALUE! | 2026-12-10 | 2026-12-03 | 181 |  | 103
43 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 5 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 5 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 3 | 2026-06-29 | 1 | 2026-06-30 | 5 | 2026-07-08 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 64 |  | 18
44 | GradeBook | Complete ASP | Yes | 0 | 2026-05-13 | page_3 | Pod 2 | Pod 2_Member1 | 2026-05-13 | 3 | 0 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 5 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 1 | 2026-06-08 | 5 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 1 | 2026-06-24 | 5 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 55 |  | 18
45 | GradeBook | Complete ASP | Yes | 0 | 2026-05-05 | page_4 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 5 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 1 | 2026-05-27 | 5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 3 | 2026-06-15 | 1 | 2026-06-16 | 5 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 63 |  | 18
46 | Home | Complete ASP | No | 2 | 2026-04-22 | page_1 | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 5 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 13
47 | Home | Complete ASP | No | 2 | 2026-04-29 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-01 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 5 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 5 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 |  | 2026-06-03 |  | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 13
48 | Home | Complete ASP | No | 2 | 2026-04-22 | page_3 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 5 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 13
49 | Home | Complete ASP | No | 2 | 2026-04-29 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-01 | 3 | 0 | 4 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 5 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 1 | 2026-05-26 | 5 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 1 | 2026-06-15 | 5 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 64 | #VALUE! | 18 |  |  | #VALUE!
50 | IssueAware | Complete ASP | Yes | 0 | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 35 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 1 | 2026-07-09 | 5 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 |  | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 |  | 2026-07-20 |  | 2026-07-20 |  | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 91 |  | 43
51 | IssueAware | Complete ASP | Yes | 0 | 2026-05-18 | page_2 | Pod 2 | Pod 2_Member1 | 2026-05-18 | 3 | 0 | 2 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 35 | 2026-07-14 | 1 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 3 | 2026-07-24 | 1 | 2026-07-27 | 5 | 2026-08-03 | 2026-08-03 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 3 | 2026-08-11 | 1 | 2026-08-12 | 5 | 2026-08-19 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 106 |  | 48
52 | Library | Complete ASP | Yes | 0 | 2026-04-29 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-29 | 3 | 0 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 35 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 1 | 2026-07-03 | 5 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 |  | 2026-07-15 |  | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 80 |  | 43
53 | Library | Complete ASP | Yes | 0 | 2026-04-24 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 5 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 13
54 | Library | Complete ASP | Yes | 0 | 2026-04-29 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 35 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 5 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 3 | 2026-07-24 | 1 | 2026-07-27 | 5 | 2026-08-03 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 108 |  | 48
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_2 | Pod 2 | Pod 2_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 35 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 3 | 2026-07-16 | 1 | 2026-07-17 | 5 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 3 | 2026-08-03 | 1 | 2026-08-04 | 5 | 2026-08-11 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 100 |  | 48
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_2 | Pod UI | Pod UI_UI-Member1 | 2026-05-08 | 5 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 35 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 1 | 2026-07-21 | 5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 3 | 2026-08-05 | 1 | 2026-08-06 | 5 | 2026-08-13 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 98 |  | 48
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod 2 | Pod 2_Member3 | 2026-05-08 | 3 | 0 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 35 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 1 | 2026-07-14 | 5 | 2026-07-21 | 2026-07-21 | 2026-07-22 | 2026-07-22 |  | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 |  | 2026-07-23 |  | 2026-07-23 |  | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 86 | #VALUE! | 43
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod UI | Pod UI_UI-Member2 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 35 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 1 | 2026-07-16 | 5 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 |  | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 |  | 2026-07-27 |  | 2026-07-27 |  | 2026-07-27 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 84 | #VALUE! | 43
57 | LMU | React/ASP | Yes | 0 | 2026-05-21 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-21 | 3 | 0 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 35 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 1 | 2026-07-30 | 5 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 1 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-11 | 3 | 2026-08-14 | 1 | 2026-08-17 | 5 | 2026-08-25 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 101 |  | 48
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod UI | Pod UI_UI-Member3 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 35 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 1 | 2026-07-16 | 5 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 |  | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 |  | 2026-07-27 |  | 2026-07-27 |  | 2026-07-27 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 84 | #VALUE! | 43
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod 2 | Pod 2_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 35 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 |  | 2026-07-16 | 1 | 2026-07-17 | 5 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 |  | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 |  | 2026-07-28 |  | 2026-07-28 |  | 2026-07-28 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 83 |  | 43
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod UI | Pod UI_UI-Member4 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 35 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 1 | 2026-07-21 | 5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 |  | 2026-07-30 |  | 2026-07-30 |  | 2026-07-30 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 79 |  | 43
59 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_6 | Pod 2 | Pod 2_Member3 | 2026-05-13 | 3 | 0 | 6 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 35 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 | 3 | 2026-07-21 | 1 | 2026-07-22 | 5 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 3 | 2026-08-06 | 1 | 2026-08-07 | 5 | 2026-08-14 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 111 | #VALUE! | 48 |  |  | #VALUE!
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod UI | Pod UI_UI-Member5 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 35 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 1 | 2026-07-21 | 5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 |  | 2026-07-30 |  | 2026-07-30 |  | 2026-07-30 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 79 |  | 43
58 | LMU | React/ASP | Yes | 0 | 2026-05-20 | page_5 | Pod UI | Pod UI_Integration | 2026-05-20 | 5 | 0 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 35 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 |  | 2026-07-27 | 1 | 2026-07-28 | 5 | 2026-08-04 | 2026-08-04 | 2026-08-05 | 2026-08-05 |  | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 |  | 2026-08-06 |  | 2026-08-06 |  | 2026-08-06 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 86 |  | 43
60 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-26 | 3 | 0 | 4 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 35 | 2026-07-22 | 1 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 1 | 2026-07-30 | 5 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 |  | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 |  | 2026-08-10 |  | 2026-08-10 |  | 2026-08-10 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 83 |  | 43
61 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 35 | 2026-07-14 | 1 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 3 | 2026-07-24 | 1 | 2026-07-27 | 5 | 2026-08-03 | 2026-08-03 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 3 | 2026-08-11 | 1 | 2026-08-12 | 5 | 2026-08-19 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 106 |  | 48
62 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-18 | 3 | 0 | 9 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 35 | 2026-07-14 | 1 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 1 | 2026-07-22 | 5 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 |  | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-31 |  | 2026-07-31 |  | 2026-07-31 |  | 2026-07-31 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 92 |  | 43
63 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_7 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 95 | 2026-10-27 | 1 | 2026-10-28 | 2026-10-28 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-03 | 2026-11-03 | 3 | 2026-11-06 | 1 | 2026-11-09 | 5 | 2026-11-17 | 2026-11-17 | 2026-11-18 | 2026-11-18 | 1 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 2026-11-20 | 3 | 2026-11-25 | 1 | 2026-11-26 | 5 | 2026-12-03 | 2026-12-03 | Release 25 | #VALUE! | 2026-12-10 | 2026-12-03 | 189 |  | 108
64 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-21 | 3 | 0 | 11 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 35 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 |  | 2026-07-24 | 1 | 2026-07-27 | 5 | 2026-08-03 | 2026-08-03 | 2026-08-04 | 2026-08-04 |  | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-05 |  | 2026-08-05 |  | 2026-08-05 |  | 2026-08-05 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 87 |  | 43
65 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-21 | 3 | 0 | 12 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 35 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 1 | 2026-07-30 | 5 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 1 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-11 | 3 | 2026-08-14 | 1 | 2026-08-17 | 5 | 2026-08-25 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 101 |  | 48
66 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_10 | Pod 2 | Pod 2_Member1 | 2026-06-05 | 3 | 0 | 10 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 95 | 2026-10-30 | 1 | 2026-11-02 | 2026-11-02 | 3 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-06 | 2026-11-06 |  | 2026-11-06 | 1 | 2026-11-09 | 5 | 2026-11-17 | 2026-11-17 | 2026-11-18 | 2026-11-18 |  | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-19 |  | 2026-11-19 |  | 2026-11-19 |  | 2026-11-19 | 2026-11-19 | Release 24 | #VALUE! | 2026-11-26 | 2026-11-19 | 170 |  | 103
67 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_14 | Pod 2 | Pod 2_Member2 | 2026-05-26 | 3 | 0 | 14 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 35 | 2026-07-22 | 1 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 3 | 2026-08-03 | 1 | 2026-08-04 | 5 | 2026-08-11 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 3 | 2026-08-19 | 1 | 2026-08-20 | 5 | 2026-08-31 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 111 | #VALUE! | 48 |  |  | #VALUE!
68 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_15 | Pod 2 | Pod 2_Member3 | 2026-05-26 | 3 | 0 | 15 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 35 | 2026-07-22 | 1 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 1 | 2026-07-30 | 5 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 |  | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 |  | 2026-08-10 |  | 2026-08-10 |  | 2026-08-10 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 83 |  | 43
69 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_13 | Pod 2 | Pod 2_Member1 | 2026-06-10 | 3 | 0 | 13 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 95 | 2026-11-04 | 1 | 2026-11-05 | 2026-11-05 | 3 | 2026-11-11 | 2026-11-11 | 2026-11-11 | 2026-11-12 | 2026-11-12 | 3 | 2026-11-17 | 1 | 2026-11-18 | 5 | 2026-11-25 | 2026-11-25 | 2026-11-26 | 2026-11-26 | 1 | 2026-11-27 | 2026-11-27 | 2026-11-27 | 2026-11-30 | 3 | 2026-12-03 | 1 | 2026-12-04 | 5 | 2026-12-11 | 2026-12-17 | Release 26 | #VALUE! | 2026-12-24 | 2026-12-17 | 195 |  | 108
70 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 17 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 95 | 2026-10-27 | 1 | 2026-10-28 | 2026-10-28 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-03 | 2026-11-03 |  | 2026-11-03 | 1 | 2026-11-04 | 5 | 2026-11-12 | 2026-11-12 | 2026-11-13 | 2026-11-13 |  | 2026-11-13 | 2026-11-13 | 2026-11-13 | 2026-11-16 |  | 2026-11-16 |  | 2026-11-16 |  | 2026-11-16 | 2026-11-19 | Release 24 | #VALUE! | 2026-11-26 | 2026-11-19 | 175 |  | 103
71 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 18 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 95 | 2026-10-27 | 1 | 2026-10-28 | 2026-10-28 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-03 | 2026-11-03 | 3 | 2026-11-06 | 1 | 2026-11-09 | 5 | 2026-11-17 | 2026-11-17 | 2026-11-18 | 2026-11-18 | 1 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 2026-11-20 | 3 | 2026-11-25 | 1 | 2026-11-26 | 5 | 2026-12-03 | 2026-12-03 | Release 25 | #VALUE! | 2026-12-10 | 2026-12-03 | 189 |  | 108
72 | LMU | Complete ASP | Yes | 0 | 2026-05-15 | page_16 | Pod 4 | Pod 4_Member3 | 2026-05-15 | 3 | 0 | 16 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 35 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 1 | 2026-07-21 | 5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 |  | 2026-07-30 |  | 2026-07-30 |  | 2026-07-30 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 79 |  | 43
73 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-05 | 3 | 0 | 20 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 95 | 2026-10-30 | 1 | 2026-11-02 | 2026-11-02 | 3 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-06 | 2026-11-06 | 3 | 2026-11-12 | 1 | 2026-11-13 | 5 | 2026-11-20 | 2026-11-20 | 2026-11-23 | 2026-11-23 | 1 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-25 | 3 | 2026-11-30 | 1 | 2026-12-01 | 5 | 2026-12-08 | 2026-12-17 | Release 26 | #VALUE! | 2026-12-24 | 2026-12-17 | 198 |  | 108
74 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-05 | 3 | 0 | 21 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 95 | 2026-10-30 | 1 | 2026-11-02 | 2026-11-02 | 3 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-06 | 2026-11-06 |  | 2026-11-06 | 1 | 2026-11-09 | 5 | 2026-11-17 | 2026-11-17 | 2026-11-18 | 2026-11-18 |  | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-19 |  | 2026-11-19 |  | 2026-11-19 |  | 2026-11-19 | 2026-11-19 | Release 24 | #VALUE! | 2026-11-26 | 2026-11-19 | 170 |  | 103
75 | LMU | Complete ASP | Yes | 0 | 2026-05-20 | page_19 | Pod 4 | Pod 4_Member3 | 2026-05-20 | 3 | 0 | 19 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 35 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 1 | 2026-07-29 | 5 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 3 | 2026-08-13 | 1 | 2026-08-14 | 5 | 2026-08-24 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 104 |  | 48
76 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-10 | 3 | 0 | 23 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 95 | 2026-11-04 | 1 | 2026-11-05 | 2026-11-05 | 3 | 2026-11-11 | 2026-11-11 | 2026-11-11 | 2026-11-12 | 2026-11-12 |  | 2026-11-12 | 1 | 2026-11-13 | 5 | 2026-11-20 | 2026-11-20 | 2026-11-23 | 2026-11-23 |  | 2026-11-23 | 2026-11-23 | 2026-11-23 | 2026-11-24 |  | 2026-11-24 |  | 2026-11-24 |  | 2026-11-24 | 2026-12-03 | Release 25 | #VALUE! | 2026-12-10 | 2026-12-03 | 181 |  | 103
77 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-10 | 3 | 0 | 24 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 95 | 2026-11-04 | 1 | 2026-11-05 | 2026-11-05 | 3 | 2026-11-11 | 2026-11-11 | 2026-11-11 | 2026-11-12 | 2026-11-12 | 3 | 2026-11-17 | 1 | 2026-11-18 | 5 | 2026-11-25 | 2026-11-25 | 2026-11-26 | 2026-11-26 | 1 | 2026-11-27 | 2026-11-27 | 2026-11-27 | 2026-11-30 | 3 | 2026-12-03 | 1 | 2026-12-04 | 5 | 2026-12-11 | 2026-12-17 | Release 26 | #VALUE! | 2026-12-24 | 2026-12-17 | 195 |  | 108
78 | LMU | Complete ASP | Yes | 0 | 2026-05-25 | page_22 | Pod 4 | Pod 4_Member3 | 2026-05-25 | 3 | 0 | 22 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 65 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 3 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-10 | 2026-09-10 |  | 2026-09-10 | 1 | 2026-09-11 | 5 | 2026-09-21 | 2026-09-21 | 2026-09-22 | 2026-09-22 |  | 2026-09-22 | 2026-09-22 | 2026-09-22 | 2026-09-23 |  | 2026-09-23 |  | 2026-09-23 |  | 2026-09-23 | 2026-09-24 | Release 20 | #VALUE! | 2026-10-01 | 2026-09-24 | 127 | #VALUE! | 73 |  |  | #VALUE!
79 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_25 | Pod 2 | Pod 2_Member3 | 2026-06-15 | 3 | 0 | 25 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 95 | 2026-11-09 | 1 | 2026-11-11 | 2026-11-11 | 3 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-17 | 2026-11-17 |  | 2026-11-17 | 1 | 2026-11-18 | 5 | 2026-11-25 | 2026-11-25 | 2026-11-26 | 2026-11-26 |  | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-11-27 |  | 2026-11-27 |  | 2026-11-27 |  | 2026-11-27 | 2026-12-03 | Release 25 | #VALUE! | 2026-12-10 | 2026-12-03 | 176 |  | 103
80 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_26 | Pod 2 | Pod 2_Member2 | 2026-06-15 | 3 | 0 | 26 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 95 | 2026-11-09 | 1 | 2026-11-11 | 2026-11-11 | 3 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-17 | 2026-11-17 | 3 | 2026-11-20 | 1 | 2026-11-23 | 5 | 2026-11-30 | 2026-11-30 | 2026-12-01 | 2026-12-01 | 1 | 2026-12-02 | 2026-12-02 | 2026-12-02 | 2026-12-03 | 3 | 2026-12-08 | 1 | 2026-12-09 | 5 | 2026-12-16 | 2026-12-17 | Release 26 | #VALUE! | 2026-12-24 | 2026-12-17 | 190 |  | 108
81 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_1 | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 65 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-19 |  | 2026-08-19 | 1 | 2026-08-20 | 5 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 |  | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-02 |  | 2026-09-02 |  | 2026-09-02 |  | 2026-09-02 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 133 |  | 73
82 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 65 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-19 |  | 2026-08-19 | 1 | 2026-08-20 | 5 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 |  | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-02 |  | 2026-09-02 |  | 2026-09-02 |  | 2026-09-02 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 133 | #VALUE! | 73 |  |  | #VALUE!
83 | Location | Complete ASP | Yes | 0 | 2026-04-29 | page_3 | Pod 3 | Pod 3_Member2 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 65 | 2026-08-07 | 1 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 1 | 2026-08-17 | 5 | 2026-08-25 | 2026-08-25 | 2026-08-27 | 2026-08-27 |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-28 |  | 2026-08-28 |  | 2026-08-28 |  | 2026-08-28 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 136 |  | 73
84 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-08 | 3 | 0 | 4 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 65 | 2026-08-17 | 1 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 1 | 2026-08-27 | 5 | 2026-09-03 | 2026-09-03 | 2026-09-04 | 2026-09-04 |  | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-09-07 |  | 2026-09-07 |  | 2026-09-07 |  | 2026-09-07 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 128 |  | 73
85 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_5 | Pod 3 | Pod 3_Member1 | 2026-05-08 | 3 | 0 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 65 | 2026-08-17 | 1 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 1 | 2026-08-27 | 5 | 2026-09-03 | 2026-09-03 | 2026-09-04 | 2026-09-04 |  | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-09-07 |  | 2026-09-07 |  | 2026-09-07 |  | 2026-09-07 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 128 |  | 73
86 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_6 | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 65 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-19 |  | 2026-08-19 | 1 | 2026-08-20 | 5 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 |  | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-02 |  | 2026-09-02 |  | 2026-09-02 |  | 2026-09-02 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 133 |  | 73
87 | Location | Complete ASP | Yes | 0 | 2026-05-13 | page_7 | Pod 3 | Pod 3_Member3 | 2026-05-13 | 3 | 0 | 7 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 65 | 2026-08-20 | 1 | 2026-08-24 | 2026-08-24 | 3 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-31 | 2026-08-31 |  | 2026-08-31 | 1 | 2026-09-01 | 5 | 2026-09-08 | 2026-09-08 | 2026-09-09 | 2026-09-09 |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-10 |  | 2026-09-10 |  | 2026-09-10 |  | 2026-09-10 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 125 |  | 73
88 | Location | Complete ASP | Yes | 0 | 2026-05-13 | page_8 | Pod 3 | Pod 3_Member1 | 2026-05-13 | 3 | 0 | 8 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 65 | 2026-08-20 | 1 | 2026-08-24 | 2026-08-24 | 3 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-31 | 2026-08-31 |  | 2026-08-31 | 1 | 2026-09-01 | 5 | 2026-09-08 | 2026-09-08 | 2026-09-09 | 2026-09-09 |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-10 |  | 2026-09-10 |  | 2026-09-10 |  | 2026-09-10 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 125 |  | 73
89 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_9 | Pod 3 | Pod 3_Member2 | 2026-05-08 | 3 | 0 | 9 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 65 | 2026-08-17 | 1 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 1 | 2026-08-27 | 5 | 2026-09-03 | 2026-09-03 | 2026-09-04 | 2026-09-04 |  | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-09-07 |  | 2026-09-07 |  | 2026-09-07 |  | 2026-09-07 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 128 |  | 73
90 | Location | Complete ASP | Yes | 0 | 2026-05-18 | page_10 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 10 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 65 | 2026-08-27 | 1 | 2026-08-28 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 |  | 2026-09-03 | 1 | 2026-09-04 | 5 | 2026-09-11 | 2026-09-11 | 2026-09-15 | 2026-09-15 |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-16 |  | 2026-09-16 |  | 2026-09-16 |  | 2026-09-16 | 2026-09-24 | Release 20 | #VALUE! | 2026-10-01 | 2026-09-24 | 134 |  | 73
91 | Location | Complete ASP | Yes | 0 | 2026-05-18 | page_11 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 11 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 65 | 2026-08-27 | 1 | 2026-08-28 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 3 | 2026-09-08 | 1 | 2026-09-09 | 5 | 2026-09-17 | 2026-09-17 | 2026-09-18 | 2026-09-18 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-22 | 3 | 2026-09-25 | 1 | 2026-09-28 | 5 | 2026-10-06 | 2026-10-08 | Release 21 | #VALUE! | 2026-10-15 | 2026-10-08 | 148 |  | 78
92 | Log | Complete ASP | Yes | 0 | 2026-05-28 | page_1 | Pod 4 | Pod 4_Member3 | 2026-05-28 | 3 | 0 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 95 | 2026-10-26 | 1 | 2026-10-27 | 2026-10-27 | 3 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-11-02 | 2026-11-02 |  | 2026-11-02 | 1 | 2026-11-03 | 5 | 2026-11-11 | 2026-11-11 | 2026-11-12 | 2026-11-12 |  | 2026-11-12 | 2026-11-12 | 2026-11-12 | 2026-11-13 |  | 2026-11-13 |  | 2026-11-13 |  | 2026-11-13 | 2026-11-19 | Release 24 | #VALUE! | 2026-11-26 | 2026-11-19 | 176 | #VALUE! | 103 |  |  | #VALUE!
93 | Log | Complete ASP | Yes | 0 | 2026-05-15 | page_2 | Pod 4 | Pod 4_Member2 | 2026-05-15 | 3 | 0 | 2 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 65 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 |  | 2026-09-02 | 1 | 2026-09-03 | 5 | 2026-09-10 | 2026-09-10 | 2026-09-11 | 2026-09-11 |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-15 |  | 2026-09-15 |  | 2026-09-15 |  | 2026-09-15 | 2026-09-24 | Release 20 | #VALUE! | 2026-10-01 | 2026-09-24 | 135 |  | 73
94 | Log | Complete ASP | Yes | 0 | 2026-06-18 | page_3 | Pod 2 | Pod 2_Member3 | 2026-06-18 | 3 | 0 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 95 | 2026-11-13 | 1 | 2026-11-16 | 2026-11-16 | 3 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 2026-11-20 | 2026-11-20 |  | 2026-11-20 | 1 | 2026-11-23 | 5 | 2026-11-30 | 2026-11-30 | 2026-12-01 | 2026-12-01 |  | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-02 |  | 2026-12-02 |  | 2026-12-02 |  | 2026-12-02 | 2026-12-03 | Release 25 | #VALUE! | 2026-12-10 | 2026-12-03 | 171 |  | 103
95 | Log | Complete ASP | Yes | 0 | 2026-06-04 | page_4 | Pod 4 | Pod 4_Member3 | 2026-06-04 | 3 | 0 | 4 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 95 | 2026-10-29 | 1 | 2026-10-30 | 2026-10-30 | 3 | 2026-11-04 | 2026-11-04 | 2026-11-04 | 2026-11-05 | 2026-11-05 |  | 2026-11-05 | 1 | 2026-11-06 | 5 | 2026-11-16 | 2026-11-16 | 2026-11-17 | 2026-11-17 | 2 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 2026-11-20 |  | 2026-11-20 | 2 | 2026-11-24 |  | 2026-11-24 | 2026-12-03 | Release 25 | #VALUE! | 2026-12-10 | 2026-12-03 | 185 |  | 103
96 | Log | Complete ASP | Yes | 0 | 2026-05-20 | page_5 | Pod 4 | Pod 4_Member2 | 2026-05-20 | 3 | 0 | 5 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 65 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 3 | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-09-07 | 2026-09-07 |  | 2026-09-07 | 1 | 2026-09-08 | 5 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-17 |  | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-18 |  | 2026-09-18 |  | 2026-09-18 |  | 2026-09-18 | 2026-09-24 | Release 20 | #VALUE! | 2026-10-01 | 2026-09-24 | 132 |  | 73
97 | Log | Complete ASP | Yes | 0 | 2026-06-23 | page_6 | Pod 2 | Pod 2_Member3 | 2026-06-23 | 3 | 0 | 6 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 95 | 2026-11-18 | 1 | 2026-11-19 | 2026-11-19 | 3 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-25 | 2026-11-25 |  | 2026-11-25 | 1 | 2026-11-26 | 5 | 2026-12-03 | 2026-12-03 | 2026-12-04 | 2026-12-04 |  | 2026-12-04 | 2026-12-04 | 2026-12-04 | 2026-12-07 |  | 2026-12-07 |  | 2026-12-07 |  | 2026-12-07 | 2026-12-17 | Release 26 | #VALUE! | 2026-12-24 | 2026-12-17 | 182 |  | 103
98 | Log | Complete ASP | Yes | 0 | 2026-05-15 | page_7 | Pod 4 | Pod 4_Member1 | 2026-05-15 | 3 | 0 | 7 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 65 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 |  | 2026-09-02 | 1 | 2026-09-03 | 5 | 2026-09-10 | 2026-09-10 | 2026-09-11 | 2026-09-11 |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-15 |  | 2026-09-15 |  | 2026-09-15 |  | 2026-09-15 | 2026-09-24 | Release 20 | #VALUE! | 2026-10-01 | 2026-09-24 | 135 |  | 73
99 | Log | Complete ASP | Yes | 0 | 2026-05-21 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-21 | 3 | 0 | 8 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 65 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-08 |  | 2026-09-08 | 1 | 2026-09-09 | 5 | 2026-09-17 | 2026-09-17 | 2026-09-18 | 2026-09-18 |  | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-21 |  | 2026-09-21 |  | 2026-09-21 |  | 2026-09-21 | 2026-09-24 | Release 20 | #VALUE! | 2026-10-01 | 2026-09-24 | 129 |  | 73
100 | Log | Complete ASP | Yes | 0 | 2026-05-13 | page_9 | Pod 1 | Pod 1_Member3 | 2026-05-13 | 3 | 0 | 9 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 65 | 2026-08-20 | 1 | 2026-08-24 | 2026-08-24 | 3 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-31 | 2026-08-31 |  | 2026-08-31 | 1 | 2026-09-01 | 5 | 2026-09-08 | 2026-09-08 | 2026-09-09 | 2026-09-09 |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-10 |  | 2026-09-10 |  | 2026-09-10 |  | 2026-09-10 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 125 |  | 73
101 | Log | Complete ASP | Yes | 0 | 2026-05-21 | page_10 | Pod 3 | Pod 3_Member1 | 2026-05-21 | 3 | 0 | 10 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 65 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-08 | 3 | 2026-09-11 | 1 | 2026-09-15 | 5 | 2026-09-22 | 2026-09-22 | 2026-09-23 | 2026-09-23 | 1 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-25 | 3 | 2026-09-30 | 1 | 2026-10-01 | 5 | 2026-10-09 | 2026-10-22 | Release 22 | #VALUE! | 2026-10-29 | 2026-10-22 | 157 | #VALUE! | 78 |  |  | #VALUE!
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-19 | page_5 | Pod 3 | Pod 3_Member2 | 2026-06-19 | 3 | 0 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 125 | 2026-12-29 | 1 | 2026-12-30 | 2026-12-30 | 3 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-05 | 2027-01-05 |  | 2027-01-05 | 1 | 2027-01-06 | 5 | 2027-01-13 | 2027-01-13 | 2027-01-14 | 2027-01-14 |  | 2027-01-14 | 2027-01-14 | 2027-01-14 | 2027-01-15 |  | 2027-01-15 |  | 2027-01-15 |  | 2027-01-15 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member1 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 125 | 2026-12-11 | 1 | 2026-12-14 | 2026-12-14 | 3 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2026-12-18 | 2026-12-18 |  | 2026-12-18 | 1 | 2026-12-21 | 5 | 2026-12-29 | 2026-12-29 | 2026-12-30 | 2026-12-30 |  | 2026-12-30 | 2026-12-30 | 2026-12-30 | 2026-12-31 |  | 2026-12-31 |  | 2026-12-31 |  | 2026-12-31 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
103 | OrderAware | React/ASP | Yes | 0 | 2026-06-19 | page_6 | Pod 3 | Pod 3_Member3 | 2026-06-19 | 3 | 0 | 2 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 125 | 2026-12-29 | 1 | 2026-12-30 | 2026-12-30 | 3 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-05 | 2027-01-05 |  | 2027-01-05 | 1 | 2027-01-06 | 5 | 2027-01-13 | 2027-01-13 | 2027-01-14 | 2027-01-14 |  | 2027-01-14 | 2027-01-14 | 2027-01-14 | 2027-01-15 |  | 2027-01-15 |  | 2027-01-15 |  | 2027-01-15 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member2 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 125 | 2026-12-11 | 1 | 2026-12-14 | 2026-12-14 | 3 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2026-12-18 | 2026-12-18 |  | 2026-12-18 | 1 | 2026-12-21 | 5 | 2026-12-29 | 2026-12-29 | 2026-12-30 | 2026-12-30 |  | 2026-12-30 | 2026-12-30 | 2026-12-30 | 2026-12-31 |  | 2026-12-31 |  | 2026-12-31 |  | 2026-12-31 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
104 | OrderAware | React/ASP | Yes | 0 | 2026-05-26 | page_7 | Pod 3 | Pod 3_Member1 | 2026-05-26 | 3 | 0 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 65 | 2026-09-04 | 1 | 2026-09-07 | 2026-09-07 | 3 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-11 | 2026-09-11 |  | 2026-09-11 | 1 | 2026-09-15 | 5 | 2026-09-22 | 2026-09-22 | 2026-09-23 | 2026-09-23 |  | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-09-24 |  | 2026-09-24 |  | 2026-09-24 |  | 2026-09-24 | 2026-09-24 | Release 20 | #VALUE! | 2026-10-01 | 2026-09-24 | 125 |  | 73
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member3 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 125 | 2026-12-11 | 1 | 2026-12-14 | 2026-12-14 | 3 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2026-12-18 | 2026-12-18 |  | 2026-12-18 | 1 | 2026-12-21 | 5 | 2026-12-29 | 2026-12-29 | 2026-12-30 | 2026-12-30 |  | 2026-12-30 | 2026-12-30 | 2026-12-30 | 2026-12-31 |  | 2026-12-31 |  | 2026-12-31 |  | 2026-12-31 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
105 | OrderAware | React/ASP | Yes | 0 | 2026-06-24 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-24 | 3 | 0 | 4 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 125 | 2027-01-01 | 1 | 2027-01-04 | 2027-01-04 | 3 | 2027-01-07 | 2027-01-07 | 2027-01-07 | 2027-01-08 | 2027-01-08 | 3 | 2027-01-13 | 1 | 2027-01-14 | 5 | 2027-01-21 | 2027-01-21 | 2027-01-22 | 2027-01-22 | 1 | 2027-01-25 | 2027-01-25 | 2027-01-25 | 2027-01-26 | 3 | 2027-01-29 | 1 | 2027-02-01 | 5 | 2027-02-08 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 138
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member4 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 125 | 2026-12-11 | 1 | 2026-12-14 | 2026-12-14 | 3 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2026-12-18 | 2026-12-18 |  | 2026-12-18 | 1 | 2026-12-21 | 5 | 2026-12-29 | 2026-12-29 | 2026-12-30 | 2026-12-30 |  | 2026-12-30 | 2026-12-30 | 2026-12-30 | 2026-12-31 |  | 2026-12-31 |  | 2026-12-31 |  | 2026-12-31 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-08 | page_5 | Pod UI | Pod UI_Integration | 2026-06-08 | 5 | 0 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 125 | 2026-12-17 | 1 | 2026-12-18 | 2026-12-18 | 3 | 2026-12-23 | 2026-12-23 | 2026-12-23 | 2026-12-24 | 2026-12-24 |  | 2026-12-24 | 1 | 2026-12-28 | 5 | 2027-01-04 | 2027-01-04 | 2027-01-05 | 2027-01-05 |  | 2027-01-05 | 2027-01-05 | 2027-01-05 | 2027-01-06 |  | 2027-01-06 |  | 2027-01-06 |  | 2027-01-06 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
106 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-26 | page_1 | Pod 1 | Pod 1_Member2 | 2026-05-28 | 3 | 0 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 125 | 2026-12-08 | 1 | 2026-12-09 | 2026-12-09 | 3 | 2026-12-14 | 2026-12-14 | 2026-12-14 | 2026-12-15 | 2026-12-15 |  | 2026-12-15 | 1 | 2026-12-16 | 5 | 2026-12-23 | 2026-12-23 | 2026-12-24 | 2026-12-24 |  | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-28 |  | 2026-12-28 |  | 2026-12-28 |  | 2026-12-28 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
107 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-19 | page_2 | Pod 1 | Pod 1_Member3 | 2026-05-21 | 3 | 0 | 2 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 65 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-08 |  | 2026-09-08 | 1 | 2026-09-09 | 5 | 2026-09-17 | 2026-09-17 | 2026-09-18 | 2026-09-18 |  | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-21 |  | 2026-09-21 |  | 2026-09-21 |  | 2026-09-21 | 2026-09-24 | Release 20 | #VALUE! | 2026-10-01 | 2026-09-24 | 129 |  | 73
108 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-20 | page_3 | Pod 4 | Pod 4_Member1 | 2026-05-22 | 3 | 0 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 65 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 3 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-09 | 2026-09-09 |  | 2026-09-09 | 1 | 2026-09-10 | 5 | 2026-09-18 | 2026-09-18 | 2026-09-21 | 2026-09-21 |  | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-22 |  | 2026-09-22 |  | 2026-09-22 |  | 2026-09-22 | 2026-09-24 | Release 20 | #VALUE! | 2026-10-01 | 2026-09-24 | 128 |  | 73
109 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-04 | page_4 | Pod 1 | Pod 1_Member2 | 2026-06-08 | 3 | 0 | 4 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 125 | 2026-12-15 | 1 | 2026-12-16 | 2026-12-16 | 3 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-22 | 2026-12-22 |  | 2026-12-22 | 1 | 2026-12-23 | 5 | 2026-12-31 | 2026-12-31 | 2027-01-01 | 2027-01-01 |  | 2027-01-01 | 2027-01-01 | 2027-01-01 | 2027-01-04 |  | 2027-01-04 |  | 2027-01-04 |  | 2027-01-04 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
110 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-26 | page_5 | Pod 1 | Pod 1_Member3 | 2026-05-28 | 3 | 0 | 5 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 125 | 2026-12-08 | 1 | 2026-12-09 | 2026-12-09 | 3 | 2026-12-14 | 2026-12-14 | 2026-12-14 | 2026-12-15 | 2026-12-15 |  | 2026-12-15 | 1 | 2026-12-16 | 5 | 2026-12-23 | 2026-12-23 | 2026-12-24 | 2026-12-24 |  | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-28 |  | 2026-12-28 |  | 2026-12-28 |  | 2026-12-28 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
111 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-27 | page_6 | Pod 4 | Pod 4_Member1 | 2026-05-29 | 3 | 0 | 6 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 125 | 2026-12-08 | 1 | 2026-12-09 | 2026-12-09 | 3 | 2026-12-14 | 2026-12-14 | 2026-12-14 | 2026-12-15 | 2026-12-15 |  | 2026-12-15 | 1 | 2026-12-16 | 5 | 2026-12-23 | 2026-12-23 | 2026-12-24 | 2026-12-24 |  | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-28 |  | 2026-12-28 |  | 2026-12-28 |  | 2026-12-28 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 133 |  |  | #N/A
112 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-11 | page_7 | Pod 1 | Pod 1_Member2 | 2026-06-15 | 3 | 0 | 7 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 125 | 2026-12-22 | 1 | 2026-12-23 | 2026-12-23 | 3 | 2026-12-29 | 2026-12-29 | 2026-12-29 | 2026-12-30 | 2026-12-30 | 3 | 2027-01-04 | 1 | 2027-01-05 | 5 | 2027-01-12 | 2027-01-12 | 2027-01-13 | 2027-01-13 | 1 | 2027-01-14 | 2027-01-14 | 2027-01-14 | 2027-01-15 | 3 | 2027-01-20 | 1 | 2027-01-21 | 5 | 2027-01-28 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 138
113 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-04 | page_1 | Pod 1 | Pod 1_Member3 | 2026-06-08 | 3 | 0 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 125 | 2026-12-15 | 1 | 2026-12-16 | 2026-12-16 | 3 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-22 | 2026-12-22 |  | 2026-12-22 | 1 | 2026-12-23 | 5 | 2026-12-31 | 2026-12-31 | 2027-01-01 | 2027-01-01 |  | 2027-01-01 | 2027-01-01 | 2027-01-01 | 2027-01-04 |  | 2027-01-04 |  | 2027-01-04 |  | 2027-01-04 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
114 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-04 | page_2 | Pod 4 | Pod 4_Member1 | 2026-06-08 | 3 | 0 | 2 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 125 | 2026-12-15 | 1 | 2026-12-16 | 2026-12-16 | 3 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-22 | 2026-12-22 |  | 2026-12-22 | 1 | 2026-12-23 | 5 | 2026-12-31 | 2026-12-31 | 2027-01-01 | 2027-01-01 |  | 2027-01-01 | 2027-01-01 | 2027-01-01 | 2027-01-04 |  | 2027-01-04 |  | 2027-01-04 |  | 2027-01-04 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
115 | Reg+Attendance | Complete ASP | No | 2 | 2026-05-25 | page_3 | Pod 4 | Pod 4_Member2 | 2026-05-27 | 3 | 0 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 125 | 2026-12-07 | 1 | 2026-12-08 | 2026-12-08 | 3 | 2026-12-11 | 2026-12-11 | 2026-12-11 | 2026-12-14 | 2026-12-14 |  | 2026-12-14 | 1 | 2026-12-15 | 5 | 2026-12-22 | 2026-12-22 | 2026-12-23 | 2026-12-23 |  | 2026-12-23 | 2026-12-23 | 2026-12-23 | 2026-12-24 |  | 2026-12-24 |  | 2026-12-24 |  | 2026-12-24 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
116 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-11 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-15 | 3 | 0 | 4 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 125 | 2026-12-22 | 1 | 2026-12-23 | 2026-12-23 | 3 | 2026-12-29 | 2026-12-29 | 2026-12-29 | 2026-12-30 | 2026-12-30 |  | 2026-12-30 | 1 | 2026-12-31 | 5 | 2027-01-07 | 2027-01-07 | 2027-01-08 | 2027-01-08 |  | 2027-01-08 | 2027-01-08 | 2027-01-08 | 2027-01-11 |  | 2027-01-11 |  | 2027-01-11 |  | 2027-01-11 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 133 |  |  | #N/A
117 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-11 | page_5 | Pod 4 | Pod 4_Member1 | 2026-06-15 | 3 | 0 | 5 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 125 | 2026-12-22 | 1 | 2026-12-23 | 2026-12-23 | 3 | 2026-12-29 | 2026-12-29 | 2026-12-29 | 2026-12-30 | 2026-12-30 | 3 | 2027-01-04 | 1 | 2027-01-05 | 5 | 2027-01-12 | 2027-01-12 | 2027-01-13 | 2027-01-13 | 1 | 2027-01-14 | 2027-01-14 | 2027-01-14 | 2027-01-15 | 3 | 2027-01-20 | 1 | 2027-01-21 | 5 | 2027-01-28 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 138 |  |  | #N/A
118 | Reports | Complete ASP | No | 2 | 2026-06-02 | page_1 | Pod 4 | Pod 4_Member2 | 2026-06-04 | 3 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 125 | 2026-12-11 | 1 | 2026-12-14 | 2026-12-14 | 3 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2026-12-18 | 2026-12-18 |  | 2026-12-18 | 1 | 2026-12-21 | 5 | 2026-12-29 | 2026-12-29 | 2026-12-30 | 2026-12-30 |  | 2026-12-30 | 2026-12-30 | 2026-12-30 | 2026-12-31 |  | 2026-12-31 |  | 2026-12-31 |  | 2026-12-31 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
119 | Reports | Complete ASP | No | 2 | 2026-06-18 | page_2 | Pod 1 | Pod 1_Member3 | 2026-06-22 | 3 | 0 | 2 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 125 | 2026-12-30 | 1 | 2026-12-31 | 2026-12-31 | 3 | 2027-01-05 | 2027-01-05 | 2027-01-05 | 2027-01-06 | 2027-01-06 |  | 2027-01-06 | 1 | 2027-01-07 | 5 | 2027-01-14 | 2027-01-14 | 2027-01-15 | 2027-01-15 | 2 | 2027-01-19 | 2027-01-19 | 2027-01-19 | 2027-01-20 |  | 2027-01-20 | 2 | 2027-01-22 |  | 2027-01-22 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
120 | Reports | Complete ASP | No | 2 | 2026-06-18 | page_3 | Pod 4 | Pod 4_Member1 | 2026-06-22 | 3 | 0 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 125 | 2026-12-30 | 1 | 2026-12-31 | 2026-12-31 | 3 | 2027-01-05 | 2027-01-05 | 2027-01-05 | 2027-01-06 | 2027-01-06 |  | 2027-01-06 | 1 | 2027-01-07 | 5 | 2027-01-14 | 2027-01-14 | 2027-01-15 | 2027-01-15 |  | 2027-01-15 | 2027-01-15 | 2027-01-15 | 2027-01-18 |  | 2027-01-18 |  | 2027-01-18 |  | 2027-01-18 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 133
121 | Reports | Complete ASP | No | 2 | 2026-06-25 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-29 | 3 | 0 | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 155 | 2027-02-16 | 1 | 2027-02-17 | 2027-02-17 | 3 | 2027-02-22 | 2027-02-22 | 2027-02-22 | 2027-02-23 | 2027-02-23 |  | 2027-02-23 | 1 | 2027-02-24 | 5 | 2027-03-03 | 2027-03-03 | 2027-03-04 | 2027-03-04 |  | 2027-03-04 | 2027-03-04 | 2027-03-04 | 2027-03-05 |  | 2027-03-05 |  | 2027-03-05 |  | 2027-03-05 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 163 |  |  | #N/A
122 | Reports | Complete ASP | No | 2 | 2026-06-09 | page_5 | Pod 4 | Pod 4_Member2 | 2026-06-11 | 3 | 0 | 5 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 125 | 2026-12-18 | 1 | 2026-12-21 | 2026-12-21 | 3 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-28 | 2026-12-28 | 3 | 2026-12-31 | 1 | 2027-01-01 | 5 | 2027-01-08 | 2027-01-08 | 2027-01-11 | 2027-01-11 | 1 | 2027-01-12 | 2027-01-12 | 2027-01-12 | 2027-01-13 | 3 | 2027-01-18 | 1 | 2027-01-19 | 5 | 2027-01-26 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 138
123 | Webuser | Complete ASP | No | 2 | 2026-04-29 | page_1 | Pod 3 | Pod 3_Member2 | 2026-05-01 | 3 | 0 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 65 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-12 | 3 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 |  | 2026-08-18 | 1 | 2026-08-19 | 5 | 2026-08-28 | 2026-08-28 | 2026-08-31 | 2026-08-31 |  | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-01 |  | 2026-09-01 |  | 2026-09-01 |  | 2026-09-01 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 134 |  | 73
124 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_2 | Pod 3 | Pod 3_Member3 | 2026-05-11 | 3 | 0 | 2 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 65 | 2026-08-18 | 1 | 2026-08-19 | 2026-08-19 | 3 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 | 2026-08-27 |  | 2026-08-27 | 1 | 2026-08-28 | 5 | 2026-09-04 | 2026-09-04 | 2026-09-07 | 2026-09-07 |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-08 |  | 2026-09-08 |  | 2026-09-08 |  | 2026-09-08 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 127 | #VALUE! | 73
125 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_3 | Pod 3 | Pod 3_Member1 | 2026-05-11 | 3 | 0 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 65 | 2026-08-18 | 1 | 2026-08-19 | 2026-08-19 | 3 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 | 2026-08-27 |  | 2026-08-27 | 1 | 2026-08-28 | 5 | 2026-09-04 | 2026-09-04 | 2026-09-07 | 2026-09-07 |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-08 |  | 2026-09-08 |  | 2026-09-08 |  | 2026-09-08 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 127 | #VALUE! | 73
126 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_4 | Pod 3 | Pod 3_Member2 | 2026-05-11 | 3 | 0 | 4 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 95 | 2026-10-05 | 1 | 2026-10-06 | 2026-10-06 | 3 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 2026-10-12 | 2026-10-12 |  | 2026-10-12 | 1 | 2026-10-13 | 5 | 2026-10-22 | 2026-10-22 | 2026-10-23 | 2026-10-23 |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-26 |  | 2026-10-26 |  | 2026-10-26 |  | 2026-10-26 | 2026-11-05 | Release 23 | #VALUE! | 2026-11-12 | 2026-11-05 | 183 |  | 103
127 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_5 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 5 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 95 | 2026-10-12 | 1 | 2026-10-13 | 2026-10-13 | 3 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-19 | 2026-10-19 |  | 2026-10-19 | 1 | 2026-10-22 | 5 | 2026-10-29 | 2026-10-29 | 2026-10-30 | 2026-10-30 |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-11-02 |  | 2026-11-02 |  | 2026-11-02 |  | 2026-11-02 | 2026-11-05 | Release 23 | #VALUE! | 2026-11-12 | 2026-11-05 | 176 | #VALUE! | 103
128 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_1 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 6 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 95 | 2026-10-12 | 1 | 2026-10-13 | 2026-10-13 | 3 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-19 | 2026-10-19 |  | 2026-10-19 | 1 | 2026-10-22 | 5 | 2026-10-29 | 2026-10-29 | 2026-10-30 | 2026-10-30 |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-11-02 |  | 2026-11-02 |  | 2026-11-02 |  | 2026-11-02 | 2026-11-05 | Release 23 | #VALUE! | 2026-11-12 | 2026-11-05 | 176 | #VALUE! | 103
129 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_2 | Pod 3 | Pod 3_Member2 | 2026-05-18 | 3 |  | 7 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 95 | 2026-10-12 | 1 | 2026-10-13 | 2026-10-13 | 3 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-19 | 2026-10-19 |  | 2026-10-19 | 1 | 2026-10-22 | 5 | 2026-10-29 | 2026-10-29 | 2026-10-30 | 2026-10-30 |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-11-02 |  | 2026-11-02 |  | 2026-11-02 |  | 2026-11-02 | 2026-11-05 | Release 23 | #VALUE! | 2026-11-12 | 2026-11-05
130 | Webuser | Complete ASP | No | 2 | 2026-05-21 | page_3 | Pod 3 | Pod 3_Member3 | 2026-05-25 | 3 |  | 8 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 95 | 2026-10-19 | 1 | 2026-10-22 | 2026-10-22 | 3 | 2026-10-27 | 2026-10-27 | 2026-10-27 | 2026-10-28 | 2026-10-28 |  | 2026-10-28 | 1 | 2026-10-29 | 5 | 2026-11-05 | 2026-11-05 | 2026-11-06 | 2026-11-06 |  | 2026-11-06 | 2026-11-06 | 2026-11-06 | 2026-11-09 |  | 2026-11-09 |  | 2026-11-09 |  | 2026-11-09 | 2026-11-19 | Release 24 | #VALUE! | 2026-11-26 | 2026-11-19
131 | Webuser | Complete ASP | No | 2 | 2026-06-01 | page_4 | Pod 3 | Pod 3_Member1 | 2026-06-03 | 3 |  | 9 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 125 | 2026-12-10 | 1 | 2026-12-11 | 2026-12-11 | 3 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-17 | 2026-12-17 |  | 2026-12-17 | 1 | 2026-12-18 | 5 | 2026-12-28 | 2026-12-28 | 2026-12-29 | 2026-12-29 |  | 2026-12-29 | 2026-12-29 | 2026-12-29 | 2026-12-30 |  | 2026-12-30 |  | 2026-12-30 |  | 2026-12-30 | 0 | #N/A | #N/A | #N/A | #N/A
132 | Webuser | Complete ASP | No | 2 | 2026-05-21 | page_5 | Pod 3 | Pod 3_Member2 | 2026-05-25 | 3 |  | 10 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 95 | 2026-10-19 | 1 | 2026-10-22 | 2026-10-22 | 3 | 2026-10-27 | 2026-10-27 | 2026-10-27 | 2026-10-28 | 2026-10-28 | 3 | 2026-11-02 | 1 | 2026-11-03 | 5 | 2026-11-11 | 2026-11-11 | 2026-11-12 | 2026-11-12 | 1 | 2026-11-13 | 2026-11-13 | 2026-11-13 | 2026-11-16 | 3 | 2026-11-19 | 1 | 2026-11-20 | 5 | 2026-11-27 | 2026-12-03 | Release 25 | #VALUE! | 2026-12-10 | 2026-12-03
133 | Gradebook | Complete ASP | No | 2 | 2026-06-08 | page_6 | Pod 3 | Pod 3_Member1 | 2026-06-10 | 3 |  | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 125 | 2026-12-17 | 1 | 2026-12-18 | 2026-12-18 | 3 | 2026-12-23 | 2026-12-23 | 2026-12-23 | 2026-12-24 | 2026-12-24 |  | 2026-12-24 | 1 | 2026-12-28 | 5 | 2027-01-04 | 2027-01-04 | 2027-01-05 | 2027-01-05 |  | 2027-01-05 | 2027-01-05 | 2027-01-05 | 2027-01-06 |  | 2027-01-06 |  | 2027-01-06 |  | 2027-01-06 | 0 | #N/A | #N/A | #N/A
134 | Gradebook | Complete ASP | No | 2 | 2026-06-15 | page_7 | Pod 3 | Pod 3_Member1 | 2026-06-17 | 3 |  | 2 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 155 | 2027-02-05 | 1 | 2027-02-08 | 2027-02-08 | 3 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 2027-02-12 | 2027-02-12 |  | 2027-02-12 | 1 | 2027-02-15 | 5 | 2027-02-22 | 2027-02-22 | 2027-02-23 | 2027-02-23 |  | 2027-02-23 | 2027-02-23 | 2027-02-23 | 2027-02-24 |  | 2027-02-24 |  | 2027-02-24 |  | 2027-02-24 | 0 | #N/A | #N/A | #N/A
135 | Gradebook | Complete ASP | No | 2 | 2026-05-28 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 |  | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 155 | 2027-01-21 | 1 | 2027-01-22 | 2027-01-22 | 3 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 2027-01-28 | 2027-01-28 |  | 2027-01-28 | 1 | 2027-01-29 | 5 | 2027-02-05 | 2027-02-05 | 2027-02-08 | 2027-02-08 |  | 2027-02-08 | 2027-02-08 | 2027-02-08 | 2027-02-09 |  | 2027-02-09 |  | 2027-02-09 |  | 2027-02-09 | 0 | #N/A | #N/A | #N/A
136 | Gradebook | React/ASP | No | 2 | 2026-06-05 | page_9 | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 |  | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 155 | 2027-01-28 | 1 | 2027-01-29 | 2027-01-29 | 3 | 2027-02-03 | 2027-02-03 | 2027-02-03 | 2027-02-04 | 2027-02-04 |  | 2027-02-04 | 1 | 2027-02-05 | 5 | 2027-02-12 | 2027-02-12 | 2027-02-15 | 2027-02-15 |  | 2027-02-15 | 2027-02-15 | 2027-02-15 | 2027-02-16 |  | 2027-02-16 |  | 2027-02-16 |  | 2027-02-16 | 0 | #N/A | #N/A | #N/A
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member1 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 155 | 2027-02-05 | 1 | 2027-02-08 | 2027-02-08 | 3 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 2027-02-12 | 2027-02-12 |  | 2027-02-12 | 1 | 2027-02-15 | 5 | 2027-02-22 | 2027-02-22 | 2027-02-23 | 2027-02-23 |  | 2027-02-23 | 2027-02-23 | 2027-02-23 | 2027-02-24 |  | 2027-02-24 |  | 2027-02-24 |  | 2027-02-24 | 0 | #N/A | #N/A | #N/A
137 | Gradebook | React/ASP | No | 2 | 2026-05-28 | page_10 | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 |  | 5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 155 | 2027-01-21 | 1 | 2027-01-22 | 2027-01-22 | 3 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 2027-01-28 | 2027-01-28 |  | 2027-01-28 | 1 | 2027-01-29 | 5 | 2027-02-05 | 2027-02-05 | 2027-02-08 | 2027-02-08 |  | 2027-02-08 | 2027-02-08 | 2027-02-08 | 2027-02-09 |  | 2027-02-09 |  | 2027-02-09 |  | 2027-02-09 | 0 | #N/A | #N/A | #N/A
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member2 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 155 | 2027-02-05 | 1 | 2027-02-08 | 2027-02-08 | 3 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 2027-02-12 | 2027-02-12 |  | 2027-02-12 | 1 | 2027-02-15 | 5 | 2027-02-22 | 2027-02-22 | 2027-02-23 | 2027-02-23 |  | 2027-02-23 | 2027-02-23 | 2027-02-23 | 2027-02-24 |  | 2027-02-24 |  | 2027-02-24 |  | 2027-02-24 | 0 | #N/A | #N/A | #N/A
138 | Gradebook | React/ASP | No | 2 | 2026-06-05 | page_11 | Pod 3 | Pod 3_Member3 | 2026-06-09 | 3 |  | 6 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 155 | 2027-01-28 | 1 | 2027-01-29 | 2027-01-29 | 3 | 2027-02-03 | 2027-02-03 | 2027-02-03 | 2027-02-04 | 2027-02-04 |  | 2027-02-04 | 1 | 2027-02-05 | 5 | 2027-02-12 | 2027-02-12 | 2027-02-15 | 2027-02-15 |  | 2027-02-15 | 2027-02-15 | 2027-02-15 | 2027-02-16 |  | 2027-02-16 |  | 2027-02-16 |  | 2027-02-16 | 0 | #N/A | #N/A | #N/A
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member3 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 155 | 2027-02-05 | 1 | 2027-02-08 | 2027-02-08 | 3 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 2027-02-12 | 2027-02-12 |  | 2027-02-12 | 1 | 2027-02-15 | 5 | 2027-02-22 | 2027-02-22 | 2027-02-23 | 2027-02-23 |  | 2027-02-23 | 2027-02-23 | 2027-02-23 | 2027-02-24 |  | 2027-02-24 |  | 2027-02-24 |  | 2027-02-24 | 0 | #N/A | #N/A | #N/A
139 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_12 | Pod 3 | Pod 3_Member1 | 2026-06-24 | 3 |  | 7 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 155 | 2027-02-12 | 1 | 2027-02-15 | 2027-02-15 | 3 | 2027-02-18 | 2027-02-18 | 2027-02-18 | 2027-02-19 | 2027-02-19 |  | 2027-02-19 | 1 | 2027-02-22 | 5 | 2027-03-01 | 2027-03-01 | 2027-03-02 | 2027-03-02 |  | 2027-03-02 | 2027-03-02 | 2027-03-02 | 2027-03-03 |  | 2027-03-03 |  | 2027-03-03 |  | 2027-03-03 | 0 | #N/A | #N/A | #N/A
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member4 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 155 | 2027-02-05 | 1 | 2027-02-08 | 2027-02-08 | 3 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 2027-02-12 | 2027-02-12 |  | 2027-02-12 | 1 | 2027-02-15 | 5 | 2027-02-22 | 2027-02-22 | 2027-02-23 | 2027-02-23 |  | 2027-02-23 | 2027-02-23 | 2027-02-23 | 2027-02-24 |  | 2027-02-24 |  | 2027-02-24 |  | 2027-02-24 | 0 | #N/A | #N/A | #N/A
140 | Gradebook | React/ASP | No | 2 | 2026-06-12 | page_13 | Pod 3 | Pod 3_Member2 | 2026-06-16 | 3 |  | 8 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 155 | 2027-02-04 | 1 | 2027-02-05 | 2027-02-05 | 3 | 2027-02-10 | 2027-02-10 | 2027-02-10 | 2027-02-11 | 2027-02-11 |  | 2027-02-11 | 1 | 2027-02-12 | 5 | 2027-02-19 | 2027-02-19 | 2027-02-22 | 2027-02-22 |  | 2027-02-22 | 2027-02-22 | 2027-02-22 | 2027-02-23 |  | 2027-02-23 |  | 2027-02-23 |  | 2027-02-23 | 0 | #N/A | #N/A | #N/A
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_9 | Pod UI | Pod UI_UI-Member1 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 155 | 2027-02-16 | 1 | 2027-02-17 | 2027-02-17 | 3 | 2027-02-22 | 2027-02-22 | 2027-02-22 | 2027-02-23 | 2027-02-23 |  | 2027-02-23 | 1 | 2027-02-24 | 5 | 2027-03-03 | 2027-03-03 | 2027-03-04 | 2027-03-04 |  | 2027-03-04 | 2027-03-04 | 2027-03-04 | 2027-03-05 |  | 2027-03-05 |  | 2027-03-05 |  | 2027-03-05 | 0 | #N/A | #N/A | #N/A
141 | Gradebook | React/ASP | No | 2 | 2026-06-12 | page_14 | Pod 3 | Pod 3_Member3 | 2026-06-16 | 3 |  | 9 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 155 | 2027-02-04 | 1 | 2027-02-05 | 2027-02-05 | 3 | 2027-02-10 | 2027-02-10 | 2027-02-10 | 2027-02-11 | 2027-02-11 | 3 | 2027-02-16 | 1 | 2027-02-17 | 5 | 2027-02-24 | 2027-02-24 | 2027-02-25 | 2027-02-25 | 1 | 2027-02-26 | 2027-02-26 | 2027-02-26 | 2027-03-01 | 3 | 2027-03-04 | 1 | 2027-03-05 | 5 | 2027-03-12 | 0 | #N/A | #N/A | #N/A
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_9 | Pod UI | Pod UI_UI-Member2 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 155 | 2027-02-16 | 1 | 2027-02-17 | 2027-02-17 | 3 | 2027-02-22 | 2027-02-22 | 2027-02-22 | 2027-02-23 | 2027-02-23 |  | 2027-02-23 | 1 | 2027-02-24 | 5 | 2027-03-03 | 2027-03-03 | 2027-03-04 | 2027-03-04 |  | 2027-03-04 | 2027-03-04 | 2027-03-04 | 2027-03-05 |  | 2027-03-05 |  | 2027-03-05 |  | 2027-03-05 | 0 | #N/A | #N/A | #N/A
136 | Gradebook | React/ASP | No | 0 | 2026-06-23 | page_9 | Pod UI | Pod UI_Integration | 2026-06-23 | 5 |  | 4 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 155 | 2027-02-15 | 1 | 2027-02-16 | 2027-02-16 | 3 | 2027-02-19 | 2027-02-19 | 2027-02-19 | 2027-02-22 | 2027-02-22 |  | 2027-02-22 | 1 | 2027-02-23 | 5 | 2027-03-02 | 2027-03-02 | 2027-03-03 | 2027-03-03 |  | 2027-03-03 | 2027-03-03 | 2027-03-03 | 2027-03-04 |  | 2027-03-04 |  | 2027-03-04 |  | 2027-03-04 | 0 | #N/A | #N/A | #N/A
Formulas:
Start Date = [Module Target Start (Input)]
Start Date = WORKDAY([Module Target Start (Input)],[Buffer In case of no KT])
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Code Freeze Date = [TCR Bugs Closure Date]
Pearson Regression Testing/UAT Date = WORKDAY([TEST Deployment], 1, IndHolidays)
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&(MAX([PR Response receive Date],[TCR Bugs Closure Date])))
Code freeze date = Release cutoff Date = WORKDAY([Release Date (2-Wk Cycle)], -5)
Release Request Approved Date = WORKDAY([Release #], 2, IndHolidays)
Release Date (2-Wk Cycle) = VLOOKUP([Release #],ReleaseTimeline!$B2:C27,2,FALSE)
Module Target Start (Input) = WORKDAY([PR raised date, row above],1)

## Adding POD 4
No. | Module | Target page Technology | Recieved Functional & Non Fuctional Walkthrough | Buffer In case of no KT | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | Status | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Code Freeze Date | TEST Deployment | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | Code freeze date = Release cutoff Date | Release # | Release Request Approved Date | Release Date (2-Wk Cycle) | Code freeze date = Release cutoff Date | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
1 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed | 1 | 2026-04-20 | 1 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | #VALUE! | 27 |  | 3
2 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_2 | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed | 1 | 2026-04-20 | 1 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 27 |  | 3
3 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed | 1 | 2026-04-20 | 1 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 27 |  | 3
4 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | page_4 | Pod 1 | Pod 1_Member1 | 2026-04-20 | 3 | 0 | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Completed | 1 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 |  | 2026-05-05 | 0 | 2026-05-05 | 0 | 2026-05-05 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 22 |  | 3
5 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | page_5 | Pod 1 | Pod 1_Member2 | 2026-04-20 | 3 | 0 | 5 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Completed | 1 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 3 | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 | #VALUE! | 3 |  |  | #VALUE!
6 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_1 | Pod 2 | Pod 2_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed | 1 | 2026-04-20 | 1 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 27 |  | 3
7 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_2 | Pod 2 | Pod 2_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed | 1 | 2026-04-20 | 1 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 27 |  | 3
8 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_3 | Pod 2 | Pod 2_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed | 1 | 2026-04-20 | 1 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 | 1 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 0 | 2026-04-29 | 0 | 2026-04-29 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 27 |  | 3
9 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_4 | Pod 2 | Pod 2_Member1 | 2026-04-20 | 3 | 0 | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Completed | 1 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 |  | 2026-05-05 | 0 | 2026-05-05 | 0 | 2026-05-05 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 22 |  | 3
10 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_5 | Pod 2 | Pod 2_Member2 | 2026-04-20 | 3 | 0 | 5 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Completed | 1 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 |  | 2026-05-05 | 0 | 2026-05-05 | 0 | 2026-05-05 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 22 |  | 3
11 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_6 | Pod 2 | Pod 2_Member3 | 2026-04-20 | 3 | 0 | 6 | 2026-04-22 | 2026-04-22 | 2026-04-22 | Completed | 1 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 |  | 2026-05-05 | 0 | 2026-05-05 | 0 | 2026-05-05 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 22 |  | 3
12 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_7 | Pod 2 | Pod 2_Member1 | 2026-04-24 | 3 | 0 | 7 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Completed | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
13 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_8 | Pod 2 | Pod 2_Member2 | 2026-04-24 | 3 | 0 | 8 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Completed | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 | #VALUE! | 3 |  |  | #VALUE!
14 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_9 | Pod 2 | Pod 2_Member3 | 2026-04-24 | 3 | 0 | 9 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Completed | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
15 | Assessments | Complete ASP | Yes | 0 | 2026-04-29 | page_10 | Pod 2 | Pod 2_Member1 | 2026-04-29 | 3 | 0 | 10 | 2026-05-04 | 2026-05-04 | 2026-05-04 | Completed | 1 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 3 | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 3
16 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-28 | 3 | 0 | 1 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Completed | 1 | 2026-05-04 | 1 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 28 |  | 3
17 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | page_2 | Pod 1 | Pod 1_Member2 | 2026-04-28 | 3 | 0 | 2 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Completed | 1 | 2026-05-04 | 1 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 28 |  | 3
18 | AssetAware | Complete ASP | No | 2 | 2026-04-20 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-22 | 3 | 0 | 3 | 2026-04-24 | 2026-04-24 | 2026-04-24 | Completed | 1 | 2026-04-27 | 1 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | 1 | 2026-05-04 | 1 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 |  | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 |  | 2026-05-07 | 0 | 2026-05-07 | 0 | 2026-05-07 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 20 |  | 3
19 | AssetAware | Complete ASP | No | 2 | 2026-05-01 | page_4 | Pod 1 | Pod 1_Member1 | 2026-05-05 | 3 | 0 | 4 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Completed | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 3 | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 3
20 | Communication | Complete ASP | No | 2 | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-07 | 3 | 0 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 |  | 1 | 2026-05-12 | 1 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 |  | 2026-05-21 | 0 | 2026-05-21 | 0 | 2026-05-21 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 17 |  | 3
21 | Communication | Complete ASP | No | 2 | 2026-04-29 | page_2 | Pod 2 | Pod 2_Member2 | 2026-05-01 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 22 |  | 3
22 | Communication | Complete ASP | No | 2 | 2026-04-29 | page_3 | Pod 2 | Pod 2_Member3 | 2026-05-01 | 3 | 0 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 22 |  | 3
23 | Communication | Complete ASP | No | 2 | 2026-05-12 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 1 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 | #VALUE! | 3 |  |  | #VALUE!
24 | Content | Complete ASP | No | 2 | 2026-04-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 | 0 | 1 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Completed | 1 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 |  | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 |  | 2026-05-04 | 0 | 2026-05-04 | 0 | 2026-05-04 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 23 |  | 3
25 | Content | Complete ASP | No | 2 | 2026-04-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-17 | 3 | 0 | 2 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Completed | 1 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 |  | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 |  | 2026-05-04 | 0 | 2026-05-04 | 0 | 2026-05-04 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 23 |  | 3
26 | Content | Complete ASP | No | 2 | 2026-04-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-17 | 3 | 0 | 3 | 2026-04-21 | 2026-04-21 | 2026-04-21 | Completed | 1 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 1 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 |  | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 |  | 2026-05-04 | 0 | 2026-05-04 | 0 | 2026-05-04 | 2026-05-07 | Release 10 | #VALUE! | 2026-05-14 | 2026-05-07 | 23 |  | 3
27 | Content | Complete ASP | No | 2 | 2026-04-22 | page_4 | Pod 3 | Pod 3_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Completed | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 1 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 3 | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
28 | Enrollment | Complete ASP | No | 2 | 2026-04-27 | page_1 | Pod 1 | Pod 1_Member3 | 2026-04-29 | 3 | 0 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | Completed | 1 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 1 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 24 |  | 3
29 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member1 | 2026-05-12 | 3 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Completed | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 28 |  | 3
30 | Enrollment | Complete ASP | No | 2 | 2026-05-01 | page_3 | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Completed | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 |  | 3
31 | Enrollment | Complete ASP | No | 2 | 2026-05-05 | page_4 | Pod 1 | Pod 1_Member3 | 2026-05-07 | 3 | 0 | 4 | 2026-05-11 | 2026-05-11 | 2026-05-11 | Completed | 1 | 2026-05-12 | 1 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 |  | 2026-05-21 | 0 | 2026-05-21 | 0 | 2026-05-21 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 17 |  | 3
32 | Enrollment | Complete ASP | No | 2 | 2026-05-15 | page_5 | Pod 1 | Pod 1_Member1 | 2026-05-19 | 3 | 0 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-21 |  | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 1 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 21 |  | 3
33 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | page_6 | Pod 1 | Pod 1_Member2 | 2026-05-12 | 3 | 0 | 6 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Completed | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 28 |  | 3
34 | Enrollment | Complete ASP | No | 2 | 2026-05-12 | page_7 | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 7 | 2026-05-18 | 2026-05-18 | 2026-05-18 | Completed | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 24 |  | 3
35 | Enrollment | Complete ASP | No | 2 | 2026-05-22 | page_8 | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 0 | 8 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  | 1 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 3 | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 3
36 | ExtendedField | Complete ASP | Yes | 0 | 2026-06-01 | page_1 | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 21 |  | 3
37 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Completed | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
38 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-05 | page_3 | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Completed | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 |  | 3
39 | ExtendedField | Complete ASP | Yes | 0 | 2026-06-05 | page_4 | Pod 1 | Pod 1_Member1 | 2026-06-05 | 3 | 0 | 4 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 3
40 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-13 | page_5 | Pod 1 | Pod 1_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 | Completed | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 27 |  | 3
41 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | page_6 | Pod 1 | Pod 1_Member3 | 2026-05-08 | 3 | 0 | 6 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Completed | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
42 | ExtendedField | Complete ASP | Yes | 0 | 2026-06-10 | page_7 | Pod 1 | Pod 1_Member1 | 2026-06-10 | 3 | 0 | 7 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 27 |  | 3
43 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 3
44 | GradeBook | Complete ASP | Yes | 0 | 2026-05-13 | page_3 | Pod 2 | Pod 2_Member1 | 2026-05-13 | 3 | 0 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | Completed | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 3 | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 3
45 | GradeBook | Complete ASP | Yes | 0 | 2026-05-05 | page_4 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Completed | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 3 | 2026-05-29 | 1 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 49 |  | 6
46 | Home | Complete ASP | No | 2 | 2026-04-22 | page_1 | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Completed | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
47 | Home | Complete ASP | No | 2 | 2026-04-29 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-01 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 | Completed | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 22 |  | 3
48 | Home | Complete ASP | No | 2 | 2026-04-22 | page_3 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Completed | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
49 | Home | Complete ASP | No | 2 | 2026-04-29 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-01 | 3 | 0 | 4 | 2026-05-06 | 2026-05-06 | 2026-05-06 | Completed | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 3 | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 | #VALUE! | 3 |  |  | #VALUE!
50 | IssueAware | Complete ASP | Yes | 0 | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Completed | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 |  | 3
51 | IssueAware | Complete ASP | Yes | 0 | 2026-05-18 | page_2 | Pod 2 | Pod 2_Member1 | 2026-05-18 | 3 | 0 | 2 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 3
52 | Library | Complete ASP | Yes | 0 | 2026-04-29 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-29 | 3 | 0 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | Completed | 1 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 1 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 24 |  | 3
53 | Library | Complete ASP | Yes | 0 | 2026-04-24 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Completed | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 |  | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 3
54 | Library | Complete ASP | Yes | 0 | 2026-04-29 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | Completed | 1 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 3 | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 3
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_2 | Pod 2 | Pod 2_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Completed | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 3 | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_2 | Pod UI | Pod UI_UI-Member1 | 2026-05-08 | 5 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Completed | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 3 | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 3
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod 2 | Pod 2_Member3 | 2026-05-08 | 3 | 0 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Completed | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 | #VALUE! | 3
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod UI | Pod UI_UI-Member2 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Completed | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 28 | #VALUE! | 3
57 | LMU | React/ASP | Yes | 0 | 2026-05-21 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-21 | 3 | 0 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 3 | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod UI | Pod UI_UI-Member3 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | Completed | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 28 | #VALUE! | 3
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod 2 | Pod 2_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 | Completed | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 27 |  | 3
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod UI | Pod UI_UI-Member4 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | Completed | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 23 |  | 3
59 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_6 | Pod 2 | Pod 2_Member3 | 2026-05-13 | 3 | 0 | 6 | 2026-05-15 | 2026-05-15 | 2026-05-15 | Completed | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 3 | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 | #VALUE! | 3 |  |  | #VALUE!
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod UI | Pod UI_UI-Member5 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | Completed | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 23 |  | 3
58 | LMU | React/ASP | Yes | 0 | 2026-05-20 | page_5 | Pod UI | Pod UI_Integration | 2026-05-20 | 5 | 0 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-26 |  | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 3
60 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-26 | 3 | 0 | 4 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  | 1 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 27 |  | 3
61 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 3
62 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-18 | 3 | 0 | 9 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 22 |  | 3
63 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_7 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 3 | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 3
64 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-21 | 3 | 0 | 11 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
65 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-21 | 3 | 0 | 12 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 3 | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
66 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_10 | Pod 2 | Pod 2_Member1 | 2026-06-05 | 3 | 0 | 10 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 3
67 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_14 | Pod 2 | Pod 2_Member2 | 2026-05-26 | 3 | 0 | 14 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  | 1 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 3 | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 | #VALUE! | 3 |  |  | #VALUE!
68 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_15 | Pod 2 | Pod 2_Member3 | 2026-05-26 | 3 | 0 | 15 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  | 1 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 27 |  | 3
69 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_13 | Pod 2 | Pod 2_Member1 | 2026-06-10 | 3 | 0 | 13 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 3 | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 3
70 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 17 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 21 |  | 3
71 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 18 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 3 | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 3
72 | LMU | Complete ASP | Yes | 0 | 2026-05-15 | page_16 | Pod 4 | Pod 4_Member3 | 2026-05-15 | 3 | 0 | 16 | 2026-05-19 | 2026-05-19 | 2026-05-19 | Completed | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 23 |  | 3
73 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-05 | 3 | 0 | 20 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 3 | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 3
74 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-05 | 3 | 0 | 21 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 30 |  | 3
75 | LMU | Complete ASP | Yes | 0 | 2026-05-20 | page_19 | Pod 4 | Pod 4_Member3 | 2026-05-20 | 3 | 0 | 19 | 2026-05-22 | 2026-05-22 | 2026-05-22 |  | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 3 | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 34 |  | 3
76 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-10 | 3 | 0 | 23 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 27 |  | 3
77 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-10 | 3 | 0 | 24 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 3 | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 3
78 | LMU | Complete ASP | Yes | 0 | 2026-05-25 | page_22 | Pod 4 | Pod 4_Member3 | 2026-05-25 | 3 | 0 | 22 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  | 1 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 29 | #VALUE! | 3 |  |  | #VALUE!
79 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_25 | Pod 2 | Pod 2_Member3 | 2026-06-15 | 3 | 0 | 25 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  | 1 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 1 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 6
80 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_26 | Pod 2 | Pod 2_Member2 | 2026-06-15 | 3 | 0 | 26 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  | 1 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 3 | 2026-07-10 | 1 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 6
81 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_1 | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Completed | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 |  | 3
82 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Completed | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 | #VALUE! | 3 |  |  | #VALUE!
83 | Location | Complete ASP | Yes | 0 | 2026-04-29 | page_3 | Pod 3 | Pod 3_Member2 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 | Completed | 1 | 2026-05-05 | 1 | 2026-05-06 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 1 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 |  | 2026-05-14 | 0 | 2026-05-14 | 0 | 2026-05-14 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 24 |  | 3
84 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-08 | 3 | 0 | 4 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Completed | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
85 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_5 | Pod 3 | Pod 3_Member1 | 2026-05-08 | 3 | 0 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Completed | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
86 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_6 | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 |  | 2026-05-19 | 0 | 2026-05-19 | 0 | 2026-05-19 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 21 |  | 3
87 | Location | Complete ASP | Yes | 0 | 2026-05-13 | page_7 | Pod 3 | Pod 3_Member3 | 2026-05-13 | 3 | 0 | 7 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 27 |  | 3
88 | Location | Complete ASP | Yes | 0 | 2026-05-13 | page_8 | Pod 3 | Pod 3_Member1 | 2026-05-13 | 3 | 0 | 8 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 27 |  | 3
89 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_9 | Pod 3 | Pod 3_Member2 | 2026-05-08 | 3 | 0 | 9 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 30 |  | 3
90 | Location | Complete ASP | Yes | 0 | 2026-05-18 | page_10 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 10 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 22 |  | 3
91 | Location | Complete ASP | Yes | 0 | 2026-05-18 | page_11 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 11 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 3
92 | Log | Complete ASP | Yes | 0 | 2026-05-28 | page_1 | Pod 4 | Pod 4_Member3 | 2026-05-28 | 3 | 0 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 |  | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 22 | #VALUE! | 3 |  |  | #VALUE!
93 | Log | Complete ASP | Yes | 0 | 2026-05-15 | page_2 | Pod 4 | Pod 4_Member2 | 2026-05-15 | 3 | 0 | 2 | 2026-05-19 | 2026-05-19 | 2026-05-19 |  | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 23 |  | 3
94 | Log | Complete ASP | Yes | 0 | 2026-06-18 | page_3 | Pod 2 | Pod 2_Member3 | 2026-06-18 | 3 | 0 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 |  | 1 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 3
95 | Log | Complete ASP | Yes | 0 | 2026-06-04 | page_4 | Pod 4 | Pod 4_Member3 | 2026-06-04 | 3 | 0 | 4 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  | 1 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 2 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 3
96 | Log | Complete ASP | Yes | 0 | 2026-05-20 | page_5 | Pod 4 | Pod 4_Member2 | 2026-05-20 | 3 | 0 | 5 | 2026-05-22 | 2026-05-22 | 2026-05-22 |  | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 1 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 |  | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 34 |  | 3
97 | Log | Complete ASP | Yes | 0 | 2026-06-23 | page_6 | Pod 2 | Pod 2_Member3 | 2026-06-23 | 3 | 0 | 6 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 1 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 |  | 2026-07-09 | 0 | 2026-07-09 | 0 | 2026-07-09 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 28 |  | 3
98 | Log | Complete ASP | Yes | 0 | 2026-05-15 | page_7 | Pod 4 | Pod 4_Member1 | 2026-05-15 | 3 | 0 | 7 | 2026-05-19 | 2026-05-19 | 2026-05-19 |  | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 23 |  | 3
99 | Log | Complete ASP | Yes | 0 | 2026-05-21 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-21 | 3 | 0 | 8 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
100 | Log | Complete ASP | Yes | 0 | 2026-05-13 | page_9 | Pod 1 | Pod 1_Member3 | 2026-05-13 | 3 | 0 | 9 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 27 |  | 3
101 | Log | Complete ASP | Yes | 0 | 2026-05-21 | page_10 | Pod 3 | Pod 3_Member1 | 2026-05-21 | 3 | 0 | 10 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 3 | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 | #VALUE! | 3 |  |  | #VALUE!
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-19 | page_5 | Pod 3 | Pod 3_Member2 | 2026-06-19 | 3 | 0 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 |  | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 1 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 30 |  | 3
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member1 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  | 1 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 17 |  | 3
103 | OrderAware | React/ASP | Yes | 0 | 2026-06-19 | page_6 | Pod 3 | Pod 3_Member3 | 2026-06-19 | 3 | 0 | 2 | 2026-06-23 | 2026-06-23 | 2026-06-23 |  | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 1 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 30 |  | 3
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member2 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  | 1 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 17 |  | 3
104 | OrderAware | React/ASP | Yes | 0 | 2026-05-26 | page_7 | Pod 3 | Pod 3_Member1 | 2026-05-26 | 3 | 0 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  | 1 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 27 |  | 3
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member3 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  | 1 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 17 |  | 3
105 | OrderAware | React/ASP | Yes | 0 | 2026-06-24 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-24 | 3 | 0 | 4 | 2026-06-29 | 2026-06-29 | 2026-06-29 |  | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 3 | 2026-07-21 | 0 | 2026-07-21 | 0 | 2026-07-21 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 38 |  | 3
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member4 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  | 1 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 17 |  | 3
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-08 | page_5 | Pod UI | Pod UI_Integration | 2026-06-08 | 5 | 0 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 27 |  | 3
106 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-26 | page_1 | Pod 1 | Pod 1_Member2 | 2026-05-28 | 3 | 0 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 |  | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 22 |  | 3
107 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-19 | page_2 | Pod 1 | Pod 1_Member3 | 2026-05-21 | 3 | 0 | 2 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 31 |  | 3
108 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-20 | page_3 | Pod 4 | Pod 4_Member1 | 2026-05-22 | 3 | 0 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 |  | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 3
109 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-04 | page_4 | Pod 1 | Pod 1_Member2 | 2026-06-08 | 3 | 0 | 4 | 2026-06-10 | 2026-06-10 | 2026-06-10 |  | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 1 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 29 |  | 3
110 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-26 | page_5 | Pod 1 | Pod 1_Member3 | 2026-05-28 | 3 | 0 | 5 | 2026-06-03 | 2026-06-03 | 2026-06-03 |  | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 22 |  | 3
111 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-27 | page_6 | Pod 4 | Pod 4_Member1 | 2026-05-29 | 3 | 0 | 6 | 2026-06-03 | 2026-06-03 | 2026-06-03 |  | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 22 | #VALUE! | 3 |  |  | #VALUE!
112 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-11 | page_7 | Pod 1 | Pod 1_Member2 | 2026-06-15 | 3 | 0 | 7 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  | 1 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 3 | 2026-07-10 | 0 | 2026-07-10 | 0 | 2026-07-10 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 3
113 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-04 | page_1 | Pod 1 | Pod 1_Member3 | 2026-06-08 | 3 | 0 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 |  | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 1 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 29 |  | 3
114 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-04 | page_2 | Pod 4 | Pod 4_Member1 | 2026-06-08 | 3 | 0 | 2 | 2026-06-10 | 2026-06-10 | 2026-06-10 |  | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 1 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 29 |  | 3
115 | Reg+Attendance | Complete ASP | No | 2 | 2026-05-25 | page_3 | Pod 4 | Pod 4_Member2 | 2026-05-27 | 3 | 0 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 |  | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 24 |  | 3
116 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-11 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-15 | 3 | 0 | 4 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  | 1 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 1 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 22 | #VALUE! | 3 |  |  | #VALUE!
117 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-11 | page_5 | Pod 4 | Pod 4_Member1 | 2026-06-15 | 3 | 0 | 5 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  | 1 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 3 | 2026-07-10 | 3 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 50 | #VALUE! | 6 |  |  | #VALUE!
118 | Reports | Complete ASP | No | 2 | 2026-06-02 | page_1 | Pod 4 | Pod 4_Member2 | 2026-06-04 | 3 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  | 1 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 17 |  | 3
119 | Reports | Complete ASP | No | 2 | 2026-06-18 | page_2 | Pod 1 | Pod 1_Member3 | 2026-06-22 | 3 | 0 | 2 | 2026-06-24 | 2026-06-24 | 2026-06-24 |  | 1 | 2026-06-25 | 1 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 1 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 2 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 |  | 2026-07-10 | 3 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 43 |  | 6
120 | Reports | Complete ASP | No | 2 | 2026-06-18 | page_3 | Pod 4 | Pod 4_Member1 | 2026-06-22 | 3 | 0 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-24 |  | 1 | 2026-06-25 | 1 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 1 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 |  | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 29 |  | 3
121 | Reports | Complete ASP | No | 2 | 2026-06-25 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-29 | 3 | 0 | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  | 1 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 22 | #VALUE! | 3 |  |  | #VALUE!
122 | Reports | Complete ASP | No | 2 | 2026-06-09 | page_5 | Pod 4 | Pod 4_Member2 | 2026-06-11 | 3 | 0 | 5 | 2026-06-15 | 2026-06-15 | 2026-06-15 |  | 1 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1 | 2026-06-25 | 1 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 38 |  | 3
123 | Webuser | Complete ASP | No | 2 | 2026-04-29 | page_1 | Pod 3 | Pod 3_Member2 | 2026-05-01 | 3 | 0 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 1 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 22 |  | 3
124 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_2 | Pod 3 | Pod 3_Member3 | 2026-05-11 | 3 | 0 | 2 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 29 | #VALUE! | 3
125 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_3 | Pod 3 | Pod 3_Member1 | 2026-05-11 | 3 | 0 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 29 | #VALUE! | 3
126 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_4 | Pod 3 | Pod 3_Member2 | 2026-05-11 | 3 | 0 | 4 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  | 1 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 1 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 |  | 2026-05-25 | 0 | 2026-05-25 | 0 | 2026-05-25 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 29 |  | 3
127 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_5 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 5 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 22 | #VALUE! | 3
128 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_1 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 6 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 22 | #VALUE! | 3
129 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_2 | Pod 3 | Pod 3_Member2 | 2026-05-18 | 3 |  | 7 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  | 1 | 2026-05-21 | 1 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04
130 | Webuser | Complete ASP | No | 2 | 2026-05-21 | page_3 | Pod 3 | Pod 3_Member3 | 2026-05-25 | 3 |  | 8 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  | 1 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18
131 | Webuser | Complete ASP | No | 2 | 2026-06-01 | page_4 | Pod 3 | Pod 3_Member1 | 2026-06-03 | 3 |  | 9 | 2026-06-05 | 2026-06-05 | 2026-06-05 |  | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18
132 | Webuser | Complete ASP | No | 2 | 2026-05-21 | page_5 | Pod 3 | Pod 3_Member2 | 2026-05-25 | 3 |  | 10 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  | 1 | 2026-05-29 | 1 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 3 | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02
133 | Gradebook | Complete ASP | No | 2 | 2026-06-08 | page_6 | Pod 3 | Pod 3_Member1 | 2026-06-10 | 3 |  | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
134 | Gradebook | Complete ASP | No | 2 | 2026-06-15 | page_7 | Pod 3 | Pod 3_Member1 | 2026-06-17 | 3 |  | 2 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
135 | Gradebook | Complete ASP | No | 2 | 2026-05-28 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 |  | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25
136 | Gradebook | React/ASP | No | 2 | 2026-06-05 | page_9 | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 |  | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 |  | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 |  | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member1 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
137 | Gradebook | React/ASP | No | 2 | 2026-05-28 | page_10 | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 |  | 5 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  | 1 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member2 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
138 | Gradebook | React/ASP | No | 2 | 2026-06-05 | page_11 | Pod 3 | Pod 3_Member3 | 2026-06-09 | 3 |  | 6 | 2026-06-11 | 2026-06-11 | 2026-06-11 |  | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 |  | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member3 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
139 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_12 | Pod 3 | Pod 3_Member1 | 2026-06-24 | 3 |  | 7 | 2026-06-29 | 2026-06-29 | 2026-06-29 |  | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 1 | 2026-07-06 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 |  | 2026-07-10 | 0 | 2026-07-10 | 0 | 2026-07-10 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member4 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
140 | Gradebook | React/ASP | No | 2 | 2026-06-12 | page_13 | Pod 3 | Pod 3_Member2 | 2026-06-16 | 3 |  | 8 | 2026-06-18 | 2026-06-18 | 2026-06-18 |  | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 1 | 2026-06-25 | 1 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_9 | Pod UI | Pod UI_UI-Member1 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  | 1 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
141 | Gradebook | React/ASP | No | 2 | 2026-06-12 | page_14 | Pod 3 | Pod 3_Member3 | 2026-06-16 | 3 |  | 9 | 2026-06-18 | 2026-06-18 | 2026-06-18 |  | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 1 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 3 | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_9 | Pod UI | Pod UI_UI-Member2 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  | 1 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 0 | 2026-06-23 | page_9 | Pod UI | Pod UI_Integration | 2026-06-23 | 5 |  | 4 | 2026-06-30 | 2026-06-30 | 2026-06-30 |  | 1 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 |  | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
Formulas:
Start Date = [Module Target Start (Input)]
Start Date = WORKDAY([Module Target Start (Input)],[Buffer In case of no KT])
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Code Freeze Date = [TCR Bugs Closure Date]
TEST Deployment = [Code Freeze Date]
Pearson Regression Testing/UAT Date = WORKDAY([TEST Deployment], 1, IndHolidays)
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&(MAX([PR Response receive Date],[TCR Bugs Closure Date])))
Code freeze date = Release cutoff Date = WORKDAY([Release Date (2-Wk Cycle)], -5)
Release Request Approved Date = WORKDAY([Release #], 2, IndHolidays)
Release Date (2-Wk Cycle) = VLOOKUP([Release #],ReleaseTimeline!$B2:C27,2,FALSE)
Module Target Start (Input) = WORKDAY([PR raised date, row above],1)

## Current scenario(PR-5)-5-11
No. | Module | Target page Technology | Recieved Functional & Non Fuctional Walkthrough | Buffer In case of no KT | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | Status | Remarks | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Code Freeze Date | TEST Deployment | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | Code freeze date = Release cutoff Date | Release # | Release Request Approved Date | Release Date (2-Wk Cycle) | Code freeze date = Release cutoff Date | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
1 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed |  | 5 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | #VALUE! | 41 |  | 11
2 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_2 | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed |  | 5 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 11
3 | AddressBook | Complete ASP | Yes | 0 | 2026-04-15 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | Completed |  | 5 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 11
4 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | page_4 | Pod 1 | Pod 1_Member1 | 2026-04-20 | 3 | 0 | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  | 5 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 2 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 11
5 | AddressBook | Complete ASP | Yes | 0 | 2026-04-20 | page_5 | Pod 1 | Pod 1_Member2 | 2026-04-20 | 3 | 0 | 5 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  | 5 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 3 | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 50 | #VALUE! | 11 |  |  | #VALUE!
6 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_1 | Pod 3 | Mizan | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  | Havent Received KT and pearson team is working to schedule | 5 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 11
7 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_2 | Pod 3 | Swarneem | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  | 5 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 11
8 | Assessments | Complete ASP | Yes | 0 | 2026-04-15 | page_3 | Pod 3 | Prem | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  | 5 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 |  | 2026-05-04 | 2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 |  | 2026-05-13 | 0 | 2026-05-13 | 0 | 2026-05-13 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 11
9 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_4 | Pod 3 | Mizan | 2026-04-20 | 3 | 0 | 4 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  | 5 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 2 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 11
10 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_5 | Pod 3 | Swarneem | 2026-04-20 | 3 | 0 | 5 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  | 5 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 2 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 11
11 | Assessments | Complete ASP | Yes | 0 | 2026-04-20 | page_6 | Pod 3 | Prem | 2026-04-20 | 3 | 0 | 6 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  | 5 | 2026-04-29 | 1.5 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-07 |  | 2026-05-07 | 2 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 |  | 2026-05-18 | 0 | 2026-05-18 | 0 | 2026-05-18 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 36 |  | 11
12 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_7 | Pod 3 | Mizan | 2026-04-24 | 3 | 0 | 7 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  | 5 | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 11
13 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_8 | Pod 3 | Swarneem | 2026-04-24 | 3 | 0 | 8 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  | 5 | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 | #VALUE! | 11 |  |  | #VALUE!
14 | Assessments | Complete ASP | Yes | 0 | 2026-04-24 | page_9 | Pod 3 | Prem | 2026-04-24 | 3 | 0 | 9 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  | 5 | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 11
15 | Assessments | Complete ASP | Yes | 0 | 2026-04-29 | page_10 | Pod 3 | Mizan | 2026-04-29 | 3 | 0 | 10 | 2026-05-04 | 2026-05-04 | 2026-05-04 |  |  | 5 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 3 | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 52 |  | 11
16 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-28 | 3 | 0 | 1 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  |  | 5 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 42 |  | 11
17 | AssetAware | Complete ASP | No | 2 | 2026-04-24 | page_2 | Pod 3 | Pod 1_Member2 | 2026-04-28 | 3 | 0 | 2 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  |  | 5 | 2026-05-08 | 1.5 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 |  | 2026-05-26 | 0 | 2026-05-26 | 0 | 2026-05-26 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 42 |  | 11
18 | AssetAware | Complete ASP | No | 2 | 2026-04-20 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-22 | 3 | 0 | 3 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  | 5 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 34 |  | 11
19 | AssetAware | Complete ASP | No | 2 | 2026-05-01 | page_4 | Pod 1 | Pod 1_Member1 | 2026-05-05 | 3 | 0 | 4 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 5 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 49 |  | 11
20 | Communication | Complete ASP | No | 2 | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-07 | 3 | 0 | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 |  |  | 5 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 |  | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 45 |  | 11
21 | Communication | Complete ASP | No | 2 | 2026-04-29 | page_2 | Pod 2 | Pod 2_Member2 | 2026-05-01 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 5 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 2 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 11
22 | Communication | Complete ASP | No | 2 | 2026-04-29 | page_3 | Pod 2 | Pod 2_Member3 | 2026-05-01 | 3 | 0 | 3 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 5 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 2 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 11
23 | Communication | Complete ASP | No | 2 | 2026-05-12 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  |  | 5 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 3 | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 52 | #VALUE! | 11 |  |  | #VALUE!
24 | Content | Complete ASP | No | 2 | 2026-04-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-17 | 3 | 0 | 1 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  | 5 | 2026-04-28 | 1.5 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 |  | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 |  | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 |  | 2026-05-15 | 0 | 2026-05-15 | 0 | 2026-05-15 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 37 |  | 11
25 | Content | Complete ASP | No | 2 | 2026-04-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-17 | 3 | 0 | 2 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  | 5 | 2026-04-28 | 1.5 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 |  | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 |  | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 |  | 2026-05-15 | 0 | 2026-05-15 | 0 | 2026-05-15 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 37 |  | 11
26 | Content | Complete ASP | No | 2 | 2026-04-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-17 | 3 | 0 | 3 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  | 5 | 2026-04-28 | 1.5 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 |  | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 |  | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 |  | 2026-05-15 | 0 | 2026-05-15 | 0 | 2026-05-15 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 37 |  | 11
27 | Content | Complete ASP | No | 2 | 2026-04-22 | page_4 | Pod 3 | Pod 3_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  | 5 | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 3 | 2026-06-04 | 0 | 2026-06-04 | 0 | 2026-06-04 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 11
28 | Enrollment | Complete ASP | No | 2 | 2026-04-27 | page_1 | Pod 1 | Pod 1_Member3 | 2026-04-29 | 3 | 0 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 |  |  | 5 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 11
29 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member1 | 2026-05-12 | 3 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 |  |  | 5 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 11
30 | Enrollment | Complete ASP | No | 2 | 2026-05-01 | page_3 | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 5 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 11
31 | Enrollment | Complete ASP | No | 2 | 2026-05-05 | page_4 | Pod 1 | Pod 1_Member3 | 2026-05-07 | 3 | 0 | 4 | 2026-05-11 | 2026-05-11 | 2026-05-11 |  |  | 5 | 2026-05-18 | 1.5 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 |  | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 |  | 2026-06-05 | 0 | 2026-06-05 | 0 | 2026-06-05 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 45 |  | 11
32 | Enrollment | Complete ASP | No | 2 | 2026-05-15 | page_5 | Pod 1 | Pod 1_Member1 | 2026-05-19 | 3 | 0 | 5 | 2026-05-21 | 2026-05-21 | 2026-05-21 |  |  | 5 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 35 |  | 11
33 | Enrollment | Complete ASP | No | 2 | 2026-05-08 | page_6 | Pod 1 | Pod 1_Member2 | 2026-05-12 | 3 | 0 | 6 | 2026-05-14 | 2026-05-14 | 2026-05-14 |  |  | 5 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 |  | 11
34 | Enrollment | Complete ASP | No | 2 | 2026-05-12 | page_7 | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 7 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  |  | 5 | 2026-05-25 | 1.5 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 |  | 2026-06-03 | 2 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 |  | 2026-06-12 | 0 | 2026-06-12 | 0 | 2026-06-12 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 11
35 | Enrollment | Complete ASP | No | 2 | 2026-05-22 | page_8 | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 0 | 8 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 5 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 3 | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 55 |  | 11
36 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | page_1 | Pod 1 | Pod 1_Member1 | 2026-05-18 | 3 | 0 | 1 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 5 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 11
37 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | page_2 | Pod 1 | Pod 1_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 5 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 |  | 11
38 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-05 | page_3 | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 5 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 11
39 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-21 | page_4 | Pod 1 | Pod 1_Member1 | 2026-05-21 | 3 | 0 | 4 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 5 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 |  | 11
40 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-13 | page_5 | Pod 1 | Pod 1_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 5 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 11
41 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-08 | page_6 | Pod 1 | Pod 1_Member3 | 2026-05-08 | 3 | 0 | 6 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 5 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 |  | 11
42 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-26 | page_7 | Pod 1 | Pod 1_Member1 | 2026-05-26 | 3 | 0 | 7 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 5 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 11
43 | ExtendedField | Complete ASP | Yes | 0 | 2026-05-18 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 5 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 3 | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 11
44 | GradeBook | Complete ASP | Yes | 0 | 2026-05-13 | page_3 | Pod 2 | Pod 2_Member1 | 2026-05-13 | 3 | 0 | 1 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 5 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 3 | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 55 |  | 11
45 | GradeBook | Complete ASP | Yes | 0 | 2026-05-05 | page_4 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 5 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 3 | 2026-06-12 | 1 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 49 |  | 14
46 | Home | Complete ASP | No | 2 | 2026-04-22 | page_1 | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  | 5 | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 11
47 | Home | Complete ASP | No | 2 | 2026-04-29 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-01 | 3 | 0 | 2 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 5 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 2 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 11
48 | Home | Complete ASP | No | 2 | 2026-04-22 | page_3 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  | 5 | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 11
49 | Home | Complete ASP | No | 2 | 2026-04-29 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-01 | 3 | 0 | 4 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 5 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 3 | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 50 | #VALUE! | 11 |  |  | #VALUE!
50 | IssueAware | Complete ASP | Yes | 0 | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 5 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 11
51 | IssueAware | Complete ASP | Yes | 0 | 2026-05-18 | page_2 | Pod 2 | Pod 2_Member1 | 2026-05-18 | 3 | 0 | 2 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 5 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 3 | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 11
52 | Library | Complete ASP | Yes | 0 | 2026-04-29 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-29 | 3 | 0 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 |  |  | 5 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 11
53 | Library | Complete ASP | Yes | 0 | 2026-04-24 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  | 5 | 2026-05-06 | 1.5 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 |  | 2026-05-13 | 2 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 |  | 2026-05-22 | 0 | 2026-05-22 | 0 | 2026-05-22 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 11
54 | Library | Complete ASP | Yes | 0 | 2026-04-29 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 |  |  | 5 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 3 | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 52 |  | 11
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_2 | Pod 2 | Pod 2_Member2 | 2026-05-08 | 3 | 0 | 2 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 5 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 3 | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 |  | 11
55 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_2 | Pod UI | Pod UI_UI-Member1 | 2026-05-08 | 5 | 0 | 2 | 2026-05-14 | 2026-05-14 | 2026-05-14 |  |  | 5 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 3 | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 56 |  | 11
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod 2 | Pod 2_Member3 | 2026-05-08 | 3 | 0 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 5 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 | #VALUE! | 11
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod UI | Pod UI_UI-Member2 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 |  |  | 5 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 | #VALUE! | 11
57 | LMU | React/ASP | Yes | 0 | 2026-05-21 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-21 | 3 | 0 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 5 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 3 | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 |  | 11
56 | LMU | React/ASP | Yes | 0 | 2026-05-08 | page_3 | Pod UI | Pod UI_UI-Member3 | 2026-05-08 | 5 | 0 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 |  |  | 5 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 42 | #VALUE! | 11
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod 2 | Pod 2_Member2 | 2026-05-13 | 3 | 0 | 5 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 5 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 11
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod UI | Pod UI_UI-Member4 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 |  |  | 5 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 11
59 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_6 | Pod 2 | Pod 2_Member3 | 2026-05-13 | 3 | 0 | 6 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 5 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 3 | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 55 | #VALUE! | 11 |  |  | #VALUE!
58 | LMU | React/ASP | Yes | 0 | 2026-05-13 | page_5 | Pod UI | Pod UI_UI-Member5 | 2026-05-13 | 5 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 |  |  | 5 | 2026-05-26 | 1.5 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 |  | 2026-06-04 | 2 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 0 | 2026-06-15 | 0 | 2026-06-15 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 11
58 | LMU | React/ASP | Yes | 0 | 2026-05-20 | page_5 | Pod UI | Pod UI_Integration | 2026-05-20 | 5 | 0 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-26 |  |  | 5 | 2026-06-04 | 1.5 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 |  | 2026-06-11 | 2 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 |  | 2026-06-22 | 0 | 2026-06-22 | 0 | 2026-06-22 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 44 |  | 11
60 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-26 | 3 | 0 | 4 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 5 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 11
61 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-18 | 3 | 0 | 8 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 5 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 3 | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 11
62 | LMU | Complete ASP | Yes | 0 | 2026-05-18 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-18 | 3 | 0 | 9 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 5 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 11
63 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_7 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 5 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 3 | 2026-07-10 | 0 | 2026-07-10 | 0 | 2026-07-10 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 49 |  | 11
64 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-21 | 3 | 0 | 11 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 5 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 |  | 11
65 | LMU | Complete ASP | Yes | 0 | 2026-05-21 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-21 | 3 | 0 | 12 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 5 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 3 | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 |  | 11
66 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_10 | Pod 2 | Pod 2_Member1 | 2026-06-05 | 3 | 0 | 10 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 5 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 44 |  | 11
67 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_14 | Pod 2 | Pod 2_Member2 | 2026-05-26 | 3 | 0 | 14 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 5 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 3 | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 55 | #VALUE! | 11 |  |  | #VALUE!
68 | LMU | Complete ASP | Yes | 0 | 2026-05-26 | page_15 | Pod 2 | Pod 2_Member3 | 2026-05-26 | 3 | 0 | 15 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 5 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 11
69 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_13 | Pod 2 | Pod 2_Member1 | 2026-06-10 | 3 | 0 | 13 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 5 | 2026-06-19 | 1.5 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 3 | 2026-07-20 | 0 | 2026-07-20 | 0 | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 55 |  | 11
70 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 17 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 5 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 11
71 | LMU | Complete ASP | Yes | 0 | 2026-06-01 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 18 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 5 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 3 | 2026-07-10 | 0 | 2026-07-10 | 0 | 2026-07-10 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 49 |  | 11
72 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_16 | Pod 2 | Pod 2_Member1 | 2026-06-15 | 3 | 0 | 16 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 5 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 |  | 11
73 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-05 | 3 | 0 | 20 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 5 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 3 | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 44 |  | 11
74 | LMU | Complete ASP | Yes | 0 | 2026-06-05 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-05 | 3 | 0 | 21 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 5 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 44 |  | 11
75 | LMU | Complete ASP | Yes | 0 | 2026-06-18 | page_19 | Pod 2 | Pod 2_Member1 | 2026-06-18 | 3 | 0 | 19 | 2026-06-22 | 2026-06-22 | 2026-06-22 |  |  | 5 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 3 | 2026-07-30 | 0 | 2026-07-30 | 0 | 2026-07-30 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 45 |  | 11
76 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-10 | 3 | 0 | 23 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 5 | 2026-06-19 | 1.5 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 |  | 2026-07-09 | 0 | 2026-07-09 | 0 | 2026-07-09 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 11
77 | LMU | Complete ASP | Yes | 0 | 2026-06-10 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-10 | 3 | 0 | 24 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 5 | 2026-06-19 | 1.5 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 3 | 2026-07-20 | 0 | 2026-07-20 | 0 | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 55 |  | 11
78 | LMU | Complete ASP | Yes | 0 | 2026-06-23 | page_22 | Pod 2 | Pod 2_Member1 | 2026-06-23 | 3 | 0 | 22 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 5 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 |  | 2026-07-23 | 2026-07-23 | 2026-07-23 | 2026-07-24 |  | 2026-07-24 | 0 | 2026-07-24 | 0 | 2026-07-24 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 42 | #VALUE! | 11 |  |  | #VALUE!
79 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_25 | Pod 2 | Pod 2_Member3 | 2026-06-15 | 3 | 0 | 25 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 5 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 1 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 50 |  | 14
80 | LMU | Complete ASP | Yes | 0 | 2026-06-15 | page_26 | Pod 2 | Pod 2_Member2 | 2026-06-15 | 3 | 0 | 26 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 5 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 2 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 3 | 2026-07-23 | 1 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 50 |  | 14
81 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_1 | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 5 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 11
82 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 5 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 | #VALUE! | 11 |  |  | #VALUE!
83 | Location | Complete ASP | Yes | 0 | 2026-04-29 | page_3 | Pod 3 | Pod 3_Member2 | 2026-04-29 | 3 | 0 | 3 | 2026-05-04 | 2026-05-04 | 2026-05-04 |  |  | 5 | 2026-05-11 | 1.5 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 |  | 2026-05-18 | 2 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 |  | 2026-05-27 | 0 | 2026-05-27 | 0 | 2026-05-27 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 38 |  | 11
84 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-08 | 3 | 0 | 4 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 5 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 |  | 11
85 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_5 | Pod 3 | Pod 3_Member1 | 2026-05-08 | 3 | 0 | 5 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 5 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 |  | 11
86 | Location | Complete ASP | Yes | 0 | 2026-05-05 | page_6 | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 |  |  | 5 | 2026-05-14 | 1.5 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 |  | 2026-05-21 | 2 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 |  | 2026-06-03 | 0 | 2026-06-03 | 0 | 2026-06-03 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 11
87 | Location | Complete ASP | Yes | 0 | 2026-05-13 | page_7 | Pod 3 | Pod 3_Member3 | 2026-05-13 | 3 | 0 | 7 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 5 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 11
88 | Location | Complete ASP | Yes | 0 | 2026-05-13 | page_8 | Pod 3 | Pod 3_Member1 | 2026-05-13 | 3 | 0 | 8 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 5 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 11
89 | Location | Complete ASP | Yes | 0 | 2026-05-08 | page_9 | Pod 3 | Pod 3_Member2 | 2026-05-08 | 3 | 0 | 9 | 2026-05-12 | 2026-05-12 | 2026-05-12 |  |  | 5 | 2026-05-19 | 1.5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 |  | 2026-05-26 | 2 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 |  | 2026-06-08 | 0 | 2026-06-08 | 0 | 2026-06-08 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 44 |  | 11
90 | Location | Complete ASP | Yes | 0 | 2026-05-18 | page_10 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 10 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 5 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 |  | 11
91 | Location | Complete ASP | Yes | 0 | 2026-05-18 | page_11 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 11 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 5 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 3 | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 50 |  | 11
92 | Log | Complete ASP | Yes | 0 | 2026-06-26 | page_1 | Pod 2 | Pod 2_Member1 | 2026-06-26 | 3 | 0 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 5 | 2026-07-09 | 1.5 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 |  | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 |  | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 |  | 2026-07-27 | 0 | 2026-07-27 | 0 | 2026-07-27 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 36 | #VALUE! | 11 |  |  | #VALUE!
93 | Log | Complete ASP | Yes | 0 | 2026-06-18 | page_2 | Pod 2 | Pod 2_Member2 | 2026-06-18 | 3 | 0 | 2 | 2026-06-22 | 2026-06-22 | 2026-06-22 |  |  | 5 | 2026-06-30 | 1.5 | 2026-07-01 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 2 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 |  | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-17 |  | 2026-07-17 | 0 | 2026-07-17 | 0 | 2026-07-17 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 45 |  | 11
94 | Log | Complete ASP | Yes | 0 | 2026-06-18 | page_3 | Pod 2 | Pod 2_Member3 | 2026-06-18 | 3 | 0 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 |  |  | 5 | 2026-06-30 | 1.5 | 2026-07-01 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 2 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 |  | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-17 |  | 2026-07-17 | 0 | 2026-07-17 | 0 | 2026-07-17 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 45 |  | 11
95 | Log | Complete ASP | Yes | 0 | 2026-07-02 | page_4 | Pod 2 | Pod 2_Member1 | 2026-07-02 | 3 | 0 | 4 | 2026-07-06 | 2026-07-06 | 2026-07-06 |  |  | 5 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 |  | 2026-07-23 | 2 | 2026-07-27 | 3 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 2 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-05 |  | 2026-08-05 | 0 | 2026-08-05 | 0 | 2026-08-05 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 45 |  | 11
96 | Log | Complete ASP | Yes | 0 | 2026-06-23 | page_5 | Pod 2 | Pod 2_Member2 | 2026-06-23 | 3 | 0 | 5 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 5 | 2026-07-03 | 3 | 2026-07-09 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 |  | 2026-07-23 | 2026-07-23 | 2026-07-23 | 2026-07-24 |  | 2026-07-24 | 0 | 2026-07-24 | 0 | 2026-07-24 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 42 |  | 11
97 | Log | Complete ASP | Yes | 0 | 2026-06-23 | page_6 | Pod 2 | Pod 2_Member3 | 2026-06-23 | 3 | 0 | 6 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 5 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 42 |  | 11
98 | Log | Complete ASP | Yes | 0 | 2026-06-01 | page_7 | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 5 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 11
99 | Log | Complete ASP | Yes | 0 | 2026-05-21 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-21 | 3 | 0 | 8 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 5 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 |  | 11
100 | Log | Complete ASP | Yes | 0 | 2026-05-13 | page_9 | Pod 1 | Pod 1_Member3 | 2026-05-13 | 3 | 0 | 9 | 2026-05-15 | 2026-05-15 | 2026-05-15 |  |  | 5 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 41 |  | 11
101 | Log | Complete ASP | Yes | 0 | 2026-05-21 | page_10 | Pod 3 | Pod 3_Member1 | 2026-05-21 | 3 | 0 | 10 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 5 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 3 | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 | #VALUE! | 11 |  |  | #VALUE!
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 5 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 11
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member1 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 5 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 11
103 | OrderAware | React/ASP | Yes | 0 | 2026-06-05 | page_6 | Pod 3 | Pod 3_Member3 | 2026-06-05 | 3 | 0 | 2 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 5 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 44 |  | 11
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member2 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 5 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 11
104 | OrderAware | React/ASP | Yes | 0 | 2026-06-10 | page_7 | Pod 3 | Pod 3_Member1 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 5 | 2026-06-19 | 1.5 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 |  | 2026-07-09 | 0 | 2026-07-09 | 0 | 2026-07-09 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 11
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member3 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 5 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 11
105 | OrderAware | React/ASP | Yes | 0 | 2026-06-05 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-05 | 3 | 0 | 4 | 2026-06-09 | 2026-06-09 | 2026-06-09 |  |  | 5 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 3 | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 44 |  | 11
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-01 | page_5 | Pod UI | Pod UI_UI-Member4 | 2026-06-01 | 5 | 0 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 |  |  | 5 | 2026-06-15 | 1.5 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 |  | 2026-07-02 | 0 | 2026-07-02 | 0 | 2026-07-02 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 31 |  | 11
102 | OrderAware | React/ASP | Yes | 0 | 2026-06-08 | page_5 | Pod UI | Pod UI_Integration | 2026-06-08 | 5 | 0 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 5 | 2026-06-19 | 1.5 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 |  | 2026-07-09 | 0 | 2026-07-09 | 0 | 2026-07-09 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 11
106 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-15 | page_1 | Pod 1 | Pod 1_Member2 | 2026-05-19 | 3 | 0 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 |  |  | 5 | 2026-05-29 | 1.5 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 |  | 2026-06-17 | 0 | 2026-06-17 | 0 | 2026-06-17 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 35 |  | 11
107 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-19 | page_2 | Pod 1 | Pod 1_Member3 | 2026-05-21 | 3 | 0 | 2 | 2026-05-25 | 2026-05-25 | 2026-05-25 |  |  | 5 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 45 |  | 11
108 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-01 | page_3 | Pod 1 | Pod 1_Member1 | 2026-06-03 | 3 | 0 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 |  |  | 5 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 |  | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 |  | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 34 |  | 11
109 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-22 | page_4 | Pod 1 | Pod 1_Member2 | 2026-05-26 | 3 | 0 | 4 | 2026-05-29 | 2026-05-29 | 2026-05-29 |  |  | 5 | 2026-06-08 | 1.5 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 |  | 2026-06-24 | 0 | 2026-06-24 | 0 | 2026-06-24 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 41 |  | 11
110 | ProgressionPlan | Complete ASP | No | 2 | 2026-05-26 | page_5 | Pod 1 | Pod 1_Member3 | 2026-05-28 | 3 | 0 | 5 | 2026-06-03 | 2026-06-03 | 2026-06-03 |  |  | 5 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 |  | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 36 |  | 11
111 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-08 | page_6 | Pod 1 | Pod 1_Member1 | 2026-06-10 | 3 | 0 | 6 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 5 | 2026-06-19 | 1.5 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 |  | 2026-07-09 | 0 | 2026-07-09 | 0 | 2026-07-09 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 | #VALUE! | 11 |  |  | #VALUE!
112 | ProgressionPlan | Complete ASP | No | 2 | 2026-06-01 | page_7 | Pod 1 | Pod 1_Member2 | 2026-06-03 | 3 | 0 | 7 | 2026-06-05 | 2026-06-05 | 2026-06-05 |  |  | 5 | 2026-06-12 | 1.5 | 2026-06-15 | 2026-06-15 | 3 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 3 | 2026-07-13 | 0 | 2026-07-13 | 0 | 2026-07-13 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 48 |  | 11
113 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-04 | page_1 | Pod 1 | Pod 1_Member3 | 2026-06-08 | 3 | 0 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 |  |  | 5 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 43 |  | 11
114 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-15 | page_2 | Pod 1 | Pod 1_Member1 | 2026-06-17 | 3 | 0 | 2 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 5 | 2026-06-29 | 1.5 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 2 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 |  | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 11
115 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-08 | page_3 | Pod 1 | Pod 1_Member2 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 |  |  | 5 | 2026-06-19 | 1.5 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 |  | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 |  | 2026-07-09 | 0 | 2026-07-09 | 0 | 2026-07-09 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 11
116 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-11 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-15 | 3 | 0 | 4 | 2026-06-17 | 2026-06-17 | 2026-06-17 |  |  | 5 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 36 | #VALUE! | 11 |  |  | #VALUE!
117 | Reg+Attendance | Complete ASP | No | 2 | 2026-06-22 | page_5 | Pod 1 | Pod 1_Member1 | 2026-06-24 | 3 | 0 | 5 | 2026-06-29 | 2026-06-29 | 2026-06-29 |  |  | 5 | 2026-07-06 | 1.5 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 3 | 2026-08-03 | 3 | 2026-08-06 | 3 | 2026-08-11 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 52 | #VALUE! | 14 |  |  | #VALUE!
118 | Reports | Complete ASP | No | 2 | 2026-06-15 | page_1 | Pod 1 | Pod 1_Member2 | 2026-06-17 | 3 | 0 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 5 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 |  | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 |  | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 |  | 2026-07-20 | 0 | 2026-07-20 | 0 | 2026-07-20 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 48 |  | 11
119 | Reports | Complete ASP | No | 2 | 2026-06-18 | page_2 | Pod 1 | Pod 1_Member3 | 2026-06-22 | 3 | 0 | 2 | 2026-06-24 | 2026-06-24 | 2026-06-24 |  |  | 5 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2 | 2026-07-16 | 3 | 2026-07-21 | 2026-07-21 | 2026-07-22 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 |  | 2026-07-27 | 3 | 2026-07-30 | 3 | 2026-08-04 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 57 |  | 14
120 | Reports | Complete ASP | No | 2 | 2026-06-30 | page_3 | Pod 1 | Pod 1_Member1 | 2026-07-02 | 3 | 0 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-06 |  |  | 5 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 |  | 2026-07-23 | 2 | 2026-07-27 | 3 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 |  | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-08-03 |  | 2026-08-03 | 0 | 2026-08-03 | 0 | 2026-08-03 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 45 |  | 11
121 | Reports | Complete ASP | No | 2 | 2026-06-25 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-29 | 3 | 0 | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 5 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 36 | #VALUE! | 11 |  |  | #VALUE!
122 | Reports | Complete ASP | No | 2 | 2026-06-22 | page_5 | Pod 1 | Pod 1_Member2 | 2026-06-24 | 3 | 0 | 5 | 2026-06-29 | 2026-06-29 | 2026-06-29 |  |  | 5 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 | 3 | 2026-07-21 | 2 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 3 | 2026-08-05 | 0 | 2026-08-05 | 0 | 2026-08-05 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 52 |  | 11
123 | Webuser | Complete ASP | No | 2 | 2026-04-29 | page_1 | Pod 3 | Pod 3_Member2 | 2026-05-01 | 3 | 0 | 1 | 2026-05-06 | 2026-05-06 | 2026-05-06 |  |  | 5 | 2026-05-13 | 1.5 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 2026-05-20 | 2 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 |  | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 36 |  | 11
124 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_2 | Pod 3 | Pod 3_Member3 | 2026-05-11 | 3 | 0 | 2 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  |  | 5 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 43 | #VALUE! | 11
125 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_3 | Pod 3 | Pod 3_Member1 | 2026-05-11 | 3 | 0 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  |  | 5 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 43 | #VALUE! | 11
126 | Webuser | Complete ASP | No | 2 | 2026-05-07 | page_4 | Pod 3 | Pod 3_Member2 | 2026-05-11 | 3 | 0 | 4 | 2026-05-13 | 2026-05-13 | 2026-05-13 |  |  | 5 | 2026-05-20 | 1.5 | 2026-05-21 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2 | 2026-06-01 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 |  | 2026-06-09 | 0 | 2026-06-09 | 0 | 2026-06-09 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 43 |  | 11
127 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_5 | Pod 3 | Pod 3_Member3 | 2026-05-18 | 3 | 0 | 5 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 5 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 | #VALUE! | 11
128 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_1 | Pod 3 | Pod 3_Member1 | 2026-05-18 | 3 | 0 | 6 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 5 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 36 | #VALUE! | 11
129 | Webuser | Complete ASP | No | 2 | 2026-05-14 | page_2 | Pod 3 | Pod 3_Member2 | 2026-05-18 | 3 |  | 7 | 2026-05-20 | 2026-05-20 | 2026-05-20 |  |  | 5 | 2026-05-27 | 1.5 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 |  | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 |  | 2026-06-16 | 0 | 2026-06-16 | 0 | 2026-06-16 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18
130 | Webuser | Complete ASP | No | 2 | 2026-05-21 | page_3 | Pod 3 | Pod 3_Member3 | 2026-05-25 | 3 |  | 8 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  |  | 5 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 |  | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02
131 | Webuser | Complete ASP | No | 2 | 2026-05-21 | page_4 | Pod 3 | Pod 3_Member1 | 2026-05-25 | 3 |  | 9 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  |  | 5 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 |  | 2026-06-12 | 2 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 |  | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 |  | 2026-06-23 | 0 | 2026-06-23 | 0 | 2026-06-23 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02
132 | Webuser | Complete ASP | No | 2 | 2026-05-21 | page_5 | Pod 3 | Pod 3_Member2 | 2026-05-25 | 3 |  | 10 | 2026-05-27 | 2026-05-27 | 2026-05-27 |  |  | 5 | 2026-06-05 | 1.5 | 2026-06-08 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 3 | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16
133 | Gradebook | Complete ASP | No | 2 | 2026-05-28 | page_6 | Pod 3 | Pod 3_Member1 | 2026-06-01 | 3 |  | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 5 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
134 | Gradebook | Complete ASP | No | 2 | 2026-06-05 | page_7 | Pod 3 | Pod 3_Member1 | 2026-06-09 | 3 |  | 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 |  |  | 5 | 2026-06-18 | 1.5 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 2 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 |  | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
135 | Gradebook | Complete ASP | No | 2 | 2026-05-28 | page_8 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 |  | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 5 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-05 | page_9 | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 |  | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 |  |  | 5 | 2026-06-18 | 1.5 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 2 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 |  | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member1 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 5 | 2026-06-29 | 1.5 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 2 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 |  | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
137 | Gradebook | React/ASP | No | 2 | 2026-05-28 | page_10 | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 |  | 5 | 2026-06-04 | 2026-06-04 | 2026-06-04 |  |  | 5 | 2026-06-11 | 1.5 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 |  | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member2 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 5 | 2026-06-29 | 1.5 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 2 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 |  | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
138 | Gradebook | React/ASP | No | 2 | 2026-06-05 | page_11 | Pod 3 | Pod 3_Member3 | 2026-06-09 | 3 |  | 6 | 2026-06-11 | 2026-06-11 | 2026-06-11 |  |  | 5 | 2026-06-18 | 1.5 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 2 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 |  | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member3 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 5 | 2026-06-29 | 1.5 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 2 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 |  | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
139 | Gradebook | React/ASP | No | 2 | 2026-06-12 | page_12 | Pod 3 | Pod 3_Member1 | 2026-06-16 | 3 |  | 7 | 2026-06-18 | 2026-06-18 | 2026-06-18 |  |  | 5 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-11 | page_9 | Pod UI | Pod UI_UI-Member4 | 2026-06-15 | 5 |  | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 |  |  | 5 | 2026-06-29 | 1.5 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 |  | 2026-07-06 | 2 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 |  | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
140 | Gradebook | React/ASP | No | 2 | 2026-06-12 | page_13 | Pod 3 | Pod 3_Member2 | 2026-06-16 | 3 |  | 8 | 2026-06-18 | 2026-06-18 | 2026-06-18 |  |  | 5 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_9 | Pod UI | Pod UI_UI-Member1 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 5 | 2026-07-09 | 1.5 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 |  | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 |  | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 |  | 2026-07-27 | 0 | 2026-07-27 | 0 | 2026-07-27 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
141 | Gradebook | React/ASP | No | 2 | 2026-06-12 | page_14 | Pod 3 | Pod 3_Member3 | 2026-06-16 | 3 |  | 9 | 2026-06-18 | 2026-06-18 | 2026-06-18 |  |  | 5 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 3 | 2026-07-24 | 0 | 2026-07-24 | 0 | 2026-07-24 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
136 | Gradebook | React/ASP | No | 2 | 2026-06-22 | page_9 | Pod UI | Pod UI_UI-Member2 | 2026-06-24 | 5 |  | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 |  |  | 5 | 2026-07-09 | 1.5 | 2026-07-10 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 |  | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 |  | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-27 |  | 2026-07-27 | 0 | 2026-07-27 | 0 | 2026-07-27 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
136 | Gradebook | React/ASP | No | 0 | 2026-06-23 | page_9 | Pod UI | Pod UI_Integration | 2026-06-23 | 5 |  | 4 | 2026-06-30 | 2026-06-30 | 2026-06-30 |  |  | 5 | 2026-07-08 | 1.5 | 2026-07-09 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 |  | 2026-07-15 | 2 | 2026-07-17 | 3 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 |  | 2026-07-23 | 2026-07-23 | 2026-07-23 | 2026-07-24 |  | 2026-07-24 | 0 | 2026-07-24 | 0 | 2026-07-24 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06
Formulas:
Start Date = [Module Target Start (Input)]
Start Date = WORKDAY([Module Target Start (Input)],[Buffer In case of no KT])
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Code Freeze Date = [TCR Bugs Closure Date]
TEST Deployment = [Code Freeze Date]
Pearson Regression Testing/UAT Date = WORKDAY([TEST Deployment], 1, IndHolidays)
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&(MAX([PR Response receive Date],[TCR Bugs Closure Date])))
Code freeze date = Release cutoff Date = WORKDAY([Release Date (2-Wk Cycle)], -5)
Release Request Approved Date = WORKDAY([Release #], 2, IndHolidays)
Release Date (2-Wk Cycle) = VLOOKUP([Release #],ReleaseTimeline!$B2:C27,2,FALSE)
Module Target Start (Input) = WORKDAY([PR raised date, row above],1)

## Module Prioritization
Priority | Objective | Module | Purpose
🔴 P0 | Launch school (Day 1 readiness) | enrollment | Student course registration
🔴 P0 |  | registration.aspx.cs | Registration backend logic
🔴 P0 |  | webuser | User account management
🔴 P0 |  | security | Authentication & access control
🔴 P0 |  | content | Course materials delivery
🔴 P0 |  | Planner | Study planning & scheduling
🔴 P0 |  | timeline | Course activity tracking
🔴 P0 |  | Assessments | Exams, quizzes
🔴 P0 |  | gradebook | Marks & grading
🔴 P0 |  | communication | Basic notifications
🔴 P0 |  | home | Landing/dashboard
🟠 P1 | Stabilize operations | attendance | Track student attendance
🟠 P1 |  | progressionPlan | Learning path tracking
🟠 P1 |  | reports | Academic/admin reports
🟠 P1 |  | log | Audit & system logs
🟠 P1 |  | forum | Student discussions
🟠 P1 |  | addressBook | Contact directory
🟠 P1 |  | importStatus | Data import tracking
🟠 P1 |  | extendedField | Custom data fields
🟡 P2 | Scale & enhance | library | Resource repository
🟡 P2 |  | assetAware | Digital asset tracking
🟡 P2 |  | orderAware | Content/licensing management
🟡 P2 |  | external | Third-party integrations
🟡 P2 |  | location | Geo/location services
🟡 P2 |  | issueAware | Issue/complaint tracking
🟢 P3 | Optimize & customize | lmu | Institution-specific module
🟢 P3 |  | extendedField (advanced) | Advanced customization
🟢 P3 |  | reports (advanced) | Analytics & insights

## With 3 PODs-as of now (hidden)
No. | Module | Target page Technology | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | TEST Deployment | Release Request Raise Date | Release Request Approved Date | Release Date (2-Wk Cycle) | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
1 | IssueAware | Complete ASP | 2026-04-15 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 1 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 1 | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-15 | 2026-05-28 | 40 |  | 4
2 | IssueAware | Complete ASP | 2026-04-15 | page_2 | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 1 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 1 | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-15 | 2026-05-28 | 40 |  | 4
3 | GradeBook | React/ASP | 2026-04-15 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-25 | 2026-05-28 | 41 |  | 4
4 | GradeBook | React/ASP | 2026-04-24 | page_4 | Pod 1 | Pod 1_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-25 | 2026-05-28 | 30 |  | 4
5 | AddressBook | Complete ASP | 2026-04-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-25 | 2026-05-28 | 41 |  | 4
6 | AddressBook | Complete ASP | 2026-04-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-25 | 2026-05-28 | 41 |  | 4
7 | AddressBook | Complete ASP | 2026-04-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-25 | 2026-05-28 | 41 |  | 4
8 | AddressBook | Complete ASP | 2026-04-24 | page_4 | Pod 3 | Pod 3_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-25 | 2026-05-28 | 30 |  | 4
9 | Orderaware | React/ASP | 2026-04-24 | page_5 | Pod 1 | Pod 1_Member2 | 2026-04-24 | 3 | 0 | 5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-06-02 | 2026-06-11 | 44 |  | 4
10 | Orderaware | React/ASP | 2026-04-24 | page_6 | Pod 1 | Pod 1_Member3 | 2026-04-24 | 3 | 0 | 6 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-06-02 | 2026-06-11 | 44 |  | 4
11 | Orderaware | React/ASP | 2026-05-05 | page_7 | Pod 1 | Pod 1_Member1 | 2026-05-05 | 3 | 0 | 7 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-06-02 | 2026-06-11 | 35 |  | 4
12 | Orderaware | React/ASP | 2026-05-05 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 8 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-06-02 | 2026-06-11 | 35 | 14 | 4 |  |  | 18
13 | Orderaware | React/ASP | 2026-05-05 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 8 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-06-02 | 2026-06-11 | 35 | 14 | 4 |  |  | 18
14 | Orderaware
15 | Orderaware
16 | Orderaware | React/ASP | 2026-05-05 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 8 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-06-02 | 2026-06-11 | 35 | 14 | 4 |  |  | 18
17 | Orderaware | React/ASP | 2026-05-05 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 8 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 1 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-06-02 | 2026-06-11 | 35 | 14 | 4 |  |  | 18
18 | Enrollment | Complete ASP | 2026-05-14 | enrollment/placement/manager.aspx ¦ RadG | Pod 1 | Pod 1_Member1 | 2026-05-14 | 3 | 0 | 1 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 38 |  | 4
19 | Enrollment | Complete ASP | 2026-05-14 | enrollment/placement/rejectReason.aspx ¦ | Pod 1 | Pod 1_Member2 | 2026-05-14 | 3 | 0 | 2 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 38 |  | 4
20 | Enrollment | Complete ASP | 2026-05-05 | enrollment/placement/placementHelp.aspx | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 49 |  | 4
21 | Enrollment | Complete ASP | 2026-05-22 | enrollment/registration/default.aspx ¦ R | Pod 1 | Pod 1_Member1 | 2026-05-22 | 3 | 0 | 4 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-02 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 30 |  | 4
22 | Enrollment | Complete ASP | 2026-05-22 | enrollment/registration/registrationLoca | Pod 1 | Pod 1_Member2 | 2026-05-22 | 3 | 0 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-02 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 30 |  | 4
23 | Enrollment | Complete ASP | 2026-05-14 | enrollment/registration/registrationLoca | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 6 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 38 |  | 4
24 | Webuser | Complete ASP | 2026-05-05 | webuser/addressContact.aspx ¦ RadAjaxM | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 49 |  | 4
25 | Webuser | Complete ASP | 2026-05-05 | webuser/contactInformationHistory.aspx | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 49 |  | 4
26 | Webuser | Complete ASP | 2026-04-24 | webuser/dataview.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 58 |  | 4
27 | Webuser | Complete ASP | 2026-05-14 | webuser/dataviewList.aspx ¦ RadGrid, R | Pod 3 | Pod 3_Member1 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 38 |  | 4
28 | Webuser | Complete ASP | 2026-05-14 | webuser/expressEdit.aspx ¦ RadAjaxMana | Pod 3 | Pod 3_Member2 | 2026-05-14 | 3 | 0 | 5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 38 |  | 4
29 | Webuser | Complete ASP | 2026-05-05 | webuser/expressUserSelection.aspx ¦ Ra | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 49 |  | 4
30 | Webuser | Complete ASP | 2026-05-22 | webuser/webuserExtended.aspx ¦ RadGrid | Pod 3 | Pod 3_Member1 | 2026-05-22 | 3 | 0 | 7 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-02 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 30 |  | 4
31 | Webuser | Complete ASP | 2026-05-22 | webuser/webusers.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member2 | 2026-05-22 | 3 | 0 | 8 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-02 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-06-25 | 30 |  | 4
32 | LMU | React/ASP | 2026-04-15 | page_1 | Pod 2 | Pod 2_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 111 |  | 4
33 | LMU | React/ASP | 2026-04-15 | page_2 | Pod 2 | Pod 2_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 111 |  | 4
34 | LMU | React/ASP | 2026-04-15 | page_3 | Pod 2 | Pod 2_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 1 | 2026-04-21 | 1 | 2026-04-22 | 2026-04-22 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 1 | 2026-04-27 | 1 | 2026-04-28 | 1 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 111 |  | 4
35 | LMU | React/ASP | 2026-04-24 | page_4 | Pod 2 | Pod 2_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 100 |  | 4
36 | LMU | React/ASP | 2026-04-24 | page_5 | Pod 2 | Pod 2_Member2 | 2026-04-24 | 3 | 0 | 5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 100 |  | 4
37 | LMU | Complete ASP | 2026-04-24 | page_6 | Pod 2 | Pod 2_Member3 | 2026-04-24 | 3 | 0 | 6 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 1 | 2026-04-29 | 1 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 1 | 2026-05-06 | 1 | 2026-05-07 | 1 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 100 |  | 4
38 | LMU | Complete ASP | 2026-05-05 | page_7 | Pod 2 | Pod 2_Member1 | 2026-05-05 | 3 | 0 | 7 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 91 |  | 4
39 | LMU | Complete ASP | 2026-05-05 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 8 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 91 |  | 4
40 | LMU | Complete ASP | 2026-05-05 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 9 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 1 | 2026-05-08 | 1 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 1 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 91 |  | 4
41 | LMU | Complete ASP | 2026-05-14 | page_10 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 10 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 80 |  | 4
42 | LMU | Complete ASP | 2026-05-14 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-14 | 3 | 0 | 11 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 80 |  | 4
43 | LMU | Complete ASP | 2026-05-14 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-14 | 3 | 0 | 12 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 1 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 1 | 2026-05-26 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 80 |  | 4
44 | LMU | Complete ASP | 2026-05-22 | page_13 | Pod 2 | Pod 2_Member1 | 2026-05-22 | 3 | 0 | 13 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-02 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 72 |  | 4
45 | LMU | Complete ASP | 2026-05-22 | page_14 | Pod 2 | Pod 2_Member2 | 2026-05-22 | 3 | 0 | 14 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-02 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 72 |  | 4
46 | LMU | Complete ASP | 2026-05-22 | page_15 | Pod 2 | Pod 2_Member3 | 2026-05-22 | 3 | 0 | 15 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-02 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 72 |  | 4
47 | LMU | Complete ASP | 2026-06-01 | page_16 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 16 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 64 |  | 4
48 | LMU | Complete ASP | 2026-06-01 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 17 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 64 |  | 4
49 | LMU | Complete ASP | 2026-06-01 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 18 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 64 |  | 4
50 | LMU | Complete ASP | 2026-06-09 | page_19 | Pod 2 | Pod 2_Member1 | 2026-06-09 | 3 | 0 | 19 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 56 |  | 4
51 | LMU | Complete ASP | 2026-06-09 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-09 | 3 | 0 | 20 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 56 |  | 4
52 | LMU | Complete ASP | 2026-06-09 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-09 | 3 | 0 | 21 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 56 |  | 4
53 | LMU | Complete ASP | 2026-06-17 | page_22 | Pod 2 | Pod 2_Member1 | 2026-06-17 | 3 | 0 | 22 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-26 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 48 |  | 4
54 | LMU | Complete ASP | 2026-06-17 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-17 | 3 | 0 | 23 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-26 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 48 |  | 4
55 | LMU | Complete ASP | 2026-06-17 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-17 | 3 | 0 | 24 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-26 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 48 |  | 4
56 | LMU | Complete ASP | 2026-06-25 | page_25 | Pod 2 | Pod 2_Member1 | 2026-06-25 | 3 | 0 | 25 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 38 |  | 4
57 | LMU | Complete ASP | 2026-06-25 | page_26 | Pod 2 | Pod 2_Member2 | 2026-06-25 | 3 | 0 | 26 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 38 | 16 | 4 |  |  | 20
58 | ProgressionPlan | Complete ASP | 2026-06-09 | progressionPlan/progressionPlan.aspx ¦ RadGrid, RadAja | Pod 1 | Pod 1_Member1 | 2026-06-09 | 3 | 0 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 56 |  | 4
59 | ProgressionPlan | Complete ASP | 2026-06-09 | progressionPlan/academicRequirement.aspx ¦ RadGrid, Ra | Pod 1 | Pod 1_Member2 | 2026-06-09 | 3 | 0 | 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 56 |  | 4
60 | ProgressionPlan | Complete ASP | 2026-05-22 | progressionPlan/academicRequirements.aspx ¦ RadGrid, R | Pod 1 | Pod 1_Member3 | 2026-05-22 | 3 | 0 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-02 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 72 |  | 4
61 | ProgressionPlan | Complete ASP | 2026-06-17 | progressionPlan/completionRequirement.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member1 | 2026-06-17 | 3 | 0 | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-26 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 48 |  | 4
62 | ProgressionPlan | Complete ASP | 2026-06-17 | progressionPlan/completionRequirements.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member2 | 2026-06-17 | 3 | 0 | 5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-26 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 48 |  | 4
63 | ProgressionPlan | Complete ASP | 2026-06-01 | progressionPlan/webusers.aspx ¦ RadGrid, RadAjaxManage | Pod 1 | Pod 1_Member3 | 2026-06-01 | 3 | 0 | 6 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 64 |  | 4
64 | ProgressionPlan | Complete ASP | 2026-06-25 | progressionPlan/help/progressionPlansSelectorHelp.aspx | Pod 1 | Pod 1_Member1 | 2026-06-25 | 3 | 0 | 7 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-08-06 | 38 | 16 | 4
65 | Library | Complete ASP | 2026-07-03 | library/resource.aspx ¦ Ra | Pod 2 | Pod 2_Member1 | 2026-07-03 | 3 | 0 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 1 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-08-03 | 2026-08-06 | 28 |  | 4
66 | Library | Complete ASP | 2026-07-03 | library/searchResults.aspx | Pod 2 | Pod 2_Member2 | 2026-07-03 | 3 | 0 | 2 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 1 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-08-03 | 2026-08-06 | 28 |  | 4
67 | ExtendedField | Complete ASP | 2026-07-03 | extendedField/extendedField.aspx ¦ RadAjax | Pod 1 | Pod 1_Member1 | 2026-07-03 | 3 | 0 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 42 |  | 4
68 | ExtendedField | Complete ASP | 2026-06-25 | extendedField/default.aspx ¦ RadGrid, RadA | Pod 1 | Pod 1_Member2 | 2026-06-25 | 3 | 0 | 2 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 52 |  | 4
69 | ExtendedField | Complete ASP | 2026-06-09 | extendedField/associations.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member3 | 2026-06-09 | 3 | 0 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 70 |  | 4
70 | ExtendedField | Complete ASP | 2026-07-15 | extendedField/calculationGroupExtendedFiel | Pod 1 | Pod 1_Member1 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 34 |  | 4
71 | ExtendedField | Complete ASP | 2026-07-03 | extendedField/extendedFieldConfirmRecalcul | Pod 1 | Pod 1_Member2 | 2026-07-03 | 3 | 0 | 5 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 42 |  | 4
72 | ExtendedField | Complete ASP | 2026-06-17 | extendedField/fieldHistory.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member3 | 2026-06-17 | 3 | 0 | 6 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-26 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 62 |  | 4
73 | ExtendedField | Complete ASP | 2026-07-15 | extendedField/dataview/dataview.aspx ¦ Rad | Pod 1 | Pod 1_Member3 | 2026-07-15 | 3 | 0 | 7 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 34 |  | 4
74 | Location | Complete ASP | 2026-06-09 | location/addressContact.aspx ¦ RadAj | Pod 3 | Pod 3_Member1 | 2026-06-09 | 3 | 0 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-02 | 1 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-16 | 2026-07-23 | 42 |  | 4
75 | Location | Complete ASP | 2026-06-01 | location/createHousehold.aspx ¦ RadA | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 0 | 2 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-02 | 1 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-16 | 2026-07-23 | 50 |  | 4
76 | Location | Complete ASP | 2026-05-22 | location/createHouseholdLinkExisting | Pod 3 | Pod 3_Member3 | 2026-05-22 | 3 | 0 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 1 | 2026-05-27 | 1 | 2026-05-28 | 2026-05-28 | 1 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-02 | 1 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-07-02 | 1 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-16 | 2026-07-23 | 58 |  | 4
77 | Location | Complete ASP | 2026-06-17 | location/dataview.aspx ¦ RadGrid, Ra | Pod 3 | Pod 3_Member1 | 2026-06-17 | 3 | 0 | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-26 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-16 | 2026-07-23 | 34 |  | 4
78 | Location | Complete ASP | 2026-06-09 | location/extendedFields.aspx ¦ RadGr | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 | 0 | 5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 1 | 2026-06-19 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-02 | 1 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-16 | 2026-07-23 | 42 |  | 4
79 | Location | Complete ASP | 2026-06-01 | location/locationExtended.aspx ¦ Rad | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 | 0 | 6 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 1 | 2026-06-11 | 1 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-02 | 1 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-16 | 2026-07-23 | 50 |  | 4
80 | AssetAware | Complete ASP | 2026-07-03 | assetAware/asset.aspx | Pod 3 | Pod 3_Member3 | 2026-07-03 | 3 | 0 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 42 |  | 4
81 | AssetAware | Complete ASP | 2026-07-03 | assetAware/assets.aspx | Pod 3 | Pod 3_Member2 | 2026-07-03 | 3 | 0 | 2 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 42 |  | 4
82 | AssetAware | Complete ASP | 2026-06-17 | assetAware/assetHistory.aspx | Pod 3 | Pod 3_Member3 | 2026-06-17 | 3 | 0 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 1 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 1 | 2026-06-26 | 1 | 2026-06-29 | 1 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 62 |  | 4
83 | AssetAware | Complete ASP | 2026-07-15 | assetAware/assetVendorAddressContact.aspx | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 34 | 14 | 4 |  |  | 18
84 | AssetAware | Complete ASP | 2026-07-15 | assetAware/assetVendorAddressContact.aspx | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 34 | 14 | 4 |  |  | 18
85 | AssetAware | Complete ASP | 2026-07-15 | assetAware/assetVendorAddressContact.aspx | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 34 | 14 | 4 |  |  | 18
86 | AssetAware | Complete ASP | 2026-07-15 | assetAware/assetVendorAddressContact.aspx | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 34 | 14 | 4 |  |  | 18
87 | AssetAware | Complete ASP | 2026-07-15 | assetAware/assetVendorAddressContact.aspx | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 34 | 14 | 4 |  |  | 18
88 | AssetAware | Complete ASP | 2026-07-15 | assetAware/assetVendorAddressContact.aspx | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 34 | 14 | 4 |  |  | 18
89 | Log | Complete ASP | 2026-07-15 | log/default.aspx ¦ RadGrid, RadAjaxManager, RadDa | Pod 2 | Pod 2_Member1 | 2026-07-15 | 3 | 0 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 34 |  | 4
90 | Log | Complete ASP | 2026-07-15 | log/logEntry.aspx ¦ RadGrid, RadAjaxManager, RadT | Pod 2 | Pod 2_Member2 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 34 |  | 4
91 | Log | Complete ASP | 2026-07-03 | log/areas.aspx ¦ RadGrid, RadAjaxManager ¦ Medium | Pod 2 | Pod 2_Member3 | 2026-07-03 | 3 | 0 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 42 |  | 4
92 | Log | Complete ASP | 2026-07-23 | log/categories.aspx ¦ RadGrid, RadAjaxManager ¦ M | Pod 2 | Pod 2_Member1 | 2026-07-23 | 3 | 0 | 4 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 1 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 24 |  | 4
93 | Log | Complete ASP | 2026-07-23 | log/contactTypes.aspx ¦ RadGrid, RadAjaxManager ¦ | Pod 2 | Pod 2_Member2 | 2026-07-23 | 3 | 0 | 5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 1 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 24 |  | 4
94 | Log | Complete ASP | 2026-07-15 | log/logEntrySystems.aspx ¦ RadGrid, RadAjaxManage | Pod 2 | Pod 2_Member3 | 2026-07-15 | 3 | 0 | 6 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 34 |  | 4
95 | Log | Complete ASP | 2026-07-23 | log/myLogSettings.aspx ¦ RadGrid, RadAjaxManager, | Pod 2 | Pod 3_Member2 | 2026-07-23 | 3 | 0 | 7 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 1 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 24 |  | 4
96 | Reg+Attendance | Complete ASP | 2026-07-23 | attendance/enterAttendance.aspx | Pod 1 | Pod 1_Member1 | 2026-07-23 | 3 | 0 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 1 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 24 |  | 4
97 | Reg+Attendance | Complete ASP | 2026-07-23 | attendance/editRecord.aspx ¦ Ra | Pod 1 | Pod 1_Member2 | 2026-07-23 | 3 | 0 | 2 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 1 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 24 |  | 4
98 | Reg+Attendance | Complete ASP | 2026-06-25 | registration.aspx | Pod 1 | Pod 1_Member3 | 2026-06-25 | 3 | 0 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 1 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 52 |  | 4
99 | Reg+Attendance | Complete ASP | 2026-07-23 | AdditionalPage 1 | Pod 1 | Pod 1_Member3 | 2026-07-23 | 3 | 0 | 4 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 1 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 1 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 2026-08-20 | 24 |  | 4
100 | Home | Complete ASP | 2026-07-15 | home/pages/caretaker.aspx ¦ | Pod 3 | Pod 3_Member3 | 2026-07-15 | 3 | 0 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 34 |  | 4
101 | Home | Complete ASP | 2026-07-15 | home/pages/teacher.aspx ¦ R | Pod 3 | Pod 3_Member2 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 2026-07-22 | 2026-07-23 | 2026-07-23 | 1 | 2026-07-24 | 1 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 2026-07-30 | 1 | 2026-07-31 | 1 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-11 | 2026-08-20 | 34 |  | 4
102 | Assessments | Complete ASP | 2026-07-31 | assessments/default.aspx ¦ RadGrid, | Pod 2 | Pod 3_Member1 | 2026-07-31 | 3 | 0 | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 44 |  | 4
103 | Assessments | Complete ASP | 2026-07-31 | assessments/questionObjectives.aspx | Pod 2 | Pod 2_Member2 | 2026-07-31 | 3 | 0 | 2 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 44 |  | 4
104 | Assessments | Complete ASP | 2026-07-31 | assessments/results/manager.aspx ¦ | Pod 2 | Pod 2_Member3 | 2026-07-31 | 3 | 0 | 3 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 44 |  | 4
105 | Assessments | Complete ASP | 2026-07-31 | assessments/webuserAssessmentFiles. | Pod 2 | Pod 3_Member2 | 2026-07-31 | 3 | 0 | 4 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 44 |  | 4
106 | Assessments | Complete ASP | 2026-07-31 | assessments/checkMyWork/checkMyWork | Pod 2 | Pod 3_Member3 | 2026-07-31 | 3 | 0 | 5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 44 |  | 4
107 | Assessments | Complete ASP | 2026-08-10 | assessments/checkMyWork/submissions | Pod 2 | Pod 2_Member3 | 2026-08-10 | 3 | 0 | 6 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 |  | 4
108 | Assessments | Complete ASP | 2026-08-10 | assessments/import.aspx ¦ RadGrid, | Pod 2 | Pod 2_Member1 | 2026-08-10 | 3 | 0 | 7 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 |  | 4
109 | Assessments | Complete ASP | 2026-08-10 | assessments/question.aspx ¦ RadAjax | Pod 2 | Pod 2_Member2 | 2026-08-10 | 3 | 0 | 8 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 |  | 4
110 | Assessments | Complete ASP | 2026-08-10 | assessments/questionManager.aspx ¦ | Pod 2 | Pod 1_Member3 | 2026-08-10 | 3 | 0 | 9 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 |  | 4
111 | Assessments | Complete ASP | 2026-08-10 | assessments/questions.aspx ¦ RadGri | Pod 2 | Pod 3_Member1 | 2026-08-10 | 3 | 0 | 10 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 | 15 | 4 |  |  | 19
112 | Assessments | Complete ASP | 2026-08-10 | assessments/questions.aspx ¦ RadGri | Pod 2 | Pod 3_Member1 | 2026-08-10 | 3 | 0 | 10 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 | 15 | 4
113 | Assessments | Complete ASP | 2026-08-10 | assessments/questions.aspx ¦ RadGri | Pod 2 | Pod 3_Member1 | 2026-08-10 | 3 | 0 | 10 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 | 15 | 4
114 | Reports | Complete ASP | 2026-07-31 | reports/aggregateLogEntry.aspx ¦ RadGrid | Pod 1 | Pod 1_Member1 | 2026-07-31 | 3 | 0 | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 44 |  | 4
115 | Reports | Complete ASP | 2026-07-31 | reports/institutionalStudentPerformanceE | Pod 1 | Pod 1_Member3 | 2026-07-31 | 3 | 0 | 2 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 44 |  | 4
116 | Reports | Complete ASP | 2026-07-03 | reports/resourceManagerExport.aspx ¦ Rad | Pod 1 | Pod 1_Member3 | 2026-07-03 | 3 | 0 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 70 |  | 4
117 | Reports | Complete ASP | 2026-08-10 | reports/sectionLogEntryReport.aspx ¦ Rad | Pod 1 | Pod 1_Member1 | 2026-08-10 | 3 | 0 | 4 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 |  | 4
118 | Reports | Complete ASP | 2026-08-10 | reports/SectionObjectivePerformance.aspx | Pod 1 | Pod 1_Member2 | 2026-08-10 | 3 | 0 | 5 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 | 15 | 4 |  |  | 19
119 | Reports | Complete ASP | 2026-07-31 | reports/aggregateLogEntry.aspx ¦ RadGrid | Pod 1 | Pod 1_Member1 | 2026-07-31 | 3 | 0 | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 44 |  | 4
120 | Reports | Complete ASP | 2026-07-31 | reports/institutionalStudentPerformanceE | Pod 1 | Pod 1_Member3 | 2026-07-31 | 3 | 0 | 2 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 1 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10 | 1 | 2026-08-11 | 1 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 44 |  | 4
121 | Reports | Complete ASP | 2026-07-03 | reports/resourceManagerExport.aspx ¦ Rad | Pod 1 | Pod 1_Member3 | 2026-07-03 | 3 | 0 | 3 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 70 |  | 4
122 | Reports | Complete ASP | 2026-08-10 | reports/sectionLogEntryReport.aspx ¦ Rad | Pod 1 | Pod 1_Member1 | 2026-08-10 | 3 | 0 | 4 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 |  | 4
123 | Reports | Complete ASP | 2026-08-10 | reports/SectionObjectivePerformance.aspx | Pod 1 | Pod 1_Member2 | 2026-08-10 | 3 | 0 | 5 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 | 15 | 4 |  |  | 19
124 | Reports | Complete ASP | 2026-08-10 | reports/SectionObjectivePerformance.aspx | Pod 1 | Pod 1_Member2 | 2026-08-10 | 3 | 0 | 5 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 | 15 | 4 |  |  | 19
125 | Reports | Complete ASP | 2026-08-10 | reports/SectionObjectivePerformance.aspx | Pod 1 | Pod 1_Member2 | 2026-08-10 | 3 | 0 | 5 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 | 15 | 4 |  |  | 19
126 | Reports | Complete ASP | 2026-08-10 | reports/SectionObjectivePerformance.aspx | Pod 1 | Pod 1_Member2 | 2026-08-10 | 3 | 0 | 5 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 | 15 | 4 |  |  | 19
127 | Content | Complete ASP | 2026-08-18 | content/hyperlink.aspx ¦ RadAjaxM | Pod 2 | Pod 1_Member3 | 2026-08-18 | 3 | 0 | 4 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 | 7 | 4 |  |  | 11
128 | Communication | Complete ASP | 2026-08-10 | communication/webmail/webmailBox.aspx ¦ RadGr | Pod 2 | Pod 3_Member2 | 2026-08-10 | 3 | 0 | 1 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 |  | 4
129 | Communication | Complete ASP | 2026-08-10 | communication/webmail/settings.aspx ¦ RadAjax | Pod 2 | Pod 3_Member3 | 2026-08-10 | 3 | 0 | 2 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 1 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 1 | 2026-08-19 | 1 | 2026-08-20 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-17 | 36 |  | 4
130 | Content | Complete ASP | 2026-08-18 | content/captionedVideoItem.aspx ¦ | Pod 2 | Pod 1_Member1 | 2026-08-18 | 3 | 0 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 |  | 4
131 | Content | Complete ASP | 2026-08-18 | content/chrome/online/footer.aspx | Pod 2 | Pod 2_Member2 | 2026-08-18 | 3 | 0 | 2 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 |  | 4
132 | Content | Complete ASP | 2026-08-18 | content/elmItemInteractive.aspx ¦ | Pod 2 | Pod 1_Member2 | 2026-08-18 | 3 | 0 | 3 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 | 7 | 4
133 | Content | Complete ASP | 2026-08-18 | content/hyperlink.aspx ¦ RadAjaxM | Pod 2 | Pod 1_Member3 | 2026-08-18 | 3 | 0 | 4 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 | 7 | 4 |  |  | 11
134 | Content | Complete ASP | 2026-08-18 | content/captionedVideoItem.aspx ¦ | Pod 2 | Pod 1_Member1 | 2026-08-18 | 3 | 0 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 |  | 4
135 | Content | Complete ASP | 2026-08-18 | content/chrome/online/footer.aspx | Pod 2 | Pod 2_Member2 | 2026-08-18 | 3 | 0 | 2 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 |  | 4
136 | Content | Complete ASP | 2026-08-18 | content/elmItemInteractive.aspx ¦ | Pod 2 | Pod 1_Member2 | 2026-08-18 | 3 | 0 | 3 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 | 7 | 4
137 | Content | Complete ASP | 2026-08-18 | content/chrome/online/footer.aspx | Pod 2 | Pod 2_Member2 | 2026-08-18 | 3 | 0 | 2 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 |  | 4
138 | Content | Complete ASP | 2026-08-18 | content/elmItemInteractive.aspx ¦ | Pod 2 | Pod 1_Member2 | 2026-08-18 | 3 | 0 | 3 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 | 7 | 4
139 | Content | Complete ASP | 2026-08-18 | content/elmItemInteractive.aspx ¦ | Pod 2 | Pod 1_Member2 | 2026-08-18 | 3 | 0 | 3 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 1 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-15 | 2026-09-17 | 28 | 7 | 4
140 | Planner | ?? | 2026-08-18 | content/elmItemInteractive.aspx ¦ | Pod 2 | Pod 1_Member2 | 2026-08-18 | 3 | 0 | 3 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 0 | 1 | 1900-01-01 | 1 | 1900-01-02 | 1 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-10 | 1900-01-11 | -46242 | 6 | 4
141 | Planner | ?? | 2026-08-18 | content/elmItemInteractive.aspx ¦ | Pod 2 | Pod 1_Member2 | 2026-08-18 | 3 | 0 | 3 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-21 | 1 | 2026-08-24 | 2026-08-24 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 1 | 2026-08-28 | 1 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 1 | 2026-09-03 | 0 | 1 | 1900-01-01 | 1 | 1900-01-02 | 1 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-10 | 1900-01-11 | -46242 | 6 | 4
Formulas:
Start Date = [Module Target Start (Input)]
Co- Pilot Comment Closure Date = [Start Date]+[Dev Efforts]
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = [Co- Pilot Comment Closure Date]
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = [Unit Testing Closure Date]
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Pearson Regression Testing/UAT Date = MAX(IF(B2:B133=[Module], AJ2:AJ133))
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
TEST Deployment = WORKDAY([PR Response receive Date], 1, IndHolidays)
Release Request Approved Date = WORKDAY([Release Request Raise Date], 3, IndHolidays)
Release Date (2-Wk Cycle) = CEILING([Release Request Approved Date]-DATE(2026,4,16), 14)+DATE(2026,4,16)

## Sheet1 (hidden)
No. | Module | Recieved Functional & Non Fuctional Walkthrough | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Code Freeze Date | TEST Deployment | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | Code freeze date = Release cutoff Date | Release # | Release Request Approved Date | Release Date (2-Wk Cycle) | Code freeze date = Release cutoff Date | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
1 | AddressBook | Yes | 2026-04-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | #VALUE! | 41 |  | 9
2 | AddressBook | Yes | 2026-04-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
3 | AddressBook | Yes | 2026-04-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
4 | AddressBook | Yes | 2026-04-24 | page_4 | Pod 3 | Pod 3_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
5 | AddressBook | Yes | 2026-04-24 | page_5 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 3 | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 | #VALUE! | 9 |  |  | #VALUE!
6 | Assessments | Yes | 2026-07-23 | page_1 | Pod 2 | Pod 3_Member2 | 2026-07-23 | 3 | 0 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
7 | Assessments | Yes | 2026-07-23 | page_2 | Pod 2 | Pod 3_Member3 | 2026-07-23 | 3 | 0 | 2 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
8 | Assessments | Yes | 2026-07-31 | page_3 | Pod 2 | Pod 2_Member3 | 2026-07-31 | 3 | 0 | 3 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
9 | Assessments | Yes | 2026-07-31 | page_4 | Pod 2 | Pod 2_Member1 | 2026-07-31 | 3 | 0 | 4 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
10 | Assessments | Yes | 2026-07-31 | page_5 | Pod 2 | Pod 2_Member2 | 2026-07-31 | 3 | 0 | 5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
11 | Assessments | Yes | 2026-07-31 | page_6 | Pod 2 | Pod 1_Member1 | 2026-07-31 | 3 | 0 | 6 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
12 | Assessments | Yes | 2026-07-31 | page_7 | Pod 2 | Pod 1_Member2 | 2026-07-31 | 3 | 0 | 7 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
13 | Assessments | Yes | 2026-07-31 | page_8 | Pod 2 | Pod 1_Member3 | 2026-07-31 | 3 | 0 | 8 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 | #VALUE! | 9 |  |  | #VALUE!
14 | Assessments | Yes | 2026-07-31 | page_9 | Pod 2 | Pod 3_Member1 | 2026-07-31 | 3 | 0 | 9 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
15 | Assessments | Yes | 2026-07-31 | page_10 | Pod 2 | Pod 3_Member2 | 2026-07-31 | 3 | 0 | 10 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 3 | 2026-08-19 | 2 | 2026-08-24 | 3 | 2026-08-28 | 2026-08-28 | 2026-08-31 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 3 | 2026-09-07 | 0 | 2026-09-07 | 0 | 2026-09-07 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 44 |  | 9
16 | AssetAware | No | 2026-05-15 | page_1 | Pod 4 | Pod 4_Member1 | 2026-05-15 | 3 | 0 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
17 | AssetAware | No | 2026-05-15 | page_2 | Pod 4 | Pod 4_Member1 | 2026-05-15 | 3 | 0 | 2 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
18 | AssetAware | No | 2026-05-15 | page_3 | Pod 4 | Pod 4_Member3 | 2026-05-15 | 3 | 0 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
19 | AssetAware | No | 2026-05-25 | page_4 | Pod 4 | Pod 4_Member2 | 2026-05-25 | 3 | 0 | 4 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 3 | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 43 |  | 9
20 | Communication | No | 2026-05-25 | page_1 | Pod 4 | Pod 4_Member1 | 2026-05-25 | 3 | 0 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 29 |  | 9
21 | Communication | No | 2026-05-25 | page_2 | Pod 4 | Pod 4_Member3 | 2026-05-25 | 3 | 0 | 2 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 29 |  | 9
22 | Communication | No | 2026-06-02 | page_3 | Pod 4 | Pod 4_Member1 | 2026-06-02 | 3 | 0 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 |  | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 34 |  | 9
23 | Communication | No | 2026-06-02 | page_4 | Pod 4 | Pod 4_Member2 | 2026-06-02 | 3 | 0 | 4 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 3 | 2026-07-09 | 0 | 2026-07-09 | 0 | 2026-07-09 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 34 | #VALUE! | 9 |  |  | #VALUE!
24 | Content | No | 2026-06-02 | page_1 | Pod 4 | Pod 4_Member3 | 2026-06-02 | 3 | 0 | 1 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 |  | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 34 |  | 9
25 | Content | No | 2026-06-10 | page_2 | Pod 4 | Pod 4_Member1 | 2026-06-10 | 3 | 0 | 2 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
26 | Content | No | 2026-06-10 | page_3 | Pod 4 | Pod 4_Member3 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
27 | Content | No | 2026-06-10 | page_4 | Pod 4 | Pod 4_Member2 | 2026-06-10 | 3 | 0 | 4 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 3 | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
28 | Enrollment | No | 2026-05-05 | page_1 | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
29 | Enrollment | No | 2026-05-14 | page_2 | Pod 1 | Pod 1_Member1 | 2026-05-14 | 3 | 0 | 2 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
30 | Enrollment | No | 2026-05-14 | page_3 | Pod 1 | Pod 1_Member2 | 2026-05-14 | 3 | 0 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
31 | Enrollment | No | 2026-05-14 | page_4 | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
32 | Enrollment | No | 2026-05-22 | page_5 | Pod 1 | Pod 1_Member1 | 2026-05-22 | 3 | 0 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
33 | Enrollment | No | 2026-05-22 | page_6 | Pod 1 | Pod 1_Member2 | 2026-05-22 | 3 | 0 | 6 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
34 | Enrollment | No | 2026-05-22 | page_7 | Pod 1 | Pod 1_Member3 | 2026-05-22 | 3 | 0 | 7 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
35 | Enrollment | No | 2026-06-01 | page_8 | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 8 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
36 | ExtendedField | Yes | 2026-04-15 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
37 | ExtendedField | Yes | 2026-04-15 | page_2 | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
38 | ExtendedField | Yes | 2026-04-15 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
39 | ExtendedField | Yes | 2026-04-24 | page_4 | Pod 1 | Pod 1_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
40 | ExtendedField | Yes | 2026-04-24 | page_5 | Pod 1 | Pod 1_Member2 | 2026-04-24 | 3 | 0 | 5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
41 | ExtendedField | Yes | 2026-04-24 | page_6 | Pod 1 | Pod 1_Member3 | 2026-04-24 | 3 | 0 | 6 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
42 | ExtendedField | Yes | 2026-05-05 | page_7 | Pod 1 | Pod 1_Member1 | 2026-05-05 | 3 | 0 | 7 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
43 | ExtendedField | Yes | 2026-05-05 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 8 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
44 | GradeBook | Yes | 2026-04-15 | page_3 | Pod 2 | Pod 2_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 3 | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
45 | GradeBook | Yes | 2026-04-15 | page_4 | Pod 2 | Pod 2_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 3 | 2026-05-20 | 1 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 12
46 | Home | No | 2026-06-25 | page_1 | Pod 3 | Pod 3_Member3 | 2026-06-25 | 3 | 0 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
47 | Home | No | 2026-07-03 | page_2 | Pod 3 | Pod 3_Member1 | 2026-07-03 | 3 | 0 | 2 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 |  | 9
48 | Home | No | 2026-07-03 | page_3 | Pod 3 | Pod 3_Member2 | 2026-07-03 | 3 | 0 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 |  | 9
49 | Home | No | 2026-07-03 | page_4 | Pod 3 | Pod 3_Member3 | 2026-07-03 | 3 | 0 | 4 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 2 | 2026-07-27 | 3 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-04 | 3 | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 43 | #VALUE! | 9 |  |  | #VALUE!
50 | IssueAware | Yes | 2026-04-15 | page_1 | Pod 2 | Pod 2_Member3 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
51 | IssueAware | Yes | 2026-04-24 | page_2 | Pod 2 | Pod 2_Member1 | 2026-04-24 | 3 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 3 | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 9
52 | Library | Yes | 2026-07-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
53 | Library | Yes | 2026-07-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
54 | Library | Yes | 2026-07-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-07-15 | 3 | 0 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 3 | 2026-08-03 | 2 | 2026-08-05 | 3 | 2026-08-10 | 2026-08-10 | 2026-08-11 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 2026-08-13 | 3 | 2026-08-18 | 0 | 2026-08-18 | 0 | 2026-08-18 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
55 | LMU | Yes | 2026-04-24 | page_2 | Pod 2 | Pod 2_Member2 | 2026-04-24 | 3 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 3 | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 9
56 | LMU | Yes | 2026-04-24 | page_3 | Pod 2 | Pod 2_Member3 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 | #VALUE! | 9
57 | LMU | Yes | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
58 | LMU | Yes | 2026-05-05 | page_5 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
59 | LMU | Yes | 2026-05-05 | page_6 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 | #VALUE! | 9 |  |  | #VALUE!
60 | LMU | Yes | 2026-05-14 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
61 | LMU | Yes | 2026-05-14 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-14 | 3 | 0 | 8 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 3 | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
62 | LMU | Yes | 2026-05-14 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-14 | 3 | 0 | 9 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
63 | LMU | Yes | 2026-05-22 | page_7 | Pod 2 | Pod 2_Member1 | 2026-05-22 | 3 | 0 | 7 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 3 | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 44 |  | 9
64 | LMU | Yes | 2026-05-22 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-22 | 3 | 0 | 11 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
65 | LMU | Yes | 2026-05-22 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-22 | 3 | 0 | 12 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 3 | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 44 |  | 9
66 | LMU | Yes | 2026-06-01 | page_10 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 10 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
67 | LMU | Yes | 2026-06-01 | page_14 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 14 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 | #VALUE! | 9 |  |  | #VALUE!
68 | LMU | Yes | 2026-06-01 | page_15 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 15 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
69 | LMU | Yes | 2026-06-09 | page_13 | Pod 2 | Pod 2_Member1 | 2026-06-09 | 3 | 0 | 13 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 3 | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 42 |  | 9
70 | LMU | Yes | 2026-06-09 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-09 | 3 | 0 | 17 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 |  | 9
71 | LMU | Yes | 2026-06-09 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-09 | 3 | 0 | 18 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 3 | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 42 |  | 9
72 | LMU | Yes | 2026-06-17 | page_16 | Pod 2 | Pod 2_Member1 | 2026-06-17 | 3 | 0 | 16 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 9
73 | LMU | Yes | 2026-06-17 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-17 | 3 | 0 | 20 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 2 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 3 | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 48 |  | 9
74 | LMU | Yes | 2026-06-17 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-17 | 3 | 0 | 21 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 9
75 | LMU | Yes | 2026-06-25 | page_19 | Pod 2 | Pod 2_Member1 | 2026-06-25 | 3 | 0 | 19 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 3 | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 3 | 2026-07-31 | 0 | 2026-07-31 | 0 | 2026-07-31 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
76 | LMU | Yes | 2026-06-25 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-25 | 3 | 0 | 23 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
77 | LMU | Yes | 2026-06-25 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-25 | 3 | 0 | 24 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 3 | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 3 | 2026-07-31 | 0 | 2026-07-31 | 0 | 2026-07-31 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
78 | LMU | Yes | 2026-07-03 | page_22 | Pod 2 | Pod 2_Member1 | 2026-07-03 | 3 | 0 | 22 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 | #VALUE! | 9 |  |  | #VALUE!
79 | LMU | Yes | 2026-07-03 | page_25 | Pod 2 | Pod 2_Member3 | 2026-07-03 | 3 | 0 | 25 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 1 | 2026-07-30 | 3 | 2026-08-04 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 |  | 12
80 | LMU | Yes | 2026-07-03 | page_26 | Pod 2 | Pod 2_Member2 | 2026-07-03 | 3 | 0 | 26 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 2 | 2026-07-27 | 3 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 43 |  | 12
81 | Location | Yes | 2026-04-24 | page_1 | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
82 | Location | Yes | 2026-05-05 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 | #VALUE! | 9 |  |  | #VALUE!
83 | Location | Yes | 2026-05-05 | page_3 | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
84 | Location | Yes | 2026-05-05 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 4 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
85 | Location | Yes | 2026-05-14 | page_5 | Pod 3 | Pod 3_Member1 | 2026-05-14 | 3 | 0 | 5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
86 | Location | Yes | 2026-05-14 | page_6 | Pod 3 | Pod 3_Member2 | 2026-05-14 | 3 | 0 | 6 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
87 | Location | Yes | 2026-05-14 | page_7 | Pod 3 | Pod 3_Member3 | 2026-05-14 | 3 | 0 | 7 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
88 | Location | Yes | 2026-05-22 | page_8 | Pod 3 | Pod 3_Member1 | 2026-05-22 | 3 | 0 | 8 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
89 | Location | Yes | 2026-05-22 | page_9 | Pod 3 | Pod 3_Member2 | 2026-05-22 | 3 | 0 | 9 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
90 | Location | Yes | 2026-05-22 | page_10 | Pod 3 | Pod 3_Member3 | 2026-05-22 | 3 | 0 | 10 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
91 | Location | Yes | 2026-06-01 | page_11 | Pod 3 | Pod 3_Member1 | 2026-06-01 | 3 | 0 | 11 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
92 | Log | Yes | 2026-07-15 | page_1 | Pod 2 | Pod 2_Member1 | 2026-07-15 | 3 | 0 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 | #VALUE! | 9 |  |  | #VALUE!
93 | Log | Yes | 2026-07-15 | page_2 | Pod 2 | Pod 2_Member2 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
94 | Log | Yes | 2026-07-15 | page_3 | Pod 2 | Pod 2_Member3 | 2026-07-15 | 3 | 0 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
95 | Log | Yes | 2026-07-23 | page_4 | Pod 2 | Pod 2_Member1 | 2026-07-23 | 3 | 0 | 4 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
96 | Log | Yes | 2026-07-23 | page_5 | Pod 2 | Pod 2_Member2 | 2026-07-23 | 3 | 0 | 5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
97 | Log | Yes | 2026-07-23 | page_6 | Pod 2 | Pod 2_Member3 | 2026-07-23 | 3 | 0 | 6 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
98 | Log | Yes | 2026-07-23 | page_7 | Pod 2 | Pod 1_Member1 | 2026-07-23 | 3 | 0 | 7 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
99 | Log | Yes | 2026-07-23 | page_8 | Pod 2 | Pod 1_Member2 | 2026-07-23 | 3 | 0 | 8 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
100 | Log | Yes | 2026-07-23 | page_9 | Pod 2 | Pod 1_Member3 | 2026-07-23 | 3 | 0 | 9 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
101 | Log | Yes | 2026-07-23 | page_10 | Pod 2 | Pod 3_Member1 | 2026-07-23 | 3 | 0 | 10 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 3 | 2026-08-11 | 2 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-19 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-24 | 3 | 2026-08-28 | 0 | 2026-08-28 | 0 | 2026-08-28 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 | #VALUE! | 9 |  |  | #VALUE!
102 | OrderAware | Yes | 2026-06-18 | page_5 | Pod 4 | Pod 4_Member2 | 2026-06-18 | 3 | 0 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 9
103 | OrderAware | Yes | 2026-06-18 | page_6 | Pod 4 | Pod 4_Member3 | 2026-06-18 | 3 | 0 | 2 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 9
104 | OrderAware | Yes | 2026-06-18 | page_7 | Pod 4 | Pod 4_Member1 | 2026-06-18 | 3 | 0 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 9
105 | OrderAware | Yes | 2026-06-26 | page_8 | Pod 4 | Pod 4_Member2 | 2026-06-26 | 3 | 0 | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 3 | 2026-07-06 | 1.5 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 3 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 36 |  | 12
106 | ProgressionPlan | No | 2026-06-01 | page_1 | Pod 1 | Pod 1_Member2 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
107 | ProgressionPlan | No | 2026-06-01 | page_2 | Pod 1 | Pod 1_Member3 | 2026-06-01 | 3 | 0 | 2 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
108 | ProgressionPlan | No | 2026-06-09 | page_3 | Pod 1 | Pod 1_Member1 | 2026-06-09 | 3 | 0 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 |  | 9
109 | ProgressionPlan | No | 2026-06-09 | page_4 | Pod 1 | Pod 1_Member2 | 2026-06-09 | 3 | 0 | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 |  | 9
110 | ProgressionPlan | No | 2026-06-09 | page_5 | Pod 1 | Pod 1_Member3 | 2026-06-09 | 3 | 0 | 5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 |  | 9
111 | ProgressionPlan | No | 2026-06-17 | page_6 | Pod 1 | Pod 1_Member1 | 2026-06-17 | 3 | 0 | 6 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 | #VALUE! | 9 |  |  | #VALUE!
112 | ProgressionPlan | No | 2026-06-17 | page_7 | Pod 1 | Pod 1_Member2 | 2026-06-17 | 3 | 0 | 7 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 2 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 3 | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 48 |  | 9
113 | Reg+Attendance | No | 2026-06-17 | page_1 | Pod 1 | Pod 1_Member3 | 2026-06-17 | 3 | 0 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 9
114 | Reg+Attendance | No | 2026-06-25 | page_2 | Pod 1 | Pod 1_Member1 | 2026-06-25 | 3 | 0 | 2 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
115 | Reg+Attendance | No | 2026-06-25 | page_3 | Pod 1 | Pod 1_Member2 | 2026-06-25 | 3 | 0 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
116 | Reg+Attendance | No | 2026-06-25 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-25 | 3 | 0 | 4 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 | #VALUE! | 9 |  |  | #VALUE!
117 | Reg+Attendance | No | 2026-07-03 | page_5 | Pod 1 | Pod 1_Member1 | 2026-07-03 | 3 | 0 | 5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 2 | 2026-07-27 | 3 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-04 | 3 | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 43 | #VALUE! | 9 |  |  | #VALUE!
118 | Reports | No | 2026-07-03 | page_1 | Pod 1 | Pod 1_Member2 | 2026-07-03 | 3 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 |  | 9
119 | Reports | No | 2026-07-03 | page_2 | Pod 1 | Pod 1_Member3 | 2026-07-03 | 3 | 0 | 2 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 |  | 9
120 | Reports | No | 2026-07-15 | page_3 | Pod 1 | Pod 1_Member1 | 2026-07-15 | 3 | 0 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
121 | Reports | No | 2026-07-15 | page_4 | Pod 1 | Pod 1_Member3 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 | #VALUE! | 9 |  |  | #VALUE!
122 | Reports | No | 2026-07-15 | page_5 | Pod 1 | Pod 1_Member2 | 2026-07-15 | 3 | 0 | 5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 3 | 2026-08-03 | 2 | 2026-08-05 | 3 | 2026-08-10 | 2026-08-10 | 2026-08-11 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 2026-08-13 | 3 | 2026-08-18 | 0 | 2026-08-18 | 0 | 2026-08-18 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
123 | Webuser | No | 2026-06-01 | page_1 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
124 | Webuser | No | 2026-06-01 | page_2 | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 | 0 | 2 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 | #VALUE! | 9
125 | Webuser | No | 2026-06-09 | page_3 | Pod 3 | Pod 3_Member1 | 2026-06-09 | 3 | 0 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 | #VALUE! | 9
126 | Webuser | No | 2026-06-09 | page_4 | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 | 0 | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 |  | 9
127 | Webuser | No | 2026-06-09 | page_5 | Pod 3 | Pod 3_Member3 | 2026-06-09 | 3 | 0 | 5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 | #VALUE! | 9
128 | Webuser | No | 2026-06-17 | page_1 | Pod 3 | Pod 3_Member1 | 2026-06-17 | 3 | 0 | 6 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 | #VALUE! | 9
129 | Webuser | No | 2026-06-17 | page_2 | Pod 3 | Pod 3_Member2 | 2026-06-17 | 3 |  | 7 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16
130 | Webuser | No | 2026-06-17 | page_3 | Pod 3 | Pod 3_Member3 | 2026-06-17 | 3 |  | 8 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16
131 | Webuser | No | 2026-06-25 | page_4 | Pod 3 | Pod 3_Member1 | 2026-06-25 | 3 |  | 9 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30
132 | Webuser | No | 2026-06-25 | page_5 | Pod 3 | Pod 3_Member2 | 2026-06-25 | 3 |  | 10 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 3 | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 3 | 2026-07-31 | 0 | 2026-07-31 | 0 | 2026-07-31 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30
Formulas:
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Code Freeze Date = [TCR Bugs Closure Date]
TEST Deployment = [Code Freeze Date]
Pearson Regression Testing/UAT Date = WORKDAY([TEST Deployment], 1, IndHolidays)
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&[TCR Bugs Closure Date])
Code freeze date = Release cutoff Date = WORKDAY([Release Date (2-Wk Cycle)], -5)
Release Request Approved Date = WORKDAY([Release #], 2, IndHolidays)
Release Date (2-Wk Cycle) = VLOOKUP([Release #],ReleaseTimeline!$B2:C27,2,FALSE)

## 0.5 estimations (hidden)
No. | Module | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | TEST Deployment | Release Request Raise Date | Release Request Approved Date | Release Date (2-Wk Cycle) | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
27 | AddressBook | 2026-04-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 0.5 | 2026-04-21 | 2026-04-30 | 1 | 2026-05-04 | 0.5 | 2026-05-04 | 0.5 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-11 | 2026-05-14 | 27 |  | 2
28 | AddressBook | 2026-04-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 0.5 | 2026-04-21 | 2026-04-30 | 1 | 2026-05-04 | 0.5 | 2026-05-04 | 0.5 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-11 | 2026-05-14 | 27 |  | 2
29 | AddressBook | 2026-04-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 0.5 | 2026-04-21 | 2026-04-30 | 1 | 2026-05-04 | 0.5 | 2026-05-04 | 0.5 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-11 | 2026-05-14 | 27 |  | 2
30 | AddressBook | 2026-04-24 | page_4 | Pod 3 | Pod 3_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 0.5 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 0.5 | 2026-05-04 | 0.5 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-11 | 2026-05-14 | 16 |  | 2
31 | AddressBook | 2026-04-24 | page_5 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 0.5 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 0.5 | 2026-05-04 | 0.5 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-11 | 2026-05-14 | 16 |  | 2
32 | Assessments | 2026-07-23 | page_1 | Pod 2 | Pod 3_Member2 | 2026-07-23 | 3 | 0 | 6 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 0.5 | 2026-07-29 | 2026-08-06 | 1 | 2026-08-07 | 0.5 | 2026-08-07 | 0.5 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 24 |  | 2
33 | Assessments | 2026-07-23 | page_2 | Pod 2 | Pod 3_Member3 | 2026-07-23 | 3 | 0 | 7 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 0.5 | 2026-07-29 | 2026-08-06 | 1 | 2026-08-07 | 0.5 | 2026-08-07 | 0.5 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 24 |  | 2
34 | Assessments | 2026-07-31 | page_3 | Pod 2 | Pod 2_Member3 | 2026-07-31 | 3 | 0 | 8 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-05 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 0.5 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 0.5 | 2026-08-07 | 0.5 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 16 | 9 | 2 |  |  | 11
35 | Assessments | 2026-07-31 | assessments/webuserAssessmentFiles. | Pod 2 | Pod 2_Member1 | 2026-07-31 | 3 | 0 | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-05 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 0.5 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 0.5 | 2026-08-07 | 0.5 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 16 |  | 2
36 | Assessments | 2026-07-31 | assessments/checkMyWork/checkMyWork | Pod 2 | Pod 2_Member2 | 2026-07-31 | 3 | 0 | 2 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-05 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 0.5 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 0.5 | 2026-08-07 | 0.5 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 16 |  | 2
37 | Assessments | 2026-07-31 | assessments/checkMyWork/submissions | Pod 2 | Pod 1_Member1 | 2026-07-31 | 3 | 0 | 3 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-05 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 0.5 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 0.5 | 2026-08-07 | 0.5 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 16 |  | 2
38 | Assessments | 2026-07-31 | assessments/import.aspx ¦ RadGrid, | Pod 2 | Pod 1_Member2 | 2026-07-31 | 3 | 0 | 4 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-05 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 0.5 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 0.5 | 2026-08-07 | 0.5 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 16 |  | 2
39 | Assessments | 2026-07-31 | assessments/question.aspx ¦ RadAjax | Pod 2 | Pod 1_Member3 | 2026-07-31 | 3 | 0 | 5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-05 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 0.5 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 0.5 | 2026-08-07 | 0.5 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 16 | 9 | 2 |  |  | 11
43 | Assessments | 2026-07-31 | assessments/questionManager.aspx ¦ | Pod 2 | Pod 3_Member1 | 2026-07-31 | 3 | 0 | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-05 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 0.5 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 0.5 | 2026-08-07 | 0.5 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 16 |  | 2
44 | Assessments | 2026-07-31 | assessments/questions.aspx ¦ RadGri | Pod 2 | Pod 3_Member2 | 2026-07-31 | 3 | 0 | 2 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 0.5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-05 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 0.5 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 0.5 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 0.5 | 2026-08-07 | 0.5 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 16 |  | 2
45 | AssetAware | 2026-05-15 | assetAware/asset.aspx | Pod 4 | Pod 2_Member1 | 2026-05-15 | 3 | 0 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 0.5 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 0.5 | 2026-05-21 | 2026-06-01 | 1 | 2026-06-03 | 0.5 | 2026-06-03 | 0.5 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-10 | 2026-06-11 | 23 |  | 2
46 | AssetAware | 2026-05-15 | assetAware/assets.aspx | Pod 4 | Pod 1_Member1 | 2026-05-15 | 3 | 0 | 4 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 0.5 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 0.5 | 2026-05-21 | 2026-06-01 | 1 | 2026-06-03 | 0.5 | 2026-06-03 | 0.5 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-10 | 2026-06-11 | 23 |  | 2
47 | AssetAware | 2026-05-15 | assetAware/assetVendorAddressContact.aspx | Pod 4 | Pod 3_Member1 | 2026-05-15 | 3 | 0 | 5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 0.5 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 0.5 | 2026-05-21 | 2026-06-01 | 1 | 2026-06-03 | 0.5 | 2026-06-03 | 0.5 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-10 | 2026-06-11 | 23 |  | 2
48 | AssetAware | 2026-05-25 | assetAware/assetHistory.aspx | Pod 4 | Pod 2_Member1 | 2026-05-25 | 3 | 0 | 6 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 0.5 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 0.5 | 2026-06-01 | 2026-06-01 | 1 | 2026-06-03 | 0.5 | 2026-06-03 | 0.5 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-10 | 2026-06-11 | 15 |  | 2
49 | Communication | 2026-05-25 | communication/webmail/webmailBox.aspx ¦ RadGr | Pod 4 | Pod 1_Member1 | 2026-05-25 | 3 | 0 | 7 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 0.5 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 0.5 | 2026-06-01 | 2026-06-09 | 1 | 2026-06-10 | 0.5 | 2026-06-10 | 0.5 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-17 | 2026-06-25 | 29 |  | 2
50 | Communication | 2026-05-25 | communication/webmail/settings.aspx ¦ RadAjax | Pod 4 | Pod 3_Member1 | 2026-05-25 | 3 | 0 | 8 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 0.5 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 0.5 | 2026-06-01 | 2026-06-09 | 1 | 2026-06-10 | 0.5 | 2026-06-10 | 0.5 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-17 | 2026-06-25 | 29 | 13 | 2 |  |  | 15
61 | Communication | 2026-06-02 | communication/webmail/autoReplySettings.aspx | Pod 4 | Pod 1_Member1 | 2026-06-02 | 3 | 0 | 1 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 0.5 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 0.5 | 2026-06-10 | 0.5 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-17 | 2026-06-25 | 20 |  | 2
62 | Communication | 2026-06-02 | communication/webmail/signatureSettings.aspx | Pod 4 | Pod 2_Member1 | 2026-06-02 | 3 | 0 | 2 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 0.5 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 0.5 | 2026-06-10 | 0.5 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-17 | 2026-06-25 | 20 |  | 2
63 | Content | 2026-06-02 | content/captionedVideoItem.aspx ¦ | Pod 4 | Pod 3_Member1 | 2026-06-02 | 3 | 0 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 0.5 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-16 | 1 | 2026-06-17 | 0.5 | 2026-06-17 | 0.5 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-24 | 2026-06-25 | 20 |  | 2
64 | Content | 2026-06-10 | content/chrome/online/footer.aspx | Pod 4 | Pod 1_Member1 | 2026-06-10 | 3 | 0 | 4 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 0.5 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 0.5 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 0.5 | 2026-06-17 | 0.5 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-24 | 2026-06-25 | 13 |  | 2
65 | Content | 2026-06-10 | content/elmItemInteractive.aspx ¦ | Pod 4 | Pod 3_Member1 | 2026-06-10 | 3 | 0 | 5 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 0.5 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 0.5 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 0.5 | 2026-06-17 | 0.5 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-24 | 2026-06-25 | 13 |  | 2
66 | Content | 2026-06-10 | content/hyperlink.aspx ¦ RadAjaxM | Pod 4 | Pod 2_Member1 | 2026-06-10 | 3 | 0 | 6 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 0.5 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 0.5 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 0.5 | 2026-06-17 | 0.5 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-24 | 2026-06-25 | 13 |  | 2
67 | Enrollment | 2026-05-05 | enrollment/placement/placementHelp.aspx | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 7 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 0.5 | 2026-05-11 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 49 |  | 2
68 | Enrollment | 2026-05-14 | enrollment/placement/manager.aspx ¦ RadG | Pod 1 | Pod 1_Member1 | 2026-05-14 | 3 | 0 | 8 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 38 |  | 2
69 | Enrollment | 2026-05-14 | enrollment/placement/rejectReason.aspx ¦ | Pod 1 | Pod 1_Member2 | 2026-05-14 | 3 | 0 | 9 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 38 |  | 2
70 | Enrollment | 2026-05-14 | enrollment/registration/registrationLoca | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 10 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 38 | 14 | 2 |  |  | 16
1 | Enrollment | 2026-05-22 | enrollment/registration/default.aspx ¦ R | Pod 1 | Pod 1_Member1 | 2026-05-22 | 3 | 0 | 1 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 30 |  | 2
2 | Enrollment | 2026-05-22 | enrollment/registration/registrationLoca | Pod 1 | Pod 1_Member2 | 2026-05-22 | 3 | 0 | 2 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 30 |  | 2
3 | Enrollment | 2026-05-22 | enrollment/registration/registrantFamily | Pod 1 | Pod 1_Member3 | 2026-05-22 | 3 | 0 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 30 |  | 2
4 | Enrollment | 2026-06-01 | enrollment/registration/resendEmail.aspx | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 4 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 21 |  | 2
5 | ExtendedField | 2026-04-15 | extendedField/extendedField.aspx ¦ RadAjax | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 5 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 0.5 | 2026-04-21 | 2026-05-11 | 1 | 2026-05-12 | 0.5 | 2026-05-12 | 0.5 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-19 | 2026-05-28 | 41 |  | 2
6 | ExtendedField | 2026-04-15 | extendedField/default.aspx ¦ RadGrid, RadA | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 6 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 0.5 | 2026-04-21 | 2026-05-11 | 1 | 2026-05-12 | 0.5 | 2026-05-12 | 0.5 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-19 | 2026-05-28 | 41 |  | 2
7 | ExtendedField | 2026-04-15 | extendedField/associations.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 7 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 0.5 | 2026-04-21 | 2026-05-11 | 1 | 2026-05-12 | 0.5 | 2026-05-12 | 0.5 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-19 | 2026-05-28 | 41 |  | 2
8 | ExtendedField | 2026-04-24 | extendedField/calculationGroupExtendedFiel | Pod 1 | Pod 1_Member1 | 2026-04-24 | 3 | 0 | 8 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 0.5 | 2026-04-30 | 2026-05-11 | 1 | 2026-05-12 | 0.5 | 2026-05-12 | 0.5 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-19 | 2026-05-28 | 30 |  | 2
9 | ExtendedField | 2026-04-24 | extendedField/extendedFieldConfirmRecalcul | Pod 1 | Pod 1_Member2 | 2026-04-24 | 3 | 0 | 9 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 0.5 | 2026-04-30 | 2026-05-11 | 1 | 2026-05-12 | 0.5 | 2026-05-12 | 0.5 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-19 | 2026-05-28 | 30 |  | 2
10 | ExtendedField | 2026-04-24 | extendedField/fieldHistory.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member3 | 2026-04-24 | 3 | 0 | 10 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 0.5 | 2026-04-30 | 2026-05-11 | 1 | 2026-05-12 | 0.5 | 2026-05-12 | 0.5 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-19 | 2026-05-28 | 30 |  | 2
11 | ExtendedField | 2026-05-05 | extendedField/dataview/dataview.aspx ¦ Rad | Pod 1 | Pod 1_Member1 | 2026-05-05 | 3 | 0 | 11 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 0.5 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 0.5 | 2026-05-12 | 0.5 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-19 | 2026-05-28 | 21 |  | 2
12 | ExtendedField | 2026-05-05 | extendedField/dataview/logEntryFilter.aspx | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 12 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 0.5 | 2026-05-11 | 2026-05-11 | 1 | 2026-05-12 | 0.5 | 2026-05-12 | 0.5 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-19 | 2026-05-28 | 21 |  | 2
13 | GradeBook | 2026-04-15 | page_3 | Pod 2 | Pod 2_Member1 | 2026-04-15 | 3 | 0 | 13 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 0.5 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 0.5 | 2026-04-22 | 0.5 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-29 | 2026-04-30 | 13 |  | 2
14 | GradeBook | 2026-04-15 | page_4 | Pod 2 | Pod 2_Member2 | 2026-04-15 | 3 | 0 | 14 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 0.5 | 2026-04-21 | 2026-04-21 | 1 | 2026-04-22 | 0.5 | 2026-04-22 | 0.5 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-29 | 2026-04-30 | 13 |  | 2
15 | Home | 2026-06-25 | home/pages/teacherBeta.aspx | Pod 3 | Pod 3_Member3 | 2026-06-25 | 3 | 0 | 15 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 0.5 | 2026-07-02 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 23 |  | 2
16 | Home | 2026-07-03 | home/pages/caretaker.aspx ¦ | Pod 3 | Pod 3_Member1 | 2026-07-03 | 3 | 0 | 16 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 0.5 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 15 |  | 2
17 | Home | 2026-07-03 | home/pages/teacher.aspx ¦ R | Pod 3 | Pod 3_Member2 | 2026-07-03 | 3 | 0 | 17 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 0.5 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 15 |  | 2
18 | Home | 2026-07-03 | home/pages/enrollment.aspx | Pod 3 | Pod 3_Member3 | 2026-07-03 | 3 | 0 | 18 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 0.5 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 15 |  | 2
19 | IssueAware | 2026-04-15 | page_1 | Pod 2 | Pod 2_Member3 | 2026-04-15 | 3 | 0 | 19 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 0.5 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 0.5 | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 0.5 | 2026-04-21 | 2026-04-30 | 1 | 2026-05-04 | 0.5 | 2026-05-04 | 0.5 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-11 | 2026-05-14 | 27 |  | 2
20 | IssueAware | 2026-04-24 | page_2 | Pod 2 | Pod 2_Member1 | 2026-04-24 | 3 | 0 | 20 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 0.5 | 2026-04-30 | 2026-04-30 | 1 | 2026-05-04 | 0.5 | 2026-05-04 | 0.5 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-11 | 2026-05-14 | 16 |  | 2
21 | Library | 2026-07-15 | library/resource.aspx ¦ Ra | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 21 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 0.5 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 0.5 | 2026-07-22 | 0.5 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-29 | 2026-08-06 | 20 |  | 2
22 | Library | 2026-07-15 | library/searchResults.aspx | Pod 3 | Pod 3_Member2 | 2026-07-15 | 3 | 0 | 22 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 0.5 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 0.5 | 2026-07-22 | 0.5 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-29 | 2026-08-06 | 20 |  | 2
23 | Library | 2026-07-15 | library/userSelector.aspx | Pod 3 | Pod 3_Member3 | 2026-07-15 | 3 | 0 | 23 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 0.5 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 0.5 | 2026-07-22 | 0.5 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-29 | 2026-08-06 | 20 |  | 2
24 | LMU | 2026-04-24 | page_2 | Pod 2 | Pod 2_Member2 | 2026-04-24 | 3 | 0 | 24 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 0.5 | 2026-04-30 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 86 |  | 2
25 | LMU | 2026-04-24 | page_3 | Pod 2 | Pod 2_Member3 | 2026-04-24 | 3 | 0 | 25 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 0.5 | 2026-04-30 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 86 |  | 2
26 | LMU | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-05 | 3 | 0 | 26 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 0.5 | 2026-05-11 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 77 | 8 | 2 |  |  | 10
71 | LMU | 2026-05-05 | page_5 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 0.5 | 2026-05-11 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 77 |  | 2
72 | LMU | 2026-05-05 | page_6 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 0.5 | 2026-05-11 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 77 |  | 2
73 | LMU | 2026-05-14 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 66 |  | 2
74 | LMU | 2026-05-14 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 66 |  | 2
75 | LMU | 2026-05-14 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-14 | 3 | 0 | 5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 66 |  | 2
76 | LMU | 2026-05-22 | page_7 | Pod 2 | Pod 2_Member1 | 2026-05-22 | 3 | 0 | 6 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 58 |  | 2
77 | LMU | 2026-05-22 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-22 | 3 | 0 | 7 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 58 | 8 | 2
40 | LMU | 2026-05-22 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-22 | 3 | 0 | 1 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 58 |  | 2
41 | LMU | 2026-06-01 | page_10 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 2 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 49 |  | 2
42 | LMU | 2026-06-01 | page_14 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 49 | 8 | 2 |  |  | 10
78 | LMU | 2026-06-01 | page_15 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 49 |  | 2
79 | LMU | 2026-06-09 | page_13 | Pod 2 | Pod 2_Member1 | 2026-06-09 | 3 | 0 | 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 42 |  | 2
80 | LMU | 2026-06-09 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-09 | 3 | 0 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 42 |  | 2
81 | LMU | 2026-06-09 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-09 | 3 | 0 | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 42 |  | 2
82 | LMU | 2026-06-17 | page_16 | Pod 2 | Pod 2_Member1 | 2026-06-17 | 3 | 0 | 5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 34 |  | 2
83 | LMU | 2026-06-17 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-17 | 3 | 0 | 6 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 34 |  | 2
84 | LMU | 2026-06-17 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-17 | 3 | 0 | 7 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 34 |  | 2
85 | LMU | 2026-06-25 | page_19 | Pod 2 | Pod 2_Member1 | 2026-06-25 | 3 | 0 | 8 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 0.5 | 2026-07-02 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 23 | 8 | 2 |  |  | 10
96 | LMU | 2026-06-25 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-25 | 3 | 0 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 0.5 | 2026-07-02 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 23 |  | 2
97 | LMU | 2026-06-25 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-25 | 3 | 0 | 2 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 0.5 | 2026-07-02 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 23 |  | 2
98 | LMU | 2026-07-03 | page_22 | Pod 2 | Pod 2_Member1 | 2026-07-03 | 3 | 0 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 0.5 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 15 |  | 2
99 | LMU | 2026-07-03 | page_25 | Pod 2 | Pod 2_Member3 | 2026-07-03 | 3 | 0 | 4 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 0.5 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 15 |  | 2
100 | LMU | 2026-07-03 | page_26 | Pod 2 | Pod 2_Member2 | 2026-07-03 | 3 | 0 | 5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 0.5 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 15 |  | 2
101 | Location | 2026-04-24 | location/createHouseholdLinkExisting | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 6 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 0.5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 0.5 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 0.5 | 2026-04-30 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 58 |  | 2
102 | Location | 2026-05-05 | location/addressContact.aspx ¦ RadAj | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 7 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 0.5 | 2026-05-11 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 49 |  | 2
103 | Location | 2026-05-05 | location/createHousehold.aspx ¦ RadA | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 8 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 0.5 | 2026-05-11 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 49 |  | 2
104 | Location | 2026-05-05 | location/locationExtended.aspx ¦ Rad | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 9 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 0.5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 0.5 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 0.5 | 2026-05-11 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 49 |  | 2
105 | Location | 2026-05-14 | location/dataview.aspx ¦ RadGrid, Ra | Pod 3 | Pod 3_Member1 | 2026-05-14 | 3 | 0 | 10 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 38 |  | 2
106 | Location | 2026-05-14 | location/extendedFields.aspx ¦ RadGr | Pod 3 | Pod 3_Member2 | 2026-05-14 | 3 | 0 | 11 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 38 | 14 | 2 |  |  | 16
112 | Location | 2026-05-14 | location/security/roleWebusers.aspx | Pod 3 | Pod 3_Member3 | 2026-05-14 | 3 | 0 | 1 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 0.5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 0.5 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 0.5 | 2026-05-20 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 38 |  | 2
113 | Location | 2026-05-22 | location/skinProperties.aspx ¦ RadAj | Pod 3 | Pod 3_Member1 | 2026-05-22 | 3 | 0 | 2 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 30 |  | 2
114 | Location | 2026-05-22 | location/reports/allUsersInRoleExten | Pod 3 | Pod 3_Member2 | 2026-05-22 | 3 | 0 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 30 |  | 2
115 | Location | 2026-05-22 | AdditionalPage 1 | Pod 3 | Pod 3_Member3 | 2026-05-22 | 3 | 0 | 4 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 0.5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 0.5 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 0.5 | 2026-05-29 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 30 | 14 | 2 |  |  | 16
51 | Location | 2026-06-01 | AdditionalPage 2 | Pod 3 | Pod 3_Member1 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-06-08 | 1 | 2026-06-09 | 0.5 | 2026-06-09 | 0.5 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-25 | 21 |  | 2
52 | Log | 2026-07-15 | log/default.aspx ¦ RadGrid, RadAjaxManager, RadDa | Pod 2 | Pod 2_Member1 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 0.5 | 2026-07-21 | 2026-07-29 | 1 | 2026-07-30 | 0.5 | 2026-07-30 | 0.5 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 20 |  | 2
53 | Log | 2026-07-15 | log/logEntry.aspx ¦ RadGrid, RadAjaxManager, RadT | Pod 2 | Pod 2_Member2 | 2026-07-15 | 3 | 0 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 0.5 | 2026-07-21 | 2026-07-29 | 1 | 2026-07-30 | 0.5 | 2026-07-30 | 0.5 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 20 |  | 2
54 | Log | 2026-07-15 | log/areas.aspx ¦ RadGrid, RadAjaxManager ¦ Medium | Pod 2 | Pod 2_Member3 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 0.5 | 2026-07-21 | 2026-07-29 | 1 | 2026-07-30 | 0.5 | 2026-07-30 | 0.5 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 20 |  | 2
55 | Log | 2026-07-23 | log/categories.aspx ¦ RadGrid, RadAjaxManager ¦ M | Pod 2 | Pod 2_Member1 | 2026-07-23 | 3 | 0 | 5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 0.5 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 0.5 | 2026-07-30 | 0.5 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 10 |  | 2
56 | Log | 2026-07-23 | log/contactTypes.aspx ¦ RadGrid, RadAjaxManager ¦ | Pod 2 | Pod 2_Member2 | 2026-07-23 | 3 | 0 | 6 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 0.5 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 0.5 | 2026-07-30 | 0.5 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 10 |  | 2
57 | Log | 2026-07-23 | log/logEntrySystems.aspx ¦ RadGrid, RadAjaxManage | Pod 2 | Pod 2_Member3 | 2026-07-23 | 3 | 0 | 7 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 0.5 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 0.5 | 2026-07-30 | 0.5 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 10 |  | 2
58 | Log | 2026-07-23 | log/myLogSettings.aspx ¦ RadGrid, RadAjaxManager, | Pod 2 | Pod 1_Member1 | 2026-07-23 | 3 | 0 | 8 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 0.5 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 0.5 | 2026-07-30 | 0.5 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 10 |  | 2
59 | Log | 2026-07-23 | log/systemProperties.aspx ¦ RadAjaxManager, RadHe | Pod 2 | Pod 1_Member2 | 2026-07-23 | 3 | 0 | 9 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 0.5 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 0.5 | 2026-07-30 | 0.5 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 10 |  | 2
60 | Log | 2026-07-23 | log/areaCategoryWindow.aspx ¦ RadTreeView, RadAja | Pod 2 | Pod 1_Member3 | 2026-07-23 | 3 | 0 | 10 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 0.5 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 0.5 | 2026-07-30 | 0.5 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 10 | 3 | 2 |  |  | 5
107 | Log | 2026-07-23 | log/specialPopulations/logSpecialPopulations.aspx | Pod 2 | Pod 3_Member1 | 2026-07-23 | 3 | 0 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 0.5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 0.5 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 0.5 | 2026-07-29 | 2026-07-29 | 1 | 2026-07-30 | 0.5 | 2026-07-30 | 0.5 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 10 |  | 2
108 | OrderAware | 2026-06-18 | page_5 | Pod 4 | Pod 2_Member1 | 2026-06-18 | 3 | 0 | 2 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 0.5 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 0.5 | 2026-06-24 | 2026-07-03 | 1 | 2026-07-06 | 0.5 | 2026-07-06 | 0.5 | 2026-07-06 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 31 |  | 2
109 | OrderAware | 2026-06-18 | page_6 | Pod 4 | Pod 3_Member1 | 2026-06-18 | 3 | 0 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 0.5 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 0.5 | 2026-06-24 | 2026-07-03 | 1 | 2026-07-06 | 0.5 | 2026-07-06 | 0.5 | 2026-07-06 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 31 |  | 2
110 | OrderAware | 2026-06-18 | page_7 | Pod 4 | Pod 1_Member1 | 2026-06-18 | 3 | 0 | 4 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 0.5 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 0.5 | 2026-06-24 | 2026-07-03 | 1 | 2026-07-06 | 0.5 | 2026-07-06 | 0.5 | 2026-07-06 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 31 |  | 2
111 | OrderAware | 2026-06-26 | page_8 | Pod 4 | Pod 2_Member1 | 2026-06-26 | 3 | 0 | 5 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 0.5 | 2026-07-02 | 0.5 | 2026-07-02 | 0.5 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-03 | 1 | 2026-07-06 | 0.5 | 2026-07-06 | 0.5 | 2026-07-06 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 22 |  | 2
125 | ProgressionPlan | 2026-06-01 | progressionPlan/academicRequirement.aspx ¦ RadGrid, Ra | Pod 1 | Pod 1_Member2 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-06-23 | 1 | 2026-06-24 | 0.5 | 2026-06-24 | 0.5 | 2026-06-24 | 2026-06-25 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 35 |  | 2
126 | ProgressionPlan | 2026-06-01 | progressionPlan/academicRequirements.aspx ¦ RadGrid, R | Pod 1 | Pod 1_Member3 | 2026-06-01 | 3 | 0 | 2 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-06-23 | 1 | 2026-06-24 | 0.5 | 2026-06-24 | 0.5 | 2026-06-24 | 2026-06-25 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 35 |  | 2
127 | ProgressionPlan | 2026-06-09 | progressionPlan/progressionPlan.aspx ¦ RadGrid, RadAja | Pod 1 | Pod 1_Member1 | 2026-06-09 | 3 | 0 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-06-23 | 1 | 2026-06-24 | 0.5 | 2026-06-24 | 0.5 | 2026-06-24 | 2026-06-25 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 28 |  | 2
128 | ProgressionPlan | 2026-06-09 | progressionPlan/completionRequirements.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member2 | 2026-06-09 | 3 | 0 | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-06-23 | 1 | 2026-06-24 | 0.5 | 2026-06-24 | 0.5 | 2026-06-24 | 2026-06-25 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 28 | 10 | 2 |  |  | 12
86 | ProgressionPlan | 2026-06-09 | progressionPlan/webusers.aspx ¦ RadGrid, RadAjaxManage | Pod 1 | Pod 1_Member3 | 2026-06-09 | 3 | 0 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-06-23 | 1 | 2026-06-24 | 0.5 | 2026-06-24 | 0.5 | 2026-06-24 | 2026-06-25 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 28 |  | 2
87 | ProgressionPlan | 2026-06-17 | progressionPlan/completionRequirement.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member1 | 2026-06-17 | 3 | 0 | 2 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 0.5 | 2026-06-24 | 0.5 | 2026-06-24 | 2026-06-25 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 20 |  | 2
88 | ProgressionPlan | 2026-06-17 | progressionPlan/help/progressionPlansSelectorHelp.aspx | Pod 1 | Pod 1_Member2 | 2026-06-17 | 3 | 0 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 0.5 | 2026-06-24 | 0.5 | 2026-06-24 | 2026-06-25 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 20 |  | 2
89 | Reg+Attendance | 2026-06-17 | registration.aspx | Pod 1 | Pod 1_Member3 | 2026-06-17 | 3 | 0 | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 34 |  | 2
90 | Reg+Attendance | 2026-06-25 | attendance/enterAttendance.aspx | Pod 1 | Pod 1_Member1 | 2026-06-25 | 3 | 0 | 5 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 0.5 | 2026-07-02 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 23 |  | 2
91 | Reg+Attendance | 2026-06-25 | attendance/editRecord.aspx ¦ Ra | Pod 1 | Pod 1_Member2 | 2026-06-25 | 3 | 0 | 6 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 0.5 | 2026-07-02 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 23 |  | 2
92 | Reg+Attendance | 2026-06-25 | AdditionalPage 1 | Pod 1 | Pod 1_Member3 | 2026-06-25 | 3 | 0 | 7 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 0.5 | 2026-07-02 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 23 |  | 2
93 | Reg+Attendance | 2026-07-03 | AdditionalPage 2 | Pod 1 | Pod 1_Member1 | 2026-07-03 | 3 | 0 | 8 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 0.5 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 0.5 | 2026-07-13 | 0.5 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 2026-07-23 | 15 |  | 2
94 | Reports | 2026-07-03 | reports/institutionalStudentPerformanceE | Pod 1 | Pod 1_Member2 | 2026-07-03 | 3 | 0 | 9 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 0.5 | 2026-07-10 | 2026-07-21 | 1 | 2026-07-22 | 0.5 | 2026-07-22 | 0.5 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-29 | 2026-08-06 | 29 |  | 2
95 | Reports | 2026-07-03 | reports/resourceManagerExport.aspx ¦ Rad | Pod 1 | Pod 1_Member3 | 2026-07-03 | 3 | 0 | 10 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 0.5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 0.5 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 2026-07-10 | 0.5 | 2026-07-10 | 2026-07-21 | 1 | 2026-07-22 | 0.5 | 2026-07-22 | 0.5 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-29 | 2026-08-06 | 29 | 13 | 2 |  |  | 15
116 | Reports | 2026-07-15 | reports/aggregateLogEntry.aspx ¦ RadGrid | Pod 1 | Pod 1_Member1 | 2026-07-15 | 3 | 0 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 0.5 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 0.5 | 2026-07-22 | 0.5 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-29 | 2026-08-06 | 20 |  | 2
117 | Reports | 2026-07-15 | reports/sectionLogEntryReport.aspx ¦ Rad | Pod 1 | Pod 1_Member3 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 0.5 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 0.5 | 2026-07-22 | 0.5 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-29 | 2026-08-06 | 20 |  | 2
118 | Reports | 2026-07-15 | reports/SectionObjectivePerformance.aspx | Pod 1 | Pod 1_Member2 | 2026-07-15 | 3 | 0 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 0.5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 0.5 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 0.5 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 0.5 | 2026-07-22 | 0.5 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-29 | 2026-08-06 | 20 |  | 2
119 | Webuser | 2026-06-01 | webuser/contactInformationHistory.aspx | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 0 | 4 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-07-02 | 1 | 2026-07-03 | 0.5 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 49 |  | 2
120 | Webuser | 2026-06-01 | webuser/dataview.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 | 0 | 5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 0.5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 0.5 | 2026-06-05 | 2026-06-05 | 2026-06-08 | 2026-06-08 | 0.5 | 2026-06-08 | 2026-07-02 | 1 | 2026-07-03 | 0.5 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 49 | 15 | 2 |  |  | 17
132 | Webuser | 2026-06-09 | webuser/addressContact.aspx ¦ RadAjaxM | Pod 3 | Pod 3_Member1 | 2026-06-09 | 3 | 0 | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-07-02 | 1 | 2026-07-03 | 0.5 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 42 | 15 | 2 |  |  | 17
121 | Webuser | 2026-06-09 | webuser/expressEdit.aspx ¦ RadAjaxMana | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 | 0 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-07-02 | 1 | 2026-07-03 | 0.5 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 42 |  | 2
122 | Webuser | 2026-06-09 | webuser/expressUserSelection.aspx ¦ Ra | Pod 3 | Pod 3_Member3 | 2026-06-09 | 3 | 0 | 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 0.5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 0.5 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 0.5 | 2026-06-15 | 2026-07-02 | 1 | 2026-07-03 | 0.5 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 42 |  | 2
123 | Webuser | 2026-06-17 | webuser/dataviewList.aspx ¦ RadGrid, R | Pod 3 | Pod 3_Member1 | 2026-06-17 | 3 | 0 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-07-02 | 1 | 2026-07-03 | 0.5 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 34 |  | 2
124 | Webuser | 2026-06-17 | webuser/webusers.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member2 | 2026-06-17 | 3 | 0 | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-07-02 | 1 | 2026-07-03 | 0.5 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 34 | 15 | 2 |  |  | 17
129 | Webuser | 2026-06-17 | webuser/overview.aspx ¦ RadTabStrip, R | Pod 3 | Pod 3_Member3 | 2026-06-17 | 3 | 0 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 0.5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 0.5 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 0.5 | 2026-06-23 | 2026-07-02 | 1 | 2026-07-03 | 0.5 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 34 |  | 2
130 | Webuser | 2026-06-25 | webuser/webuserExtended.aspx ¦ RadGrid | Pod 3 | Pod 3_Member1 | 2026-06-25 | 3 | 0 | 2 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 0.5 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 0.5 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 23 |  | 2
131 | Webuser | 2026-06-25 | webuser/sections.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member2 | 2026-06-25 | 3 | 0 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 0.5 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 0.5 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 0.5 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 0.5 | 2026-07-03 | 0.5 | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 23 | 15 | 2
Formulas:
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Pearson Regression Testing/UAT Date = MAX(IF(B2:B133=[Module], AI2:AI133))
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
TEST Deployment = WORKDAY([PR Response receive Date], 1, IndHolidays)
Release Request Approved Date = WORKDAY([Release Request Raise Date], 3, IndHolidays)
Release Date (2-Wk Cycle) = CEILING([Release Request Approved Date]-DATE(2026,4,16), 14)+DATE(2026,4,16)

## With POD-4-NEW (hidden)
No. | Module | Recieved Functional & Non Fuctional Walkthrough | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Code Freeze Date | TEST Deployment | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | Code freeze date = Release cutoff Date | Release # | Release Request Approved Date | Release Date (2-Wk Cycle) | Code freeze date = Release cutoff Date | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
1 | AddressBook | Yes | 2026-04-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | #VALUE! | 41 |  | 9
2 | AddressBook | Yes | 2026-04-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
3 | AddressBook | Yes | 2026-04-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
4 | AddressBook | Yes | 2026-04-24 | page_4 | Pod 3 | Pod 3_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
5 | AddressBook | Yes | 2026-04-24 | page_5 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 3 | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 | #VALUE! | 9 |  |  | #VALUE!
6 | Assessments | Yes | 2026-07-23 | page_1 | Pod 3 | Pod 3_Member2 | 2026-07-23 | 3 | 0 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
7 | Assessments | Yes | 2026-07-23 | page_2 | Pod 3 | Pod 3_Member3 | 2026-07-23 | 3 | 0 | 2 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
8 | Assessments | Yes | 2026-07-31 | page_3 | Pod 2 | Pod 2_Member3 | 2026-07-31 | 3 | 0 | 3 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
9 | Assessments | Yes | 2026-07-31 | page_4 | Pod 2 | Pod 2_Member1 | 2026-07-31 | 3 | 0 | 4 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
10 | Assessments | Yes | 2026-07-31 | page_5 | Pod 2 | Pod 2_Member2 | 2026-07-31 | 3 | 0 | 5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
11 | Assessments | Yes | 2026-07-31 | page_6 | Pod 1 | Pod 1_Member1 | 2026-07-31 | 3 | 0 | 6 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
12 | Assessments | Yes | 2026-07-31 | page_7 | Pod 1 | Pod 1_Member2 | 2026-07-31 | 3 | 0 | 7 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
13 | Assessments | Yes | 2026-07-31 | page_8 | Pod 1 | Pod 1_Member3 | 2026-07-31 | 3 | 0 | 8 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 | #VALUE! | 9 |  |  | #VALUE!
14 | Assessments | Yes | 2026-07-31 | page_9 | Pod 3 | Pod 3_Member1 | 2026-07-31 | 3 | 0 | 9 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-27 |  | 2026-08-27 | 0 | 2026-08-27 | 0 | 2026-08-27 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 30 |  | 9
15 | Assessments | Yes | 2026-07-31 | page_10 | Pod 3 | Pod 3_Member2 | 2026-07-31 | 3 | 0 | 10 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 3 | 2026-08-19 | 2 | 2026-08-24 | 3 | 2026-08-28 | 2026-08-28 | 2026-08-31 | 2026-08-31 | 1 | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 3 | 2026-09-07 | 0 | 2026-09-07 | 0 | 2026-09-07 | 2026-09-10 | Release 19 | #VALUE! | 2026-09-17 | 2026-09-10 | 44 |  | 9
16 | AssetAware | No | 2026-05-15 | page_1 | Pod 4 | Pod 4_Member1 | 2026-05-15 | 3 | 0 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
17 | AssetAware | No | 2026-05-15 | page_2 | Pod 4 | Pod 4_Member1 | 2026-05-15 | 3 | 0 | 2 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
18 | AssetAware | No | 2026-05-15 | page_3 | Pod 4 | Pod 4_Member3 | 2026-05-15 | 3 | 0 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 1.5 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 |  | 2026-06-01 | 2 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 |  | 2026-06-11 | 0 | 2026-06-11 | 0 | 2026-06-11 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 37 |  | 9
19 | AssetAware | No | 2026-05-25 | page_4 | Pod 4 | Pod 4_Member2 | 2026-05-25 | 3 | 0 | 4 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 3 | 2026-07-01 | 0 | 2026-07-01 | 0 | 2026-07-01 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 43 |  | 9
20 | Communication | No | 2026-05-25 | page_1 | Pod 4 | Pod 4_Member1 | 2026-05-25 | 3 | 0 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 29 |  | 9
21 | Communication | No | 2026-05-25 | page_2 | Pod 4 | Pod 4_Member3 | 2026-05-25 | 3 | 0 | 2 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 1.5 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 |  | 2026-06-10 | 2 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 |  | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-19 |  | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 29 |  | 9
22 | Communication | No | 2026-06-02 | page_3 | Pod 4 | Pod 4_Member1 | 2026-06-02 | 3 | 0 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 |  | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 34 |  | 9
23 | Communication | No | 2026-06-02 | page_4 | Pod 4 | Pod 4_Member2 | 2026-06-02 | 3 | 0 | 4 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 3 | 2026-07-09 | 0 | 2026-07-09 | 0 | 2026-07-09 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 34 | #VALUE! | 9 |  |  | #VALUE!
24 | Content | No | 2026-06-02 | page_1 | Pod 4 | Pod 4_Member3 | 2026-06-02 | 3 | 0 | 1 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1.5 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2 | 2026-06-19 | 3 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 |  | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 |  | 2026-06-29 | 0 | 2026-06-29 | 0 | 2026-06-29 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 34 |  | 9
25 | Content | No | 2026-06-10 | page_2 | Pod 4 | Pod 4_Member1 | 2026-06-10 | 3 | 0 | 2 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
26 | Content | No | 2026-06-10 | page_3 | Pod 4 | Pod 4_Member3 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 |  | 2026-07-06 | 0 | 2026-07-06 | 0 | 2026-07-06 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
27 | Content | No | 2026-06-10 | page_4 | Pod 4 | Pod 4_Member2 | 2026-06-10 | 3 | 0 | 4 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 1.5 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 3 | 2026-07-16 | 0 | 2026-07-16 | 0 | 2026-07-16 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 41 |  | 9
28 | Enrollment | No | 2026-05-05 | page_1 | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
29 | Enrollment | No | 2026-05-14 | page_2 | Pod 1 | Pod 1_Member1 | 2026-05-14 | 3 | 0 | 2 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
30 | Enrollment | No | 2026-05-14 | page_3 | Pod 1 | Pod 1_Member2 | 2026-05-14 | 3 | 0 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
31 | Enrollment | No | 2026-05-14 | page_4 | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
32 | Enrollment | No | 2026-05-22 | page_5 | Pod 1 | Pod 1_Member1 | 2026-05-22 | 3 | 0 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
33 | Enrollment | No | 2026-05-22 | page_6 | Pod 1 | Pod 1_Member2 | 2026-05-22 | 3 | 0 | 6 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
34 | Enrollment | No | 2026-05-22 | page_7 | Pod 1 | Pod 1_Member3 | 2026-05-22 | 3 | 0 | 7 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
35 | Enrollment | No | 2026-06-01 | page_8 | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 8 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
36 | ExtendedField | Yes | 2026-04-15 | page_1 | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
37 | ExtendedField | Yes | 2026-04-15 | page_2 | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
38 | ExtendedField | Yes | 2026-04-15 | page_3 | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 3 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
39 | ExtendedField | Yes | 2026-04-24 | page_4 | Pod 1 | Pod 1_Member1 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
40 | ExtendedField | Yes | 2026-04-24 | page_5 | Pod 1 | Pod 1_Member2 | 2026-04-24 | 3 | 0 | 5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
41 | ExtendedField | Yes | 2026-04-24 | page_6 | Pod 1 | Pod 1_Member3 | 2026-04-24 | 3 | 0 | 6 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
42 | ExtendedField | Yes | 2026-05-05 | page_7 | Pod 1 | Pod 1_Member1 | 2026-05-05 | 3 | 0 | 7 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
43 | ExtendedField | Yes | 2026-05-05 | page_8 | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 8 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
44 | GradeBook | Yes | 2026-04-15 | page_3 | Pod 2 | Pod 2_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 3 | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
45 | GradeBook | Yes | 2026-04-15 | page_4 | Pod 2 | Pod 2_Member2 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2 | 2026-05-07 | 3 | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 1 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 3 | 2026-05-20 | 1 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 12
46 | Home | No | 2026-06-25 | page_1 | Pod 3 | Pod 3_Member3 | 2026-06-25 | 3 | 0 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
47 | Home | No | 2026-07-03 | page_2 | Pod 3 | Pod 3_Member1 | 2026-07-03 | 3 | 0 | 2 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 |  | 9
48 | Home | No | 2026-07-03 | page_3 | Pod 3 | Pod 3_Member2 | 2026-07-03 | 3 | 0 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 |  | 9
49 | Home | No | 2026-07-03 | page_4 | Pod 3 | Pod 3_Member3 | 2026-07-03 | 3 | 0 | 4 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 2 | 2026-07-27 | 3 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-04 | 3 | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 43 | #VALUE! | 9 |  |  | #VALUE!
50 | IssueAware | Yes | 2026-04-15 | page_1 | Pod 2 | Pod 2_Member3 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 1.5 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 |  | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 |  | 2026-05-11 | 0 | 2026-05-11 | 0 | 2026-05-11 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 41 |  | 9
51 | IssueAware | Yes | 2026-04-24 | page_2 | Pod 2 | Pod 2_Member1 | 2026-04-24 | 3 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 3 | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 9
52 | Library | Yes | 2026-07-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
53 | Library | Yes | 2026-07-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
54 | Library | Yes | 2026-07-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-07-15 | 3 | 0 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 3 | 2026-08-03 | 2 | 2026-08-05 | 3 | 2026-08-10 | 2026-08-10 | 2026-08-11 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 2026-08-13 | 3 | 2026-08-18 | 0 | 2026-08-18 | 0 | 2026-08-18 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
55 | LMU | Yes | 2026-04-24 | page_2 | Pod 2 | Pod 2_Member2 | 2026-04-24 | 3 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2 | 2026-05-18 | 3 | 2026-05-21 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 1 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 3 | 2026-06-01 | 0 | 2026-06-01 | 0 | 2026-06-01 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 44 |  | 9
56 | LMU | Yes | 2026-04-24 | page_3 | Pod 2 | Pod 2_Member3 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 | #VALUE! | 9
57 | LMU | Yes | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
58 | LMU | Yes | 2026-05-05 | page_5 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
59 | LMU | Yes | 2026-05-05 | page_6 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 3 | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 | #VALUE! | 9 |  |  | #VALUE!
60 | LMU | Yes | 2026-05-14 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
61 | LMU | Yes | 2026-05-14 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-14 | 3 | 0 | 8 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 3 | 2026-06-04 | 2 | 2026-06-08 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-12 | 2026-06-12 | 1 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 3 | 2026-06-19 | 0 | 2026-06-19 | 0 | 2026-06-19 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
62 | LMU | Yes | 2026-05-14 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-14 | 3 | 0 | 9 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
63 | LMU | Yes | 2026-05-22 | page_7 | Pod 2 | Pod 2_Member1 | 2026-05-22 | 3 | 0 | 7 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 3 | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 44 |  | 9
64 | LMU | Yes | 2026-05-22 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-22 | 3 | 0 | 11 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
65 | LMU | Yes | 2026-05-22 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-22 | 3 | 0 | 12 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 3 | 2026-06-12 | 2 | 2026-06-16 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-22 | 2026-06-22 | 1 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 3 | 2026-06-30 | 0 | 2026-06-30 | 0 | 2026-06-30 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 44 |  | 9
66 | LMU | Yes | 2026-06-01 | page_10 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 10 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
67 | LMU | Yes | 2026-06-01 | page_14 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 14 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 | #VALUE! | 9 |  |  | #VALUE!
68 | LMU | Yes | 2026-06-01 | page_15 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 15 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
69 | LMU | Yes | 2026-06-09 | page_13 | Pod 2 | Pod 2_Member1 | 2026-06-09 | 3 | 0 | 13 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 3 | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 42 |  | 9
70 | LMU | Yes | 2026-06-09 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-09 | 3 | 0 | 17 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 |  | 9
71 | LMU | Yes | 2026-06-09 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-09 | 3 | 0 | 18 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 3 | 2026-06-29 | 2 | 2026-07-01 | 3 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-10 | 3 | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 42 |  | 9
72 | LMU | Yes | 2026-06-17 | page_16 | Pod 2 | Pod 2_Member1 | 2026-06-17 | 3 | 0 | 16 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 9
73 | LMU | Yes | 2026-06-17 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-17 | 3 | 0 | 20 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 2 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 3 | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 48 |  | 9
74 | LMU | Yes | 2026-06-17 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-17 | 3 | 0 | 21 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 9
75 | LMU | Yes | 2026-06-25 | page_19 | Pod 2 | Pod 2_Member1 | 2026-06-25 | 3 | 0 | 19 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 3 | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 3 | 2026-07-31 | 0 | 2026-07-31 | 0 | 2026-07-31 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
76 | LMU | Yes | 2026-06-25 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-25 | 3 | 0 | 23 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
77 | LMU | Yes | 2026-06-25 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-25 | 3 | 0 | 24 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 3 | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 3 | 2026-07-31 | 0 | 2026-07-31 | 0 | 2026-07-31 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
78 | LMU | Yes | 2026-07-03 | page_22 | Pod 2 | Pod 2_Member1 | 2026-07-03 | 3 | 0 | 22 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 | #VALUE! | 9 |  |  | #VALUE!
79 | LMU | Yes | 2026-07-03 | page_25 | Pod 2 | Pod 2_Member3 | 2026-07-03 | 3 | 0 | 25 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 1 | 2026-07-30 | 3 | 2026-08-04 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 |  | 12
80 | LMU | Yes | 2026-07-03 | page_26 | Pod 2 | Pod 2_Member2 | 2026-07-03 | 3 | 0 | 26 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 2 | 2026-07-27 | 3 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 43 |  | 12
81 | Location | Yes | 2026-04-24 | page_1 | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 |  | 2026-05-11 | 2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 |  | 2026-05-20 | 0 | 2026-05-20 | 0 | 2026-05-20 | 2026-05-21 | Release 11 | #VALUE! | 2026-05-28 | 2026-05-21 | 30 |  | 9
82 | Location | Yes | 2026-05-05 | page_2 | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 | #VALUE! | 9 |  |  | #VALUE!
83 | Location | Yes | 2026-05-05 | page_3 | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
84 | Location | Yes | 2026-05-05 | page_4 | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 4 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 |  | 2026-05-19 | 2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | 0 | 2026-05-29 | 0 | 2026-05-29 | 2026-06-04 | Release 12 | #VALUE! | 2026-06-11 | 2026-06-04 | 35 |  | 9
85 | Location | Yes | 2026-05-14 | page_5 | Pod 3 | Pod 3_Member1 | 2026-05-14 | 3 | 0 | 5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
86 | Location | Yes | 2026-05-14 | page_6 | Pod 3 | Pod 3_Member2 | 2026-05-14 | 3 | 0 | 6 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
87 | Location | Yes | 2026-05-14 | page_7 | Pod 3 | Pod 3_Member3 | 2026-05-14 | 3 | 0 | 7 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 |  | 2026-05-29 | 2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 |  | 2026-06-10 | 0 | 2026-06-10 | 0 | 2026-06-10 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 38 |  | 9
88 | Location | Yes | 2026-05-22 | page_8 | Pod 3 | Pod 3_Member1 | 2026-05-22 | 3 | 0 | 8 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
89 | Location | Yes | 2026-05-22 | page_9 | Pod 3 | Pod 3_Member2 | 2026-05-22 | 3 | 0 | 9 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
90 | Location | Yes | 2026-05-22 | page_10 | Pod 3 | Pod 3_Member3 | 2026-05-22 | 3 | 0 | 10 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | 2026-06-09 | 2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 |  | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 |  | 2026-06-18 | 0 | 2026-06-18 | 0 | 2026-06-18 | 2026-06-18 | Release 13 | #VALUE! | 2026-06-25 | 2026-06-18 | 30 |  | 9
91 | Location | Yes | 2026-06-01 | page_11 | Pod 3 | Pod 3_Member1 | 2026-06-01 | 3 | 0 | 11 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 3 | 2026-06-19 | 2 | 2026-06-23 | 3 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 3 | 2026-07-08 | 0 | 2026-07-08 | 0 | 2026-07-08 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
92 | Log | Yes | 2026-07-15 | page_1 | Pod 2 | Pod 2_Member1 | 2026-07-15 | 3 | 0 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 | #VALUE! | 9 |  |  | #VALUE!
93 | Log | Yes | 2026-07-15 | page_2 | Pod 2 | Pod 2_Member2 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
94 | Log | Yes | 2026-07-15 | page_3 | Pod 2 | Pod 2_Member3 | 2026-07-15 | 3 | 0 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
95 | Log | Yes | 2026-07-23 | page_4 | Pod 2 | Pod 2_Member1 | 2026-07-23 | 3 | 0 | 4 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
96 | Log | Yes | 2026-07-23 | page_5 | Pod 2 | Pod 2_Member2 | 2026-07-23 | 3 | 0 | 5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
97 | Log | Yes | 2026-07-23 | page_6 | Pod 2 | Pod 2_Member3 | 2026-07-23 | 3 | 0 | 6 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
98 | Log | Yes | 2026-07-23 | page_7 | Pod 1 | Pod 1_Member1 | 2026-07-23 | 3 | 0 | 7 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
99 | Log | Yes | 2026-07-23 | page_8 | Pod 1 | Pod 1_Member2 | 2026-07-23 | 3 | 0 | 8 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
100 | Log | Yes | 2026-07-23 | page_9 | Pod 1 | Pod 1_Member3 | 2026-07-23 | 3 | 0 | 9 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 |  | 2026-08-17 | 0 | 2026-08-17 | 0 | 2026-08-17 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 |  | 9
101 | Log | Yes | 2026-07-23 | page_10 | Pod 3 | Pod 3_Member1 | 2026-07-23 | 3 | 0 | 10 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 3 | 2026-08-11 | 2 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-19 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-24 | 3 | 2026-08-28 | 0 | 2026-08-28 | 0 | 2026-08-28 | 2026-08-27 | Release 18 | #VALUE! | 2026-09-03 | 2026-08-27 | 38 | #VALUE! | 9 |  |  | #VALUE!
102 | OrderAware | Yes | 2026-06-18 | page_5 | Pod 4 | Pod 4_Member2 | 2026-06-18 | 3 | 0 | 1 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 9
103 | OrderAware | Yes | 2026-06-18 | page_6 | Pod 4 | Pod 4_Member3 | 2026-06-18 | 3 | 0 | 2 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 9
104 | OrderAware | Yes | 2026-06-18 | page_7 | Pod 4 | Pod 4_Member1 | 2026-06-18 | 3 | 0 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 1.5 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 |  | 2026-07-03 | 2 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 |  | 2026-07-15 | 0 | 2026-07-15 | 0 | 2026-07-15 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 31 |  | 9
105 | OrderAware | Yes | 2026-06-26 | page_8 | Pod 4 | Pod 4_Member2 | 2026-06-26 | 3 | 0 | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 3 | 2026-07-06 | 1.5 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 3 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 36 |  | 12
106 | ProgressionPlan | No | 2026-06-01 | page_1 | Pod 1 | Pod 1_Member2 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
107 | ProgressionPlan | No | 2026-06-01 | page_2 | Pod 1 | Pod 1_Member3 | 2026-06-01 | 3 | 0 | 2 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
108 | ProgressionPlan | No | 2026-06-09 | page_3 | Pod 1 | Pod 1_Member1 | 2026-06-09 | 3 | 0 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 |  | 9
109 | ProgressionPlan | No | 2026-06-09 | page_4 | Pod 1 | Pod 1_Member2 | 2026-06-09 | 3 | 0 | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 |  | 9
110 | ProgressionPlan | No | 2026-06-09 | page_5 | Pod 1 | Pod 1_Member3 | 2026-06-09 | 3 | 0 | 5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 |  | 9
111 | ProgressionPlan | No | 2026-06-17 | page_6 | Pod 1 | Pod 1_Member1 | 2026-06-17 | 3 | 0 | 6 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 | #VALUE! | 9 |  |  | #VALUE!
112 | ProgressionPlan | No | 2026-06-17 | page_7 | Pod 1 | Pod 1_Member2 | 2026-06-17 | 3 | 0 | 7 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 2 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-15 | 2026-07-16 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 3 | 2026-07-23 | 0 | 2026-07-23 | 0 | 2026-07-23 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 48 |  | 9
113 | Reg+Attendance | No | 2026-06-17 | page_1 | Pod 1 | Pod 1_Member3 | 2026-06-17 | 3 | 0 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 |  | 9
114 | Reg+Attendance | No | 2026-06-25 | page_2 | Pod 1 | Pod 1_Member1 | 2026-06-25 | 3 | 0 | 2 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
115 | Reg+Attendance | No | 2026-06-25 | page_3 | Pod 1 | Pod 1_Member2 | 2026-06-25 | 3 | 0 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 |  | 9
116 | Reg+Attendance | No | 2026-06-25 | page_4 | Pod 1 | Pod 1_Member3 | 2026-06-25 | 3 | 0 | 4 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 37 | #VALUE! | 9 |  |  | #VALUE!
117 | Reg+Attendance | No | 2026-07-03 | page_5 | Pod 1 | Pod 1_Member1 | 2026-07-03 | 3 | 0 | 5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 2 | 2026-07-27 | 3 | 2026-07-30 | 2026-07-30 | 2026-07-31 | 2026-07-31 | 1 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-04 | 3 | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 43 | #VALUE! | 9 |  |  | #VALUE!
118 | Reports | No | 2026-07-03 | page_1 | Pod 1 | Pod 1_Member2 | 2026-07-03 | 3 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 |  | 9
119 | Reports | No | 2026-07-03 | page_2 | Pod 1 | Pod 1_Member3 | 2026-07-03 | 3 | 0 | 2 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 |  | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 |  | 2026-07-29 | 0 | 2026-07-29 | 0 | 2026-07-29 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30 | 29 |  | 9
120 | Reports | No | 2026-07-15 | page_3 | Pod 1 | Pod 1_Member1 | 2026-07-15 | 3 | 0 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
121 | Reports | No | 2026-07-15 | page_4 | Pod 1 | Pod 1_Member3 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 |  | 2026-07-29 | 2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 |  | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 2026-08-07 | 0 | 2026-08-07 | 0 | 2026-08-07 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 | #VALUE! | 9 |  |  | #VALUE!
122 | Reports | No | 2026-07-15 | page_5 | Pod 1 | Pod 1_Member2 | 2026-07-15 | 3 | 0 | 5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 3 | 2026-08-03 | 2 | 2026-08-05 | 3 | 2026-08-10 | 2026-08-10 | 2026-08-11 | 2026-08-11 | 1 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 2026-08-13 | 3 | 2026-08-18 | 0 | 2026-08-18 | 0 | 2026-08-18 | 2026-08-13 | Release 17 | #VALUE! | 2026-08-20 | 2026-08-13 | 34 |  | 9
123 | Webuser | No | 2026-06-01 | page_1 | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 |  | 9
124 | Webuser | No | 2026-06-01 | page_2 | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 | 0 | 2 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 |  | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 |  | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-25 |  | 2026-06-25 | 0 | 2026-06-25 | 0 | 2026-06-25 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 35 | #VALUE! | 9
125 | Webuser | No | 2026-06-09 | page_3 | Pod 3 | Pod 3_Member1 | 2026-06-09 | 3 | 0 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 | #VALUE! | 9
126 | Webuser | No | 2026-06-09 | page_4 | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 | 0 | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 |  | 9
127 | Webuser | No | 2026-06-09 | page_5 | Pod 3 | Pod 3_Member3 | 2026-06-09 | 3 | 0 | 5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 |  | 2026-07-03 | 0 | 2026-07-03 | 0 | 2026-07-03 | 2026-07-02 | Release 14 | #VALUE! | 2026-07-09 | 2026-07-02 | 28 | #VALUE! | 9
128 | Webuser | No | 2026-06-17 | page_1 | Pod 3 | Pod 3_Member1 | 2026-06-17 | 3 | 0 | 6 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16 | 34 | #VALUE! | 9
129 | Webuser | No | 2026-06-17 | page_2 | Pod 3 | Pod 3_Member2 | 2026-06-17 | 3 |  | 7 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16
130 | Webuser | No | 2026-06-17 | page_3 | Pod 3 | Pod 3_Member3 | 2026-06-17 | 3 |  | 8 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 |  | 2026-07-02 | 2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 |  | 2026-07-14 | 0 | 2026-07-14 | 0 | 2026-07-14 | 2026-07-16 | Release 15 | #VALUE! | 2026-07-23 | 2026-07-16
131 | Webuser | No | 2026-06-25 | page_4 | Pod 3 | Pod 3_Member1 | 2026-06-25 | 3 |  | 9 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 | 2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-22 |  | 2026-07-22 | 0 | 2026-07-22 | 0 | 2026-07-22 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30
132 | Webuser | No | 2026-06-25 | page_5 | Pod 3 | Pod 3_Member2 | 2026-06-25 | 3 |  | 10 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 3 | 2026-07-16 | 2 | 2026-07-20 | 3 | 2026-07-23 | 2026-07-23 | 2026-07-24 | 2026-07-24 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 3 | 2026-07-31 | 0 | 2026-07-31 | 0 | 2026-07-31 | 2026-07-30 | Release 16 | #VALUE! | 2026-08-06 | 2026-07-30
Formulas:
Start Date = [Module Target Start (Input)]
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Code Freeze Date = [TCR Bugs Closure Date]
Pearson Regression Testing/UAT Date = WORKDAY([TEST Deployment], 1, IndHolidays)
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&[TCR Bugs Closure Date])
Code freeze date = Release cutoff Date = WORKDAY([Release Date (2-Wk Cycle)], -5)
Release Request Approved Date = WORKDAY([Release #], 2, IndHolidays)
Release Date (2-Wk Cycle) = VLOOKUP([Release #],ReleaseTimeline!$B2:C27,2,FALSE)

## Adding Pod 4old (hidden)
No. | Module | Recieved Functional & Non Fuctional Walkthrough | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR Bugs Closure Date | Pearson Regression Testing/UAT Date | Pearson Regression Testing Day | Pearson Regression End Date | Issue Fix Days | PR raised date | PR Response Days | PR Response receive Date | TEST Deployment | Release Request Raise Date | Release Request Approved Date | Release Date (2-Wk Cycle) | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
1 | AddressBook |  | 2026-04-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-15 | 3 | 0 | 12 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 2 | 2026-04-24 | 2026-04-24 | 3 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 2026-06-25 |  |  | 12
2 | AddressBook |  | 2026-04-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-15 | 3 | 0 | 13 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 2 | 2026-04-24 | 2026-04-24 | 3 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 2026-06-25 |  |  | 12
3 | AddressBook |  | 2026-04-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-15 | 3 | 0 | 14 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 2 | 2026-04-24 | 2026-04-24 | 3 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 2026-06-25 |  |  | 12
4 | AddressBook |  | 2026-04-24 | page_4 | Pod 3 | Pod 3_Member1 | 2026-04-24 | 3 | 0 | 15 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2 | 2026-05-06 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 2026-06-25 |  |  | 12
5 | AddressBook |  | 2026-04-24 | page_5 | Pod 3 | Pod 3_Member2 | 2026-04-24 | 3 | 0 | 16 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2 | 2026-05-06 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 2026-06-25 | 58 |  | 12
6 | Assessments |  | 2026-07-23 | page_1 | Pod 2 | Pod 3_Member2 | 2026-07-23 | 3 | 0 | 4 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 2 | 2026-08-03 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 3 | 2026-08-12 | 2 | 2026-08-14 | 3 | 2026-08-19 | 2026-08-19 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 2026-09-02 | 3 | 2026-09-07 | 1 | 2026-09-08 | 3 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-10-01 |  |  | 12
7 | Assessments |  | 2026-07-23 | page_2 | Pod 2 | Pod 3_Member3 | 2026-07-23 | 3 | 0 | 5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 2 | 2026-08-03 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 3 | 2026-08-12 | 2 | 2026-08-14 | 3 | 2026-08-19 | 2026-08-19 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 2026-09-02 | 3 | 2026-09-07 | 1 | 2026-09-08 | 3 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-10-01 |  |  | 12
8 | Assessments |  | 2026-07-31 | page_3 | Pod 2 | Pod 2_Member3 | 2026-07-31 | 3 | 0 | 6 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 2 | 2026-08-11 | 2026-08-11 | 3 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 3 | 2026-08-20 | 2 | 2026-08-25 | 3 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 1 | 2026-09-08 | 3 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-10-01 |  |  | 12
9 | Assessments |  | 2026-07-31 | assessments/webuserAssessmentFiles. | Pod 2 | Pod 2_Member1 | 2026-07-31 | 3 | 0 | 7 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 2 | 2026-08-11 | 2026-08-11 | 3 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 3 | 2026-08-20 | 2 | 2026-08-25 | 3 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 1 | 2026-09-08 | 3 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-10-01 |  |  | 12
10 | Assessments |  | 2026-07-31 | assessments/checkMyWork/checkMyWork | Pod 2 | Pod 2_Member2 | 2026-07-31 | 3 | 0 | 8 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 2 | 2026-08-11 | 2026-08-11 | 3 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 3 | 2026-08-20 | 2 | 2026-08-25 | 3 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 1 | 2026-09-08 | 3 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-10-01 |  |  | 12
11 | Assessments |  | 2026-07-31 | assessments/checkMyWork/submissions | Pod 2 | Pod 1_Member1 | 2026-07-31 | 3 | 0 | 9 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 2 | 2026-08-11 | 2026-08-11 | 3 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 3 | 2026-08-20 | 2 | 2026-08-25 | 3 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 1 | 2026-09-08 | 3 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-10-01 |  |  | 12
12 | Assessments |  | 2026-07-31 | assessments/import.aspx ¦ RadGrid, | Pod 2 | Pod 1_Member2 | 2026-07-31 | 3 | 0 | 10 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 2 | 2026-08-11 | 2026-08-11 | 3 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 3 | 2026-08-20 | 2 | 2026-08-25 | 3 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 1 | 2026-09-08 | 3 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-10-01 |  |  | 12
13 | Assessments |  | 2026-07-31 | assessments/question.aspx ¦ RadAjax | Pod 2 | Pod 1_Member3 | 2026-07-31 | 3 | 0 | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 2 | 2026-08-11 | 2026-08-11 | 3 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 3 | 2026-08-20 | 2 | 2026-08-25 | 3 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 1 | 2026-09-08 | 3 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-10-01 |  |  | 12
14 | Assessments |  | 2026-07-31 | assessments/questionManager.aspx ¦ | Pod 2 | Pod 3_Member1 | 2026-07-31 | 3 | 0 | 2 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 2 | 2026-08-11 | 2026-08-11 | 3 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 3 | 2026-08-20 | 2 | 2026-08-25 | 3 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 1 | 2026-09-08 | 3 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-10-01 |  |  | 12
15 | Assessments |  | 2026-07-31 | assessments/questions.aspx ¦ RadGri | Pod 2 | Pod 3_Member2 | 2026-07-31 | 3 | 0 | 3 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 2 | 2026-08-11 | 2026-08-11 | 3 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 3 | 2026-08-20 | 2 | 2026-08-25 | 3 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 1 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 1 | 2026-09-08 | 3 | 2026-09-11 | 2026-09-15 | 2026-09-16 | 2026-09-21 | 2026-10-01 |  |  | 12
16 | AssetAware |  | 2026-05-15 | assetAware/asset.aspx | Pod 4 | Pod 2_Member1 | 2026-05-15 | 3 | 0 | 1 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-25 | 3 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-15 | 2026-07-23 |  |  | 12
17 | AssetAware |  | 2026-05-15 | assetAware/assets.aspx | Pod 4 | Pod 1_Member1 | 2026-05-15 | 3 | 0 | 2 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-25 | 3 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-15 | 2026-07-23 |  |  | 12
18 | AssetAware |  | 2026-05-15 | assetAware/assetVendorAddressContact.aspx | Pod 4 | Pod 3_Member1 | 2026-05-15 | 3 | 0 | 4 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 3 | 2026-05-22 | 2 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-25 | 3 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-15 | 2026-07-23 |  |  | 12
19 | AssetAware |  | 2026-05-25 | assetAware/assetHistory.aspx | Pod 4 | Pod 2_Member1 | 2026-05-25 | 3 | 0 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-15 | 2026-07-23 | 57 |  | 12
20 | Communication |  | 2026-05-25 | communication/webmail/webmailBox.aspx ¦ RadGr | Pod 4 | Pod 1_Member1 | 2026-05-25 | 3 | 0 | 4 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-07-03 | 3 | 2026-07-09 | 1 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-22 | 2026-07-23 |  |  | 12
21 | Communication |  | 2026-05-25 | communication/webmail/settings.aspx ¦ RadAjax | Pod 4 | Pod 3_Member1 | 2026-05-25 | 3 | 0 | 1 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 3 | 2026-06-03 | 2 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-07-03 | 3 | 2026-07-09 | 1 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-22 | 2026-07-23 |  |  | 12
22 | Communication |  | 2026-06-02 | communication/webmail/autoReplySettings.aspx | Pod 4 | Pod 1_Member1 | 2026-06-02 | 3 | 0 | 2 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 2 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 1 | 2026-07-10 | 3 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-22 | 2026-07-23 |  |  | 12
23 | Communication |  | 2026-06-02 | communication/webmail/signatureSettings.aspx | Pod 4 | Pod 2_Member1 | 2026-06-02 | 3 | 0 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 1 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 1 | 2026-06-12 | 1 | 2026-06-15 | 1 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-07-03 | 1 | 2026-07-06 | 0 | 2026-07-06 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-15 | 2026-07-23 | 48 |  | 4
24 | Content |  | 2026-06-02 | content/captionedVideoItem.aspx ¦ | Pod 4 | Pod 3_Member1 | 2026-06-02 | 3 | 0 | 3 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2 | 2026-06-09 | 2 | 2026-06-11 | 2026-06-11 | 2 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 2 | 2026-06-18 | 2 | 2026-06-22 | 2 | 2026-06-24 | 2026-06-24 | 2026-06-25 | 2026-06-25 | 2 | 2026-06-30 | 2026-08-06 | 2 | 2026-08-10 | 1 | 2026-08-11 | 2 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 8
25 | Content |  | 2026-06-10 | content/chrome/online/footer.aspx | Pod 4 | Pod 1_Member1 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 3 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 3 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-08-06 | 3 | 2026-08-11 | 2 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-27 | 2026-09-03 |  |  | 12
26 | Content |  | 2026-06-10 | content/elmItemInteractive.aspx ¦ | Pod 4 | Pod 3_Member1 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 4 | 2026-06-18 | 4 | 2026-06-24 | 2026-06-24 | 4 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 4 | 2026-07-09 | 4 | 2026-07-15 | 4 | 2026-07-21 | 2026-07-21 | 2026-07-22 | 2026-07-22 | 4 | 2026-07-28 | 2026-08-06 | 4 | 2026-08-12 | 3 | 2026-08-17 | 4 | 2026-08-24 | 2026-08-25 | 2026-08-27 | 2026-09-01 | 2026-09-03 |  |  | 16
27 | Content |  | 2026-06-10 | content/hyperlink.aspx ¦ RadAjaxM | Pod 4 | Pod 2_Member1 | 2026-06-10 | 3 | 0 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 5 | 2026-06-19 | 5 | 2026-06-29 | 2026-06-29 | 5 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 5 | 2026-07-15 | 5 | 2026-07-22 | 5 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 5 | 2026-08-06 | 2026-08-06 | 5 | 2026-08-13 | 4 | 2026-08-19 | 5 | 2026-08-28 | 2026-08-31 | 2026-09-01 | 2026-09-04 | 2026-09-17 | 97 |  | 20
28 | Enrollment |  | 2026-05-05 | enrollment/placement/placementHelp.aspx | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 22 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
29 | Enrollment |  | 2026-05-14 | enrollment/placement/manager.aspx ¦ RadG | Pod 1 | Pod 1_Member1 | 2026-05-14 | 3 | 0 | 20 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
30 | Enrollment |  | 2026-05-14 | enrollment/placement/rejectReason.aspx ¦ | Pod 1 | Pod 1_Member2 | 2026-05-14 | 3 | 0 | 21 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
31 | Enrollment |  | 2026-05-14 | enrollment/registration/registrationLoca | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 25 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
32 | Enrollment |  | 2026-05-22 | enrollment/registration/default.aspx ¦ R | Pod 1 | Pod 1_Member1 | 2026-05-22 | 3 | 0 | 23 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
33 | Enrollment |  | 2026-05-22 | enrollment/registration/registrationLoca | Pod 1 | Pod 1_Member2 | 2026-05-22 | 3 | 0 | 24 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
34 | Enrollment |  | 2026-05-22 | enrollment/registration/registrantFamily | Pod 1 | Pod 1_Member3 | 2026-05-22 | 3 | 0 | 26 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
35 | Enrollment |  | 2026-06-01 | enrollment/registration/resendEmail.aspx | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 | 49 |  | 12
36 | ExtendedField |  | 2026-04-15 | extendedField/extendedField.aspx ¦ RadAjax | Pod 1 | Pod 1_Member1 | 2026-04-15 | 3 | 0 | 11 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 2 | 2026-04-24 | 2026-04-24 | 3 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-23 | 2026-06-25 |  |  | 12
37 | ExtendedField |  | 2026-04-15 | extendedField/default.aspx ¦ RadGrid, RadA | Pod 1 | Pod 1_Member2 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 2 | 2026-04-24 | 2026-04-24 | 3 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-23 | 2026-06-25 |  |  | 12
38 | ExtendedField |  | 2026-04-15 | extendedField/associations.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member3 | 2026-04-15 | 3 | 0 | 2 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 2 | 2026-04-24 | 2026-04-24 | 3 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-23 | 2026-06-25 |  |  | 12
39 | ExtendedField |  | 2026-04-24 | extendedField/calculationGroupExtendedFiel | Pod 1 | Pod 1_Member1 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2 | 2026-05-06 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-23 | 2026-06-25 |  |  | 12
40 | ExtendedField |  | 2026-04-24 | extendedField/extendedFieldConfirmRecalcul | Pod 1 | Pod 1_Member2 | 2026-04-24 | 3 | 0 | 4 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2 | 2026-05-06 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-23 | 2026-06-25 |  |  | 12
41 | ExtendedField |  | 2026-04-24 | extendedField/fieldHistory.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member3 | 2026-04-24 | 3 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2 | 2026-05-06 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-23 | 2026-06-25 |  |  | 12
42 | ExtendedField |  | 2026-05-05 | extendedField/dataview/dataview.aspx ¦ Rad | Pod 1 | Pod 1_Member1 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-23 | 2026-06-25 |  |  | 12
43 | ExtendedField |  | 2026-05-05 | extendedField/dataview/logEntryFilter.aspx | Pod 1 | Pod 1_Member2 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-06-05 | 3 | 2026-06-10 | 1 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-23 | 2026-06-25 | 49 |  | 12
44 | GradeBook |  | 2026-04-15 | page_3 | Pod 2 | Pod 2_Member1 | 2026-04-15 | 3 | 0 | 6 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 2 | 2026-04-24 | 2026-04-24 | 3 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 1 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-27 | 2026-05-29 | 2026-06-04 | 2026-06-11 |  |  | 12
45 | GradeBook |  | 2026-04-15 | page_4 | Pod 2 | Pod 2_Member2 | 2026-04-15 | 3 | 0 | 7 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 2 | 2026-04-24 | 2026-04-24 | 3 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 3 | 2026-05-20 | 1 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-27 | 2026-05-29 | 2026-06-04 | 2026-06-11 | 55 |  | 12
46 | Home |  | 2026-06-25 | home/pages/teacherBeta.aspx | Pod 3 | Pod 3_Member3 | 2026-06-25 | 3 | 0 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 1 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 1 | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-08-04 | 1 | 2026-08-05 | 0 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 |  |  | 4
47 | Home |  | 2026-07-03 | home/pages/caretaker.aspx ¦ | Pod 3 | Pod 3_Member1 | 2026-07-03 | 3 | 0 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1 | 2026-07-21 | 2026-08-04 | 1 | 2026-08-05 | 0 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 |  |  | 4
48 | Home |  | 2026-07-03 | home/pages/teacher.aspx ¦ R | Pod 3 | Pod 3_Member2 | 2026-07-03 | 3 | 0 | 2 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 3 | 2026-07-24 | 2 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
49 | Home |  | 2026-07-03 | home/pages/enrollment.aspx | Pod 3 | Pod 3_Member3 | 2026-07-03 | 3 | 0 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1 | 2026-07-21 | 2026-08-04 | 1 | 2026-08-05 | 0 | 2026-08-05 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 43 |  | 4
50 | IssueAware |  | 2026-04-15 | page_1 | Pod 2 | Pod 2_Member3 | 2026-04-15 | 3 | 0 | 4 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 3 | 2026-04-22 | 2 | 2026-04-24 | 2026-04-24 | 3 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 3 | 2026-05-06 | 2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 2026-06-25 |  |  | 12
51 | IssueAware |  | 2026-04-24 | page_2 | Pod 2 | Pod 2_Member1 | 2026-04-24 | 3 | 0 | 5 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2 | 2026-05-06 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 2026-06-25 | 58 |  | 12
52 | Library |  | 2026-07-15 | library/resource.aspx ¦ Ra | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 17 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 3 | 2026-08-04 | 2 | 2026-08-06 | 3 | 2026-08-11 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 3 | 2026-08-18 | 1 | 2026-08-19 | 3 | 2026-08-25 | 2026-08-27 | 2026-08-28 | 2026-09-02 | 2026-09-03 |  |  | 12
53 | Library |  | 2026-07-15 | library/searchResults.aspx | Pod 3 | Pod 3_Member2 | 2026-07-15 | 3 | 0 | 18 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 3 | 2026-08-04 | 2 | 2026-08-06 | 3 | 2026-08-11 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 3 | 2026-08-18 | 1 | 2026-08-19 | 3 | 2026-08-25 | 2026-08-27 | 2026-08-28 | 2026-09-02 | 2026-09-03 |  |  | 12
54 | Library |  | 2026-07-15 | library/userSelector.aspx | Pod 3 | Pod 3_Member3 | 2026-07-15 | 3 | 0 | 19 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 3 | 2026-08-04 | 2 | 2026-08-06 | 3 | 2026-08-11 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 3 | 2026-08-18 | 1 | 2026-08-19 | 3 | 2026-08-25 | 2026-08-27 | 2026-08-28 | 2026-09-02 | 2026-09-03 | 48 |  | 12
55 | LMU |  | 2026-04-24 | page_2 | Pod 2 | Pod 2_Member2 | 2026-04-24 | 3 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2 | 2026-05-06 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
56 | LMU |  | 2026-04-24 | page_3 | Pod 2 | Pod 2_Member3 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2 | 2026-05-06 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
57 | LMU | Yes | 2026-05-05 | page_1 | Pod 2 | Pod 2_Member1 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
58 | LMU |  | 2026-05-05 | page_5 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
59 | LMU | No | 2026-05-05 | page_6 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
60 | LMU |  | 2026-05-14 | page_4 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
61 | LMU |  | 2026-05-14 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-14 | 3 | 0 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
62 | LMU |  | 2026-05-14 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
63 | LMU |  | 2026-05-22 | page_7 | Pod 2 | Pod 2_Member1 | 2026-05-22 | 3 | 0 | 2 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
64 | LMU |  | 2026-05-22 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-22 | 3 | 0 | 6 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
65 | LMU |  | 2026-05-22 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-22 | 3 | 0 | 7 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
66 | LMU |  | 2026-06-01 | page_10 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
67 | LMU | No | 2026-06-01 | page_14 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 1 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
68 | LMU |  | 2026-06-01 | page_15 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 2 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
69 | LMU |  | 2026-06-09 | page_13 | Pod 2 | Pod 2_Member1 | 2026-06-09 | 3 | 0 | 8 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  | 3 | 12 |  |  | 15
70 | LMU |  | 2026-06-09 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-09 | 3 | 0 | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
71 | LMU |  | 2026-06-09 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-09 | 3 | 0 | 5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
72 | LMU |  | 2026-06-17 | page_16 | Pod 2 | Pod 2_Member1 | 2026-06-17 | 3 | 0 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
73 | LMU |  | 2026-06-17 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-17 | 3 | 0 | 7 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
74 | LMU |  | 2026-06-17 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-17 | 3 | 0 | 8 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
75 | LMU |  | 2026-06-25 | page_19 | Pod 2 | Pod 2_Member1 | 2026-06-25 | 3 | 0 | 6 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
76 | LMU |  | 2026-06-25 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-25 | 3 | 0 | 10 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  | 3 | 12 |  |  | 15
77 | LMU |  | 2026-06-25 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-25 | 3 | 0 | 1 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
78 | LMU |  | 2026-07-03 | page_22 | Pod 2 | Pod 2_Member1 | 2026-07-03 | 3 | 0 | 9 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 3 | 2026-07-24 | 2 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
79 | LMU |  | 2026-07-03 | page_25 | Pod 2 | Pod 2_Member3 | 2026-07-03 | 3 | 0 | 2 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 3 | 2026-07-24 | 2 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 |  |  | 12
80 | LMU |  | 2026-07-03 | page_26 | Pod 2 | Pod 2_Member2 | 2026-07-03 | 3 | 0 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 3 | 2026-07-24 | 2 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 43 |  | 12
81 | Location |  | 2026-04-24 | location/createHouseholdLinkExisting | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 2 | 2026-05-06 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 3 | 2026-05-15 | 2 | 2026-05-19 | 3 | 2026-05-22 | 2026-05-22 | 2026-05-25 | 2026-05-25 | 1 | 2026-05-26 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
82 | Location |  | 2026-05-05 | location/addressContact.aspx ¦ RadAj | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 4 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
83 | Location |  | 2026-05-05 | location/createHousehold.aspx ¦ RadA | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 5 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
84 | Location |  | 2026-05-05 | location/locationExtended.aspx ¦ Rad | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 4 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 2 | 2026-05-14 | 2026-05-14 | 3 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2 | 2026-05-27 | 3 | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 1 | 2026-06-05 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  | 7 | 12 |  |  | 19
85 | Location |  | 2026-05-14 | location/dataview.aspx ¦ RadGrid, Ra | Pod 3 | Pod 3_Member1 | 2026-05-14 | 3 | 0 | 2 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
86 | Location |  | 2026-05-14 | location/extendedFields.aspx ¦ RadGr | Pod 3 | Pod 3_Member2 | 2026-05-14 | 3 | 0 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
87 | Location |  | 2026-05-14 | location/security/roleWebusers.aspx | Pod 3 | Pod 3_Member3 | 2026-05-14 | 3 | 0 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 2 | 2026-05-25 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-01 | 3 | 2026-06-05 | 2 | 2026-06-09 | 3 | 2026-06-12 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 1 | 2026-06-16 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
88 | Location |  | 2026-05-22 | location/skinProperties.aspx ¦ RadAj | Pod 3 | Pod 3_Member1 | 2026-05-22 | 3 | 0 | 1 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
89 | Location |  | 2026-05-22 | location/reports/allUsersInRoleExten | Pod 3 | Pod 3_Member2 | 2026-05-22 | 3 | 0 | 2 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
90 | Location |  | 2026-05-22 | AdditionalPage 1 | Pod 3 | Pod 3_Member3 | 2026-05-22 | 3 | 0 | 4 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 2 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1 | 2026-06-24 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 |  |  | 12
91 | Location |  | 2026-06-01 | AdditionalPage 2 | Pod 3 | Pod 3_Member1 | 2026-06-01 | 3 | 0 | 5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-02 | 3 | 2026-07-08 | 1 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-21 | 2026-07-23 | 49 |  | 12
92 | Log |  | 2026-07-15 | log/default.aspx ¦ RadGrid, RadAjaxManager, RadDa | Pod 2 | Pod 2_Member1 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 3 | 2026-08-04 | 2 | 2026-08-06 | 3 | 2026-08-11 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-24 | 3 | 2026-08-28 | 1 | 2026-08-31 | 3 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-17 |  |  | 12
93 | Log |  | 2026-07-15 | log/logEntry.aspx ¦ RadGrid, RadAjaxManager, RadT | Pod 2 | Pod 2_Member2 | 2026-07-15 | 3 | 0 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 3 | 2026-08-04 | 2 | 2026-08-06 | 3 | 2026-08-11 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-24 | 3 | 2026-08-28 | 1 | 2026-08-31 | 3 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-17 |  |  | 12
94 | Log |  | 2026-07-15 | log/areas.aspx ¦ RadGrid, RadAjaxManager ¦ Medium | Pod 2 | Pod 2_Member3 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 3 | 2026-08-04 | 2 | 2026-08-06 | 3 | 2026-08-11 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-24 | 3 | 2026-08-28 | 1 | 2026-08-31 | 3 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-17 |  |  | 12
95 | Log |  | 2026-07-23 | log/categories.aspx ¦ RadGrid, RadAjaxManager ¦ M | Pod 2 | Pod 2_Member1 | 2026-07-23 | 3 | 0 | 5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 2 | 2026-08-03 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 3 | 2026-08-12 | 2 | 2026-08-14 | 3 | 2026-08-19 | 2026-08-19 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 2026-08-24 | 3 | 2026-08-28 | 1 | 2026-08-31 | 3 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-17 |  |  | 12
96 | Log |  | 2026-07-23 | log/contactTypes.aspx ¦ RadGrid, RadAjaxManager ¦ | Pod 2 | Pod 2_Member2 | 2026-07-23 | 3 | 0 | 6 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 2 | 2026-08-03 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 3 | 2026-08-12 | 2 | 2026-08-14 | 3 | 2026-08-19 | 2026-08-19 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 2026-08-24 | 3 | 2026-08-28 | 1 | 2026-08-31 | 3 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-17 |  |  | 12
97 | Log |  | 2026-07-23 | log/logEntrySystems.aspx ¦ RadGrid, RadAjaxManage | Pod 2 | Pod 2_Member3 | 2026-07-23 | 3 | 0 | 7 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 2 | 2026-08-03 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 3 | 2026-08-12 | 2 | 2026-08-14 | 3 | 2026-08-19 | 2026-08-19 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 2026-08-24 | 3 | 2026-08-28 | 1 | 2026-08-31 | 3 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-17 |  | 10 | 12
98 | Log |  | 2026-07-23 | log/myLogSettings.aspx ¦ RadGrid, RadAjaxManager, | Pod 2 | Pod 1_Member1 | 2026-07-23 | 3 | 0 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 2 | 2026-08-03 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 3 | 2026-08-12 | 2 | 2026-08-14 | 3 | 2026-08-19 | 2026-08-19 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 2026-08-24 | 3 | 2026-08-28 | 1 | 2026-08-31 | 3 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-17 |  |  | 12
99 | Log |  | 2026-07-23 | log/systemProperties.aspx ¦ RadAjaxManager, RadHe | Pod 2 | Pod 1_Member2 | 2026-07-23 | 3 | 0 | 2 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 2 | 2026-08-03 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 3 | 2026-08-12 | 2 | 2026-08-14 | 3 | 2026-08-19 | 2026-08-19 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 2026-08-24 | 3 | 2026-08-28 | 1 | 2026-08-31 | 3 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-17 |  |  | 12
100 | Log |  | 2026-07-23 | log/areaCategoryWindow.aspx ¦ RadTreeView, RadAja | Pod 2 | Pod 1_Member3 | 2026-07-23 | 3 | 0 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 2 | 2026-08-03 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 3 | 2026-08-12 | 2 | 2026-08-14 | 3 | 2026-08-19 | 2026-08-19 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 2026-08-24 | 3 | 2026-08-28 | 1 | 2026-08-31 | 3 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-17 |  | 10 | 12 |  |  | 22
101 | Log |  | 2026-07-23 | log/specialPopulations/logSpecialPopulations.aspx | Pod 2 | Pod 3_Member1 | 2026-07-23 | 3 | 0 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 2 | 2026-08-03 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-07 | 2026-08-07 | 3 | 2026-08-12 | 2 | 2026-08-14 | 3 | 2026-08-19 | 2026-08-19 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 2026-08-24 | 3 | 2026-08-28 | 1 | 2026-08-31 | 3 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-10 | 2026-09-17 | 52 |  | 12
102 | OrderAware |  | 2026-06-18 | page_5 | Pod 4 | Pod 2_Member1 | 2026-06-18 | 3 | 0 | 8 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-29 | 3 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 |  |  | 12
103 | OrderAware |  | 2026-06-18 | page_6 | Pod 4 | Pod 3_Member1 | 2026-06-18 | 3 | 0 | 9 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-29 | 3 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 |  |  | 12
104 | OrderAware |  | 2026-06-18 | page_7 | Pod 4 | Pod 1_Member1 | 2026-06-18 | 3 | 0 | 10 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 3 | 2026-06-25 | 2 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1 | 2026-07-21 | 2026-07-29 | 3 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 |  |  | 12
105 | OrderAware |  | 2026-06-26 | page_8 | Pod 4 | Pod 2_Member1 | 2026-06-26 | 3 | 0 | 11 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 3 | 2026-07-06 | 2 | 2026-07-09 | 2026-07-09 | 3 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 3 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-20 | 50 |  | 12
106 | ProgressionPlan |  | 2026-06-01 | progressionPlan/academicRequirement.aspx ¦ RadGrid, Ra | Pod 1 | Pod 1_Member2 | 2026-06-01 | 3 | 0 | 5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-20 | 3 | 2026-07-23 | 1 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-05 | 2026-08-06 |  |  | 12
107 | ProgressionPlan |  | 2026-06-01 | progressionPlan/academicRequirements.aspx ¦ RadGrid, R | Pod 1 | Pod 1_Member3 | 2026-06-01 | 3 | 0 | 6 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-20 | 3 | 2026-07-23 | 1 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-05 | 2026-08-06 |  |  | 12
108 | ProgressionPlan |  | 2026-06-09 | progressionPlan/progressionPlan.aspx ¦ RadGrid, RadAja | Pod 1 | Pod 1_Member1 | 2026-06-09 | 3 | 0 | 4 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-20 | 3 | 2026-07-23 | 1 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-05 | 2026-08-06 |  |  | 12
109 | ProgressionPlan |  | 2026-06-09 | progressionPlan/completionRequirements.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member2 | 2026-06-09 | 3 | 0 | 8 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-20 | 3 | 2026-07-23 | 1 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-05 | 2026-08-06 |  |  | 12
110 | ProgressionPlan |  | 2026-06-09 | progressionPlan/webusers.aspx ¦ RadGrid, RadAjaxManage | Pod 1 | Pod 1_Member3 | 2026-06-09 | 3 | 0 | 9 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-20 | 3 | 2026-07-23 | 1 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-05 | 2026-08-06 |  |  | 12
111 | ProgressionPlan |  | 2026-06-17 | progressionPlan/completionRequirement.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member1 | 2026-06-17 | 3 | 0 | 7 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 1 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-05 | 2026-08-06 |  |  | 12
112 | ProgressionPlan |  | 2026-06-17 | progressionPlan/help/progressionPlansSelectorHelp.aspx | Pod 1 | Pod 1_Member2 | 2026-06-17 | 3 | 0 | 10 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-20 | 3 | 2026-07-23 | 1 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-05 | 2026-08-06 | 48 |  | 12
113 | Reg+Attendance |  | 2026-06-17 | registration.aspx | Pod 1 | Pod 1_Member3 | 2026-06-17 | 3 | 0 | 8 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 62 |  | 12
114 | Reg+Attendance |  | 2026-06-25 | attendance/enterAttendance.aspx | Pod 1 | Pod 1_Member1 | 2026-06-25 | 3 | 0 | 6 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 51 |  | 12
115 | Reg+Attendance |  | 2026-06-25 | attendance/editRecord.aspx ¦ Ra | Pod 1 | Pod 1_Member2 | 2026-06-25 | 3 | 0 | 7 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 51 |  | 12
116 | Reg+Attendance |  | 2026-06-25 | AdditionalPage 1 | Pod 1 | Pod 1_Member3 | 2026-06-25 | 3 | 0 | 9 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 51 |  | 12
117 | Reg+Attendance |  | 2026-07-03 | AdditionalPage 2 | Pod 1 | Pod 1_Member1 | 2026-07-03 | 3 | 0 | 10 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 3 | 2026-07-24 | 2 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 43 | 3 | 12 |  |  | 15
118 | Reports |  | 2026-07-03 | reports/institutionalStudentPerformanceE | Pod 1 | Pod 1_Member2 | 2026-07-03 | 3 | 0 | 4 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 1 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-10 | 1 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 1 | 2026-07-15 | 1 | 2026-07-16 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1 | 2026-07-21 | 2026-08-13 | 1 | 2026-08-14 | 1 | 2026-08-17 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-27 | 2026-09-03 | 57 | 14 | 4 |  |  | 18
119 | Reports |  | 2026-07-03 | reports/resourceManagerExport.aspx ¦ Rad | Pod 1 | Pod 1_Member3 | 2026-07-03 | 3 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2 | 2026-07-15 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 3 | 2026-07-24 | 2 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-03 | 1 | 2026-08-04 | 2026-08-13 | 3 | 2026-08-18 | 1 | 2026-08-19 | 3 | 2026-08-25 | 2026-08-27 | 2026-08-28 | 2026-09-02 | 2026-09-03 | 57 |  | 12
120 | Reports |  | 2026-07-15 | reports/aggregateLogEntry.aspx ¦ RadGrid | Pod 1 | Pod 1_Member1 | 2026-07-15 | 3 | 0 | 5 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 3 | 2026-08-04 | 2 | 2026-08-06 | 3 | 2026-08-11 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 3 | 2026-08-18 | 1 | 2026-08-19 | 3 | 2026-08-25 | 2026-08-27 | 2026-08-28 | 2026-09-02 | 2026-09-03 | 48 | 6 | 12 |  |  | 18
121 | Reports |  | 2026-07-15 | reports/sectionLogEntryReport.aspx ¦ Rad | Pod 1 | Pod 1_Member3 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 3 | 2026-08-04 | 2 | 2026-08-06 | 3 | 2026-08-11 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 3 | 2026-08-18 | 1 | 2026-08-19 | 3 | 2026-08-25 | 2026-08-27 | 2026-08-28 | 2026-09-02 | 2026-09-03 | 48 |  | 12
122 | Reports |  | 2026-07-15 | reports/SectionObjectivePerformance.aspx | Pod 1 | Pod 1_Member2 | 2026-07-15 | 3 | 0 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 2 | 2026-07-24 | 2026-07-24 | 3 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-30 | 2026-07-30 | 3 | 2026-08-04 | 2 | 2026-08-06 | 3 | 2026-08-11 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 1 | 2026-08-13 | 2026-08-13 | 3 | 2026-08-18 | 1 | 2026-08-19 | 3 | 2026-08-25 | 2026-08-27 | 2026-08-28 | 2026-09-02 | 2026-09-03 | 48 |  | 12
123 | Webuser |  | 2026-06-01 | webuser/contactInformationHistory.aspx | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 0 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-28 | 3 | 2026-07-31 | 1 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 77 |  | 12
124 | Webuser |  | 2026-06-01 | webuser/dataview.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 | 0 | 4 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 2 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2 | 2026-06-24 | 3 | 2026-06-30 | 2026-06-30 | 2026-07-01 | 2026-07-01 | 1 | 2026-07-02 | 2026-07-28 | 3 | 2026-07-31 | 1 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 77 |  | 12
125 | Webuser |  | 2026-06-09 | webuser/addressContact.aspx ¦ RadAjaxM | Pod 3 | Pod 3_Member1 | 2026-06-09 | 3 | 0 | 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-28 | 3 | 2026-07-31 | 1 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 70 |  | 12
126 | Webuser |  | 2026-06-09 | webuser/expressEdit.aspx ¦ RadAjaxMana | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 | 0 | 6 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-28 | 3 | 2026-07-31 | 1 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 70 |  | 12
127 | Webuser |  | 2026-06-09 | webuser/expressUserSelection.aspx ¦ Ra | Pod 3 | Pod 3_Member3 | 2026-06-09 | 3 | 0 | 7 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 2 | 2026-06-18 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 3 | 2026-06-30 | 2 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 1 | 2026-07-10 | 2026-07-28 | 3 | 2026-07-31 | 1 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 70 |  | 12
128 | Webuser |  | 2026-06-17 | webuser/dataviewList.aspx ¦ RadGrid, R | Pod 3 | Pod 3_Member1 | 2026-06-17 | 3 | 0 | 5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-28 | 3 | 2026-07-31 | 1 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 62 |  | 12
129 | Webuser |  | 2026-06-17 | webuser/webusers.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member2 | 2026-06-17 | 3 | 0 | 1 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-28 | 3 | 2026-07-31 | 1 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 62 |  | 12
130 | Webuser |  | 2026-06-17 | webuser/overview.aspx ¦ RadTabStrip, R | Pod 3 | Pod 3_Member3 | 2026-06-17 | 3 | 0 | 2 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 2 | 2026-06-29 | 2026-06-29 | 3 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-03 | 2026-07-03 | 3 | 2026-07-09 | 2 | 2026-07-13 | 3 | 2026-07-16 | 2026-07-16 | 2026-07-17 | 2026-07-17 | 1 | 2026-07-20 | 2026-07-28 | 3 | 2026-07-31 | 1 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 62 |  | 12
131 | Webuser |  | 2026-06-25 | webuser/webuserExtended.aspx ¦ RadGrid | Pod 3 | Pod 3_Member1 | 2026-06-25 | 3 | 0 | 8 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 3 | 2026-07-31 | 1 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 51 | 10 | 12 |  |  | 22
132 | Webuser |  | 2026-06-25 | webuser/sections.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member2 | 2026-06-25 | 3 | 0 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 2 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2 | 2026-07-21 | 3 | 2026-07-24 | 2026-07-24 | 2026-07-27 | 2026-07-27 | 1 | 2026-07-28 | 2026-07-28 | 3 | 2026-07-31 | 1 | 2026-08-03 | 3 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 51 |  | 12
Formulas:
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
Pearson Regression Testing/UAT Date = MAX(IF(B2:B125=[Module], AJ2:AJ125))
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing Day], IndHolidays)
TEST Deployment = WORKDAY([PR Response receive Date], 1, IndHolidays)
Release Request Approved Date = WORKDAY([Release Request Raise Date], 3, IndHolidays)
Release Date (2-Wk Cycle) = CEILING([Release Request Approved Date]-DATE(2026,4,16), 14)+DATE(2026,4,16)

## Sheet1_Revised
No. | Module | Target page Technology | Recieved Functional & Non Fuctional Walkthrough | Module Target Start (Input) | Page | Pod | Developer | Start Date | Dev + Integration Efforts | Sick/Leave (Input) | PR Number | Co- Pilot Comment Closure Date | Unit Testing Closure Date | PR raised date | PR Response Days | PR Response receive Date | PR Review Comments Fix Days | PR Issue Fix Date | PR Raised Date | PR Response Days | PR Response receive Date | PR Final Approval date | Code Merge Date (INT Ready) | TCR Deployment Date | TCR QE Testing Start Date | QE Testing Days (TCR) | TCR QE Testing End Date | Issue Fix Days | PR Raise Date | PR Response Days | PR Response receive Date | New PR Update (Re-deploy) Date | Code Merge Date (INT Ready) | TCR QE Re-Testing Start Date | QE Re-Testing Days (TCR) | TCR Bugs Closure Date | Code Freeze Date | Pearson Regression Testing | Pearson Regression Test Support Efforts (Ascendion) | Pearson Regression Testing/UAT Date | Code freeze date = Release cutoff Date | Release # | Release Date | Pearson Regression End Date | Regression Issue Fix Days | PR raised date | PR Response Days | PR Approveal/Merge Date | TCR/TEST Deployment | Release Request Raise Date | Release Request Approved Date | Release Date (2-Wk Cycle) | Elapsed time due to dependencies | Release alignment lost date | PR Review days | Time Lost due to Regression Testing | Release approval delays | Total time lost | Issue Fix days | Development efforts can we reduce?
35 | AddressBook | Complete ASP | Yes | 2026-04-15 | page_1 | Pod 3 | Pod 3_Member1 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 5 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 | 1.5 | 2026-05-05 | 1.2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 1 | 2026-05-13 | 2026-05-13 | 3 | 0.6 | 2026-05-19 | 2026-05-21 | Release 11 | 2026-05-28 | 2026-05-22 | 1 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-05 | 2026-06-11 | 55 |  | 14
36 | AddressBook | Complete ASP |  | 2026-04-15 | page_2 | Pod 3 | Pod 3_Member2 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 5 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 | 1.5 | 2026-05-05 | 1.2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 1 | 2026-05-13 | 2026-05-13 | 3 | 0.6 | 2026-05-19 | 2026-05-21 | Release 11 | 2026-05-28 | 2026-05-22 | 1 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-05 | 2026-06-11 | 55 |  | 14
37 | AddressBook | Complete ASP |  | 2026-04-15 | page_3 | Pod 3 | Pod 3_Member3 | 2026-04-15 | 3 | 0 | 1 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 5 | 2026-04-24 | 1.5 | 2026-04-27 | 2026-04-27 | 3 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-04 | 1.5 | 2026-05-05 | 1.2 | 2026-05-06 | 3 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-12 | 1 | 2026-05-13 | 2026-05-13 | 3 | 0.6 | 2026-05-19 | 2026-05-21 | Release 11 | 2026-05-28 | 2026-05-22 | 1 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-05 | 2026-06-11 | 55 |  | 14
38 | AddressBook | Complete ASP |  | 2026-04-21 | page_4 | Pod 3 | Pod 3_Member1 | 2026-04-21 | 3 | 0 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 5 | 2026-04-30 | 1.5 | 2026-05-04 | 2026-05-04 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 1.5 | 2026-05-11 | 1.2 | 2026-05-12 | 3 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 1 | 2026-05-19 | 2026-05-19 | 3 | 0.6 | 2026-05-19 | 2026-05-21 | Release 11 | 2026-05-28 | 2026-05-22 | 1 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-05 | 2026-06-11 | 49 |  | 14
39 | AddressBook | Complete ASP |  | 2026-04-21 | page_5 | Pod 3 | Pod 3_Member2 | 2026-04-21 | 3 | 0 | 1 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 3 | 2026-04-28 | 1.5 | 2026-04-29 | 2026-04-29 | 3 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 | 1.5 | 2026-05-07 | 1.2 | 2026-05-08 | 3 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 1 | 2026-05-15 | 2026-05-15 | 3 | 0.6 | 2026-05-19 | 2026-05-21 | Release 11 | 2026-05-28 | 2026-05-22 | 1 | 2026-05-25 | 3 | 2026-05-29 | 2026-05-29 | 2026-06-01 | 2026-06-05 | 2026-06-11 | 49 | 10 | 12 |  |  | 22
43 | Enrollment | Complete ASP | No | 2026-05-14 | enrollment/placement/manager.aspx ¦ RadG | Pod 1 | Pod 1_Member1 | 2026-05-14 | 3 | 0 | 1 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1.5 | 2026-06-01 | 1.2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 3 | 0.6 | 2026-06-25 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 66 |  | 12
44 | Enrollment | Complete ASP |  | 2026-05-14 | enrollment/placement/rejectReason.aspx ¦ | Pod 1 | Pod 1_Member2 | 2026-05-14 | 3 | 0 | 2 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1.5 | 2026-06-01 | 1.2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 3 | 0.6 | 2026-06-25 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 66 |  | 12
45 | Enrollment | Complete ASP |  | 2026-05-05 | enrollment/placement/placementHelp.aspx | Pod 1 | Pod 1_Member3 | 2026-05-05 | 3 | 0 | 3 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 1.5 | 2026-05-20 | 1.2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 3 | 0.6 | 2026-06-25 | 2026-06-04 | Release 12 | 2026-06-11 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 77 |  | 12
46 | Enrollment | Complete ASP |  | 2026-05-22 | enrollment/registration/default.aspx ¦ R | Pod 1 | Pod 1_Member1 | 2026-05-22 | 3 | 0 | 4 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1.5 | 2026-06-10 | 1.2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 3 | 0.6 | 2026-06-25 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 58 |  | 12
47 | Enrollment | Complete ASP |  | 2026-05-22 | enrollment/registration/registrationLoca | Pod 1 | Pod 1_Member2 | 2026-05-22 | 3 | 0 | 5 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1.5 | 2026-06-10 | 1.2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 3 | 0.6 | 2026-06-25 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 58 |  | 12
48 | Enrollment | Complete ASP |  | 2026-05-14 | enrollment/registration/registrationLoca | Pod 1 | Pod 1_Member3 | 2026-05-14 | 3 | 0 | 6 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1.5 | 2026-06-01 | 1.2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 3 | 0.6 | 2026-06-25 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 66 |  | 12
49 | Enrollment | Complete ASP |  | 2026-06-01 | enrollment/registration/registrantFamily | Pod 1 | Pod 1_Member1 | 2026-06-01 | 3 | 0 | 7 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1.5 | 2026-06-17 | 1.2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 0.6 | 2026-06-25 | 2026-07-02 | Release 14 | 2026-07-09 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 49 |  | 12
50 | Enrollment | Complete ASP |  | 2026-06-01 | enrollment/registration/resendEmail.aspx | Pod 1 | Pod 1_Member2 | 2026-06-01 | 3 | 0 | 8 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1.5 | 2026-06-17 | 1.2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 0.6 | 2026-06-25 | 2026-07-02 | Release 14 | 2026-07-09 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 49 | 14 | 12 |  |  | 26
61 | Webuser | Complete ASP | No | 2026-05-05 | webuser/addressContact.aspx ¦ RadAjaxM | Pod 3 | Pod 3_Member1 | 2026-05-05 | 3 | 0 | 1 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 1.5 | 2026-05-20 | 1.2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 3 | 0.6 | 2026-06-25 | 2026-06-04 | Release 12 | 2026-06-11 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 77 |  | 12
62 | Webuser | Complete ASP |  | 2026-05-05 | webuser/contactInformationHistory.aspx | Pod 3 | Pod 3_Member2 | 2026-05-05 | 3 | 0 | 2 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 1.5 | 2026-05-20 | 1.2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 3 | 0.6 | 2026-06-25 | 2026-06-04 | Release 12 | 2026-06-11 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 77 |  | 12
63 | Webuser | Complete ASP |  | 2026-04-24 | webuser/dataview.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member3 | 2026-04-24 | 3 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 1.5 | 2026-05-12 | 1.2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 3 | 0.6 | 2026-06-25 | 2026-05-21 | Release 11 | 2026-05-28 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 86 |  | 12
64 | Webuser | Complete ASP |  | 2026-05-14 | webuser/dataviewList.aspx ¦ RadGrid, R | Pod 3 | Pod 3_Member1 | 2026-05-14 | 3 | 0 | 4 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1.5 | 2026-06-01 | 1.2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 3 | 0.6 | 2026-06-25 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 66 |  | 12
65 | Webuser | Complete ASP |  | 2026-05-14 | webuser/expressEdit.aspx ¦ RadAjaxMana | Pod 3 | Pod 3_Member2 | 2026-05-14 | 3 | 0 | 5 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1.5 | 2026-06-01 | 1.2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 3 | 0.6 | 2026-06-25 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 66 |  | 12
66 | Webuser | Complete ASP |  | 2026-05-05 | webuser/expressUserSelection.aspx ¦ Ra | Pod 3 | Pod 3_Member3 | 2026-05-05 | 3 | 0 | 6 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 1.5 | 2026-05-20 | 1.2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 3 | 0.6 | 2026-06-25 | 2026-06-04 | Release 12 | 2026-06-11 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 77 |  | 12
67 | Webuser | Complete ASP |  | 2026-05-22 | webuser/webuserExtended.aspx ¦ RadGrid | Pod 3 | Pod 3_Member1 | 2026-05-22 | 3 | 0 | 7 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1.5 | 2026-06-10 | 1.2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 3 | 0.6 | 2026-06-25 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 58 |  | 12
68 | Webuser | Complete ASP |  | 2026-05-22 | webuser/webusers.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member2 | 2026-05-22 | 3 | 0 | 8 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1.5 | 2026-06-10 | 1.2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 3 | 0.6 | 2026-06-25 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 58 |  | 12
69 | Webuser | Complete ASP |  | 2026-05-14 | webuser/overview.aspx ¦ RadTabStrip, R | Pod 3 | Pod 3_Member3 | 2026-05-14 | 3 | 0 | 9 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1.5 | 2026-06-01 | 1.2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 3 | 0.6 | 2026-06-25 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 66 |  | 12
70 | Webuser | Complete ASP |  | 2026-06-01 | webuser/sections.aspx ¦ RadGrid, RadAj | Pod 3 | Pod 3_Member1 | 2026-06-01 | 3 | 0 | 10 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1.5 | 2026-06-17 | 1.2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 0.6 | 2026-06-25 | 2026-07-02 | Release 14 | 2026-07-09 | 2026-07-01 | 1 | 2026-07-02 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-23 | 49 | 14 | 12 |  |  | 26
1 | LMU | React/ASP |  | 2026-04-15 | page_1 | Pod 2 | Pod 2_Member1 | 2026-04-15 | 10 | 0 | 1 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 5 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 | 5 | 2026-05-22 | 4 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 3 | 2 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 100 |  | 12
2 | LMU | React/ASP |  | 2026-04-15 | page_2 | Pod 2 | Pod 2_Member2 | 2026-04-15 | 10 | 0 | 2 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 5 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 | 5 | 2026-05-22 | 4 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 3 | 2 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 100 |  | 12
3 | LMU | React/ASP |  | 2026-04-15 | page_3 | Pod 2 | Pod 2_Member3 | 2026-04-15 | 10 | 0 | 3 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 5 | 2026-05-11 | 2026-05-11 | 3 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 | 5 | 2026-05-22 | 4 | 2026-05-29 | 3 | 2026-06-04 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 1 | 2026-06-08 | 2026-06-08 | 3 | 2 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 100 |  | 12
4 | LMU | React/ASP |  | 2026-04-24 | page_4 | Pod 2 | Pod 2_Member1 | 2026-04-24 | 10 | 0 | 4 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 5 | 2026-06-04 | 4 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 3 | 2 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 90 |  | 12
5 | LMU | React/ASP |  | 2026-04-24 | page_5 | Pod 2 | Pod 2_Member2 | 2026-04-24 | 10 | 0 | 5 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 3 | 2026-05-13 | 5 | 2026-05-20 | 2026-05-20 | 3 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 5 | 2026-06-04 | 4 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1 | 2026-06-17 | 2026-06-17 | 3 | 2 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 90 |  | 12
6 | LMU | Complete ASP |  | 2026-04-24 | page_6 | Pod 2 | Pod 2_Member3 | 2026-04-24 | 3 | 0 | 6 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 3 | 2026-05-04 | 1.5 | 2026-05-05 | 2026-05-05 | 3 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-11 | 1.5 | 2026-05-12 | 1.2 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 1 | 2026-05-20 | 2026-05-20 | 3 | 0.6 | 2026-07-22 | 2026-05-21 | Release 11 | 2026-05-28 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 100 |  | 12
7 | LMU | Complete ASP |  | 2026-05-05 | page_7 | Pod 2 | Pod 2_Member1 | 2026-05-05 | 3 | 0 | 7 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 1.5 | 2026-05-20 | 1.2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 3 | 0.6 | 2026-07-22 | 2026-06-04 | Release 12 | 2026-06-11 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 91 |  | 12
8 | LMU | Complete ASP |  | 2026-05-05 | page_8 | Pod 2 | Pod 2_Member2 | 2026-05-05 | 3 | 0 | 8 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 1.5 | 2026-05-20 | 1.2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 3 | 0.6 | 2026-07-22 | 2026-06-04 | Release 12 | 2026-06-11 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 91 |  | 12
9 | LMU | Complete ASP |  | 2026-05-05 | page_9 | Pod 2 | Pod 2_Member3 | 2026-05-05 | 3 | 0 | 9 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 3 | 2026-05-12 | 1.5 | 2026-05-13 | 2026-05-13 | 3 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 1.5 | 2026-05-20 | 1.2 | 2026-05-21 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 1 | 2026-05-29 | 2026-05-29 | 3 | 0.6 | 2026-07-22 | 2026-06-04 | Release 12 | 2026-06-11 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 91 |  | 12
10 | LMU | Complete ASP |  | 2026-05-14 | page_10 | Pod 2 | Pod 2_Member1 | 2026-05-14 | 3 | 0 | 10 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1.5 | 2026-06-01 | 1.2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 3 | 0.6 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 80 |  | 12
11 | LMU | Complete ASP |  | 2026-05-14 | page_11 | Pod 2 | Pod 2_Member2 | 2026-05-14 | 3 | 0 | 11 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1.5 | 2026-06-01 | 1.2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 3 | 0.6 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 80 |  | 12
12 | LMU | Complete ASP |  | 2026-05-14 | page_12 | Pod 2 | Pod 2_Member3 | 2026-05-14 | 3 | 0 | 12 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 3 | 2026-05-21 | 1.5 | 2026-05-22 | 2026-05-22 | 3 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-29 | 2026-05-29 | 1.5 | 2026-06-01 | 1.2 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1 | 2026-06-10 | 2026-06-10 | 3 | 0.6 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 80 |  | 12
13 | LMU | Complete ASP |  | 2026-05-22 | page_13 | Pod 2 | Pod 2_Member1 | 2026-05-22 | 3 | 0 | 13 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1.5 | 2026-06-10 | 1.2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 3 | 0.6 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 72 |  | 12
14 | LMU | Complete ASP |  | 2026-05-22 | page_14 | Pod 2 | Pod 2_Member2 | 2026-05-22 | 3 | 0 | 14 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1.5 | 2026-06-10 | 1.2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 3 | 0.6 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 72 |  | 12
15 | LMU | Complete ASP |  | 2026-05-22 | page_15 | Pod 2 | Pod 2_Member3 | 2026-05-22 | 3 | 0 | 15 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1.5 | 2026-06-10 | 1.2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 3 | 0.6 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 72 |  | 12
16 | LMU | Complete ASP |  | 2026-06-01 | page_16 | Pod 2 | Pod 2_Member1 | 2026-06-01 | 3 | 0 | 16 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1.5 | 2026-06-17 | 1.2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 0.6 | 2026-07-22 | 2026-07-02 | Release 14 | 2026-07-09 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 63 |  | 12
17 | LMU | Complete ASP |  | 2026-06-01 | page_17 | Pod 2 | Pod 2_Member2 | 2026-06-01 | 3 | 0 | 17 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1.5 | 2026-06-17 | 1.2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 0.6 | 2026-07-22 | 2026-07-02 | Release 14 | 2026-07-09 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 63 |  | 12
18 | LMU | Complete ASP |  | 2026-06-01 | page_18 | Pod 2 | Pod 2_Member3 | 2026-06-01 | 3 | 0 | 18 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1.5 | 2026-06-17 | 1.2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 0.6 | 2026-07-22 | 2026-07-02 | Release 14 | 2026-07-09 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 63 |  | 12
19 | LMU | Complete ASP |  | 2026-06-09 | page_19 | Pod 2 | Pod 2_Member1 | 2026-06-09 | 3 | 0 | 19 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1.5 | 2026-06-24 | 1.2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 3 | 0.6 | 2026-07-22 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 56 |  | 12
20 | LMU | Complete ASP |  | 2026-06-09 | page_20 | Pod 2 | Pod 2_Member2 | 2026-06-09 | 3 | 0 | 20 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1.5 | 2026-06-24 | 1.2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 3 | 0.6 | 2026-07-22 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 56 |  | 12
21 | LMU | Complete ASP |  | 2026-06-09 | page_21 | Pod 2 | Pod 2_Member3 | 2026-06-09 | 3 | 0 | 21 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1.5 | 2026-06-24 | 1.2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 3 | 0.6 | 2026-07-22 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 56 |  | 12
22 | LMU | Complete ASP |  | 2026-06-17 | page_22 | Pod 2 | Pod 2_Member1 | 2026-06-17 | 3 | 0 | 22 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1.5 | 2026-07-03 | 1.2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 0.6 | 2026-07-22 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 48 |  | 12
23 | LMU | Complete ASP |  | 2026-06-17 | page_23 | Pod 2 | Pod 2_Member2 | 2026-06-17 | 3 | 0 | 23 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1.5 | 2026-07-03 | 1.2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 0.6 | 2026-07-22 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 48 |  | 12
24 | LMU | Complete ASP |  | 2026-06-17 | page_24 | Pod 2 | Pod 2_Member3 | 2026-06-17 | 3 | 0 | 24 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1.5 | 2026-07-03 | 1.2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 0.6 | 2026-07-22 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 48 |  | 12
25 | LMU | Complete ASP |  | 2026-06-25 | page_25 | Pod 2 | Pod 2_Member1 | 2026-06-25 | 3 | 0 | 25 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1.5 | 2026-07-14 | 1.2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 3 | 0.6 | 2026-07-22 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 37 |  | 12
26 | LMU | Complete ASP |  | 2026-06-25 | page_26 | Pod 2 | Pod 2_Member2 | 2026-06-25 | 3 | 0 | 26 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1.5 | 2026-07-14 | 1.2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 3 | 0.6 | 2026-07-22 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 37 | 3 | 12 |  |  | 15
71 | ProgressionPlan | Complete ASP |  | 2026-06-09 | progressionPlan/progressionPlan.aspx ¦ RadGrid, RadAja | Pod 1 | Pod 1_Member1 | 2026-06-09 | 3 | 0 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1.5 | 2026-06-24 | 1.2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 3 | 0.6 | 2026-07-22 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 56 |  | 12
72 | ProgressionPlan | Complete ASP |  | 2026-06-09 | progressionPlan/academicRequirement.aspx ¦ RadGrid, Ra | Pod 1 | Pod 1_Member2 | 2026-06-09 | 3 | 0 | 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1.5 | 2026-06-24 | 1.2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 3 | 0.6 | 2026-07-22 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 56 |  | 12
73 | ProgressionPlan | Complete ASP |  | 2026-05-22 | progressionPlan/academicRequirements.aspx ¦ RadGrid, R | Pod 1 | Pod 1_Member3 | 2026-05-22 | 3 | 0 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1.5 | 2026-06-10 | 1.2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 3 | 0.6 | 2026-07-22 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 72 |  | 12
74 | ProgressionPlan | Complete ASP |  | 2026-06-17 | progressionPlan/completionRequirement.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member1 | 2026-06-17 | 3 | 0 | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1.5 | 2026-07-03 | 1.2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 0.6 | 2026-07-22 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 48 |  | 12
75 | ProgressionPlan | Complete ASP |  | 2026-06-17 | progressionPlan/completionRequirements.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member2 | 2026-06-17 | 3 | 0 | 5 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1.5 | 2026-07-03 | 1.2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 0.6 | 2026-07-22 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 48 |  | 12
76 | ProgressionPlan | Complete ASP |  | 2026-06-01 | progressionPlan/webusers.aspx ¦ RadGrid, RadAjaxManage | Pod 1 | Pod 1_Member3 | 2026-06-01 | 3 | 0 | 6 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1.5 | 2026-06-17 | 1.2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 0.6 | 2026-07-22 | 2026-07-02 | Release 14 | 2026-07-09 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 63 |  | 12
77 | ProgressionPlan | Complete ASP |  | 2026-06-25 | progressionPlan/help/progressionPlansSelectorHelp.aspx | Pod 1 | Pod 1_Member1 | 2026-06-25 | 3 | 0 | 7 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1.5 | 2026-07-14 | 1.2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 3 | 0.6 | 2026-07-22 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-07-27 | 1 | 2026-07-28 | 3 | 2026-07-31 | 2026-07-31 | 2026-08-03 | 2026-08-06 | 2026-08-06 | 37 | 3 | 12
40 | Library | Complete ASP |  | 2026-07-03 | library/resource.aspx ¦ Ra | Pod 2 | Pod 2_Member1 | 2026-07-03 | 3 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1.5 | 2026-07-21 | 1.2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 3 | 0.6 | 2026-07-29 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 43 |  | 12
41 | Library | Complete ASP |  | 2026-07-03 | library/searchResults.aspx | Pod 2 | Pod 2_Member2 | 2026-07-03 | 3 | 0 | 2 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1.5 | 2026-07-21 | 1.2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 3 | 0.6 | 2026-07-29 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 43 |  | 12
42 | Library | Complete ASP |  | 2026-06-25 | library/userSelector.aspx | Pod 2 | Pod 2_Member3 | 2026-06-25 | 3 | 0 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1.5 | 2026-07-14 | 1.2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 3 | 0.6 | 2026-07-29 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 51 | 10 | 12 |  |  | 22
78 | ExtendedField | Complete ASP |  | 2026-07-03 | extendedField/extendedField.aspx ¦ RadAjax | Pod 1 | Pod 1_Member1 | 2026-07-03 | 3 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1.5 | 2026-07-21 | 1.2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 3 | 0.6 | 2026-08-07 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 57 |  | 12
79 | ExtendedField | Complete ASP |  | 2026-06-25 | extendedField/default.aspx ¦ RadGrid, RadA | Pod 1 | Pod 1_Member2 | 2026-06-25 | 3 | 0 | 2 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1.5 | 2026-07-14 | 1.2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 3 | 0.6 | 2026-08-07 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 65 |  | 12
80 | ExtendedField | Complete ASP |  | 2026-06-09 | extendedField/associations.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member3 | 2026-06-09 | 3 | 0 | 3 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1.5 | 2026-06-24 | 1.2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 3 | 0.6 | 2026-08-07 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 84 |  | 12
81 | ExtendedField | Complete ASP |  | 2026-07-15 | extendedField/calculationGroupExtendedFiel | Pod 1 | Pod 1_Member1 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1.5 | 2026-07-30 | 1.2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 3 | 0.6 | 2026-08-07 | 2026-08-13 | Release 17 | 2026-08-20 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 48 |  | 12
82 | ExtendedField | Complete ASP |  | 2026-07-03 | extendedField/extendedFieldConfirmRecalcul | Pod 1 | Pod 1_Member2 | 2026-07-03 | 3 | 0 | 5 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1.5 | 2026-07-21 | 1.2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 3 | 0.6 | 2026-08-07 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 57 |  | 12
83 | ExtendedField | Complete ASP |  | 2026-06-17 | extendedField/fieldHistory.aspx ¦ RadGrid, | Pod 1 | Pod 1_Member3 | 2026-06-17 | 3 | 0 | 6 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1.5 | 2026-07-03 | 1.2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 0.6 | 2026-08-07 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 76 |  | 12
84 | ExtendedField | Complete ASP |  | 2026-07-15 | extendedField/dataview/dataview.aspx ¦ Rad | Pod 1 | Pod 1_Member3 | 2026-07-15 | 3 | 0 | 7 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1.5 | 2026-07-30 | 1.2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 3 | 0.6 | 2026-08-07 | 2026-08-13 | Release 17 | 2026-08-20 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 48 |  | 12
85 | ExtendedField | Complete ASP |  | 2026-07-15 | extendedField/dataview/logEntryFilter.aspx | Pod 1 | Pod 1_Member2 | 2026-07-15 | 3 | 0 | 8 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1.5 | 2026-07-30 | 1.2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 3 | 0.6 | 2026-08-07 | 2026-08-13 | Release 17 | 2026-08-20 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 48 | 15 | 12 |  |  | 27
96 | Location | Complete ASP |  | 2026-06-09 | location/addressContact.aspx ¦ RadAj | Pod 3 | Pod 3_Member1 | 2026-06-09 | 3 | 0 | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1.5 | 2026-06-24 | 1.2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 3 | 0.6 | 2026-07-29 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 70 |  | 12
97 | Location | Complete ASP |  | 2026-06-01 | location/createHousehold.aspx ¦ RadA | Pod 3 | Pod 3_Member2 | 2026-06-01 | 3 | 0 | 2 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1.5 | 2026-06-17 | 1.2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 0.6 | 2026-07-29 | 2026-07-02 | Release 14 | 2026-07-09 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 77 |  | 12
98 | Location | Complete ASP |  | 2026-05-22 | location/createHouseholdLinkExisting | Pod 3 | Pod 3_Member3 | 2026-05-22 | 3 | 0 | 3 | 2026-05-26 | 2026-05-26 | 2026-05-26 | 3 | 2026-06-01 | 1.5 | 2026-06-03 | 2026-06-03 | 3 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 1.5 | 2026-06-10 | 1.2 | 2026-06-11 | 3 | 2026-06-16 | 2026-06-16 | 2026-06-17 | 2026-06-17 | 1 | 2026-06-18 | 2026-06-18 | 3 | 0.6 | 2026-07-29 | 2026-06-18 | Release 13 | 2026-06-25 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 86 |  | 12
99 | Location | Complete ASP |  | 2026-06-17 | location/dataview.aspx ¦ RadGrid, Ra | Pod 3 | Pod 3_Member1 | 2026-06-17 | 3 | 0 | 4 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1.5 | 2026-07-03 | 1.2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 0.6 | 2026-07-29 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 62 |  | 12
100 | Location | Complete ASP |  | 2026-06-09 | location/extendedFields.aspx ¦ RadGr | Pod 3 | Pod 3_Member2 | 2026-06-09 | 3 | 0 | 5 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1.5 | 2026-06-24 | 1.2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 3 | 0.6 | 2026-07-29 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 70 |  | 12
101 | Location | Complete ASP |  | 2026-06-01 | location/locationExtended.aspx ¦ Rad | Pod 3 | Pod 3_Member3 | 2026-06-01 | 3 | 0 | 6 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3 | 2026-06-09 | 1.5 | 2026-06-10 | 2026-06-10 | 3 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 1.5 | 2026-06-17 | 1.2 | 2026-06-18 | 3 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | 1 | 2026-06-25 | 2026-06-25 | 3 | 0.6 | 2026-07-29 | 2026-07-02 | Release 14 | 2026-07-09 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 77 |  | 12
102 | Location | Complete ASP |  | 2026-06-25 | location/skinProperties.aspx ¦ RadAj | Pod 3 | Pod 3_Member1 | 2026-06-25 | 3 | 0 | 7 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1.5 | 2026-07-14 | 1.2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 3 | 0.6 | 2026-07-29 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 51 |  | 12
103 | Location | Complete ASP |  | 2026-06-17 | location/reports/allUsersInRoleExten | Pod 3 | Pod 3_Member2 | 2026-06-17 | 3 | 0 | 8 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1.5 | 2026-07-03 | 1.2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 0.6 | 2026-07-29 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 62 |  | 12
104 | Location | Complete ASP |  | 2026-06-09 | location/security/roleWebusers.aspx | Pod 3 | Pod 3_Member3 | 2026-06-09 | 3 | 0 | 9 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 3 | 2026-06-16 | 1.5 | 2026-06-17 | 2026-06-17 | 3 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-23 | 1.5 | 2026-06-24 | 1.2 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1 | 2026-07-03 | 2026-07-03 | 3 | 0.6 | 2026-07-29 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 70 |  | 12
105 | Location | Complete ASP |  | 2026-07-03 | AdditionalPage 1 | Pod 3 | Pod 3_Member1 | 2026-07-03 | 3 | 0 | 10 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1.5 | 2026-07-21 | 1.2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 3 | 0.6 | 2026-07-29 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 43 |  | 12
106 | Location | Complete ASP |  | 2026-06-25 | AdditionalPage 2 | Pod 3 | Pod 3_Member2 | 2026-06-25 | 3 | 0 | 11 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1.5 | 2026-07-14 | 1.2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 3 | 0.6 | 2026-07-29 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-03 | 1 | 2026-08-04 | 3 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-20 | 51 | 10 | 12 |  |  | 22
112 | AssetAware | Complete ASP |  | 2026-07-03 | assetAware/asset.aspx | Pod 3 | Pod 3_Member3 | 2026-07-03 | 3 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1.5 | 2026-07-21 | 1.2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 3 | 0.6 | 2026-08-07 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 57 |  | 12
113 | AssetAware | Complete ASP |  | 2026-07-03 | assetAware/assets.aspx | Pod 3 | Pod 3_Member2 | 2026-07-03 | 3 | 0 | 2 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1.5 | 2026-07-21 | 1.2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 3 | 0.6 | 2026-08-07 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 57 |  | 12
114 | AssetAware | Complete ASP |  | 2026-06-17 | assetAware/assetHistory.aspx | Pod 3 | Pod 3_Member3 | 2026-06-17 | 3 | 0 | 3 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 3 | 2026-06-24 | 1.5 | 2026-06-25 | 2026-06-25 | 3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 1.5 | 2026-07-03 | 1.2 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1 | 2026-07-14 | 2026-07-14 | 3 | 0.6 | 2026-08-07 | 2026-07-16 | Release 15 | 2026-07-23 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 76 |  | 12
115 | AssetAware | Complete ASP |  | 2026-07-15 | assetAware/assetVendorAddressContact.aspx | Pod 3 | Pod 3_Member1 | 2026-07-15 | 3 | 0 | 4 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1.5 | 2026-07-30 | 1.2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 3 | 0.6 | 2026-08-07 | 2026-08-13 | Release 17 | 2026-08-20 | 2026-08-12 | 1 | 2026-08-13 | 3 | 2026-08-18 | 2026-08-18 | 2026-08-19 | 2026-08-25 | 2026-09-03 | 48 | 15 | 12 |  |  | 27
51 | Log | Complete ASP |  | 2026-07-15 | log/default.aspx ¦ RadGrid, RadAjaxManager, RadDa | Pod 2 | Pod 2_Member1 | 2026-07-15 | 3 | 0 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1.5 | 2026-07-30 | 1.2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 3 | 0.6 | 2026-08-27 | 2026-08-13 | Release 17 | 2026-08-20 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 62 |  | 12
52 | Log | Complete ASP |  | 2026-07-15 | log/logEntry.aspx ¦ RadGrid, RadAjaxManager, RadT | Pod 2 | Pod 2_Member2 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1.5 | 2026-07-30 | 1.2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 3 | 0.6 | 2026-08-27 | 2026-08-13 | Release 17 | 2026-08-20 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 62 |  | 12
53 | Log | Complete ASP |  | 2026-07-03 | log/areas.aspx ¦ RadGrid, RadAjaxManager ¦ Medium | Pod 2 | Pod 2_Member3 | 2026-07-03 | 3 | 0 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1.5 | 2026-07-21 | 1.2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 3 | 0.6 | 2026-08-27 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 71 |  | 12
54 | Log | Complete ASP |  | 2026-07-23 | log/categories.aspx ¦ RadGrid, RadAjaxManager ¦ M | Pod 2 | Pod 2_Member1 | 2026-07-23 | 3 | 0 | 4 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1.5 | 2026-08-07 | 1.2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 3 | 0.6 | 2026-08-27 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 52 |  | 12
55 | Log | Complete ASP |  | 2026-07-23 | log/contactTypes.aspx ¦ RadGrid, RadAjaxManager ¦ | Pod 2 | Pod 2_Member2 | 2026-07-23 | 3 | 0 | 5 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1.5 | 2026-08-07 | 1.2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 3 | 0.6 | 2026-08-27 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 52 |  | 12
56 | Log | Complete ASP |  | 2026-07-15 | log/logEntrySystems.aspx ¦ RadGrid, RadAjaxManage | Pod 2 | Pod 2_Member3 | 2026-07-15 | 3 | 0 | 6 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1.5 | 2026-07-30 | 1.2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 3 | 0.6 | 2026-08-27 | 2026-08-13 | Release 17 | 2026-08-20 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 62 |  | 12
57 | Log | Complete ASP |  | 2026-07-23 | log/myLogSettings.aspx ¦ RadGrid, RadAjaxManager, | Pod 2 | Pod 3_Member2 | 2026-07-23 | 3 | 0 | 7 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1.5 | 2026-08-07 | 1.2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 3 | 0.6 | 2026-08-27 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 52 |  | 12
58 | Log | Complete ASP |  | 2026-07-23 | log/systemProperties.aspx ¦ RadAjaxManager, RadHe | Pod 2 | Pod 3_Member3 | 2026-07-23 | 3 | 0 | 8 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1.5 | 2026-08-07 | 1.2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 3 | 0.6 | 2026-08-27 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 52 |  | 12
59 | Log | Complete ASP |  | 2026-07-23 | log/areaCategoryWindow.aspx ¦ RadTreeView, RadAja | Pod 2 | Pod 2_Member3 | 2026-07-23 | 3 | 0 | 9 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1.5 | 2026-08-07 | 1.2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 3 | 0.6 | 2026-08-27 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 52 |  | 12
60 | Log | Complete ASP |  | 2026-07-31 | log/specialPopulations/logSpecialPopulations.aspx | Pod 2 | Pod 2_Member1 | 2026-07-31 | 3 | 0 | 10 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1.5 | 2026-08-17 | 1.2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 0.6 | 2026-08-27 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 44 | 9 | 12 |  |  | 21
107 | Reg+Attendance | Complete ASP |  | 2026-07-23 | attendance/enterAttendance.aspx | Pod 1 | Pod 1_Member1 | 2026-07-23 | 3 | 0 | 1 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1.5 | 2026-08-07 | 1.2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 3 | 0.6 | 2026-08-27 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 52 |  | 12
108 | Reg+Attendance | Complete ASP |  | 2026-07-23 | attendance/editRecord.aspx ¦ Ra | Pod 1 | Pod 1_Member2 | 2026-07-23 | 3 | 0 | 2 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1.5 | 2026-08-07 | 1.2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 3 | 0.6 | 2026-08-27 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 52 |  | 12
109 | Reg+Attendance | Complete ASP |  | 2026-06-25 | registration.aspx | Pod 1 | Pod 1_Member3 | 2026-06-25 | 3 | 0 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1.5 | 2026-07-14 | 1.2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 3 | 0.6 | 2026-08-27 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 79 |  | 12
110 | Reg+Attendance | Complete ASP |  | 2026-07-23 | AdditionalPage 1 | Pod 1 | Pod 1_Member3 | 2026-07-23 | 3 | 0 | 4 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1.5 | 2026-08-07 | 1.2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 3 | 0.6 | 2026-08-27 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 52 |  | 12
111 | Reg+Attendance | Complete ASP |  | 2026-07-31 | AdditionalPage 2 | Pod 1 | Pod 1_Member2 | 2026-07-31 | 3 | 0 | 5 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1.5 | 2026-08-17 | 1.2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 0.6 | 2026-08-27 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-01 | 1 | 2026-09-02 | 3 | 2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-11 | 2026-09-17 | 44 |  | 12
125 | Home | Complete ASP |  | 2026-07-15 | home/pages/caretaker.aspx ¦ | Pod 3 | Pod 3_Member3 | 2026-07-15 | 3 | 0 | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1.5 | 2026-07-30 | 1.2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 3 | 0.6 | 2026-08-17 | 2026-08-13 | Release 17 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 3 | 2026-08-28 | 2026-08-28 | 2026-08-31 | 2026-09-03 | 2026-09-03 | 48 |  | 12
126 | Home | Complete ASP |  | 2026-07-15 | home/pages/teacher.aspx ¦ R | Pod 3 | Pod 3_Member2 | 2026-07-15 | 3 | 0 | 2 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 3 | 2026-07-22 | 1.5 | 2026-07-23 | 2026-07-23 | 3 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-07-29 | 1.5 | 2026-07-30 | 1.2 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1 | 2026-08-07 | 2026-08-07 | 3 | 0.6 | 2026-08-17 | 2026-08-13 | Release 17 | 2026-08-20 | 2026-08-20 | 1 | 2026-08-24 | 3 | 2026-08-28 | 2026-08-28 | 2026-08-31 | 2026-09-03 | 2026-09-03 | 48 |  | 12
127 | Home | Complete ASP |  | 2026-06-25 | home/pages/teacherBeta.aspx | Pod 3 | Pod 3_Member3 | 2026-06-25 | 3 | 0 | 3 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 3 | 2026-07-03 | 1.5 | 2026-07-06 | 2026-07-06 | 3 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-13 | 2026-07-13 | 1.5 | 2026-07-14 | 1.2 | 2026-07-15 | 3 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-21 | 1 | 2026-07-22 | 2026-07-22 | 3 | 0.6 | 2026-08-17 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-08-20 | 1 | 2026-08-24 | 3 | 2026-08-28 | 2026-08-28 | 2026-08-31 | 2026-09-03 | 2026-09-03 | 65 |  | 12
128 | Home | Complete ASP |  | 2026-07-23 | home/pages/enrollment.aspx | Pod 3 | Pod 3_Member1 | 2026-07-23 | 3 | 0 | 4 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 3 | 2026-07-30 | 1.5 | 2026-07-31 | 2026-07-31 | 3 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-06 | 1.5 | 2026-08-07 | 1.2 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1 | 2026-08-17 | 2026-08-17 | 3 | 0.6 | 2026-08-17 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-08-20 | 1 | 2026-08-24 | 3 | 2026-08-28 | 2026-08-28 | 2026-08-31 | 2026-09-03 | 2026-09-03 | 38 | 3 | 12 |  |  | 15
86 | Assessments | Complete ASP |  | 2026-07-31 | assessments/default.aspx ¦ RadGrid, | Pod 2 | Pod 3_Member1 | 2026-07-31 | 3 | 0 | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1.5 | 2026-08-17 | 1.2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 0.6 | 2026-09-04 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 58 |  | 12
87 | Assessments | Complete ASP |  | 2026-07-31 | assessments/questionObjectives.aspx | Pod 2 | Pod 2_Member2 | 2026-07-31 | 3 | 0 | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1.5 | 2026-08-17 | 1.2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 0.6 | 2026-09-04 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 58 |  | 12
88 | Assessments | Complete ASP |  | 2026-07-31 | assessments/results/manager.aspx ¦ | Pod 2 | Pod 2_Member3 | 2026-07-31 | 3 | 0 | 2 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1.5 | 2026-08-17 | 1.2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 0.6 | 2026-09-04 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 58 |  | 12
89 | Assessments | Complete ASP |  | 2026-07-31 | assessments/webuserAssessmentFiles. | Pod 2 | Pod 3_Member2 | 2026-07-31 | 3 | 0 | 3 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1.5 | 2026-08-17 | 1.2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 0.6 | 2026-09-04 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 58 |  | 12
90 | Assessments | Complete ASP |  | 2026-07-31 | assessments/checkMyWork/checkMyWork | Pod 2 | Pod 3_Member3 | 2026-07-31 | 3 | 0 | 4 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1.5 | 2026-08-17 | 1.2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 0.6 | 2026-09-04 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 58 |  | 12
91 | Assessments | Complete ASP |  | 2026-08-10 | assessments/checkMyWork/submissions | Pod 2 | Pod 2_Member3 | 2026-08-10 | 3 | 0 | 5 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 3 | 2026-08-17 | 1.5 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1.5 | 2026-08-27 | 1.2 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 3 | 0.6 | 2026-09-04 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 50 |  | 12
92 | Assessments | Complete ASP |  | 2026-08-10 | assessments/import.aspx ¦ RadGrid, | Pod 2 | Pod 2_Member1 | 2026-08-10 | 3 | 0 | 6 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 3 | 2026-08-17 | 1.5 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1.5 | 2026-08-27 | 1.2 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 3 | 0.6 | 2026-09-04 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 50 |  | 12
93 | Assessments | Complete ASP |  | 2026-08-10 | assessments/question.aspx ¦ RadAjax | Pod 2 | Pod 2_Member2 | 2026-08-10 | 3 | 0 | 7 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 3 | 2026-08-17 | 1.5 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1.5 | 2026-08-27 | 1.2 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 3 | 0.6 | 2026-09-04 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 50 |  | 12
94 | Assessments | Complete ASP |  | 2026-08-10 | assessments/questionManager.aspx ¦ | Pod 2 | Pod 1_Member3 | 2026-08-10 | 3 | 0 | 8 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 3 | 2026-08-17 | 1.5 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1.5 | 2026-08-27 | 1.2 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 3 | 0.6 | 2026-09-04 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 50 |  | 12
95 | Assessments | Complete ASP |  | 2026-08-10 | assessments/questions.aspx ¦ RadGri | Pod 2 | Pod 3_Member1 | 2026-08-10 | 3 | 0 | 9 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 3 | 2026-08-17 | 1.5 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1.5 | 2026-08-27 | 1.2 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 3 | 0.6 | 2026-09-04 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 50 | 14 | 12 |  |  | 26
116 | Reports | Complete ASP |  | 2026-07-31 | reports/aggregateLogEntry.aspx ¦ RadGrid | Pod 1 | Pod 1_Member1 | 2026-07-31 | 3 | 0 | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1.5 | 2026-08-17 | 1.2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 0.6 | 2026-09-04 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 58 |  | 12
117 | Reports | Complete ASP |  | 2026-07-31 | reports/institutionalStudentPerformanceE | Pod 1 | Pod 1_Member3 | 2026-07-31 | 3 | 0 | 2 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 3 | 2026-08-07 | 1.5 | 2026-08-10 | 2026-08-10 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 1.5 | 2026-08-17 | 1.2 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1 | 2026-08-27 | 2026-08-27 | 3 | 0.6 | 2026-09-04 | 2026-08-27 | Release 18 | 2026-09-03 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 58 |  | 12
118 | Reports | Complete ASP |  | 2026-07-03 | reports/resourceManagerExport.aspx ¦ Rad | Pod 1 | Pod 1_Member3 | 2026-07-03 | 3 | 0 | 3 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 3 | 2026-07-13 | 1.5 | 2026-07-14 | 2026-07-14 | 3 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-20 | 1.5 | 2026-07-21 | 1.2 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-28 | 1 | 2026-07-29 | 2026-07-29 | 3 | 0.6 | 2026-09-04 | 2026-07-30 | Release 16 | 2026-08-06 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 85 |  | 12
119 | Reports | Complete ASP |  | 2026-08-10 | reports/sectionLogEntryReport.aspx ¦ Rad | Pod 1 | Pod 1_Member1 | 2026-08-10 | 3 | 0 | 4 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 3 | 2026-08-17 | 1.5 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1.5 | 2026-08-27 | 1.2 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 3 | 0.6 | 2026-09-04 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 50 |  | 12
120 | Reports | Complete ASP |  | 2026-08-10 | reports/SectionObjectivePerformance.aspx | Pod 1 | Pod 1_Member2 | 2026-08-10 | 3 | 0 | 5 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 3 | 2026-08-17 | 1.5 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1.5 | 2026-08-27 | 1.2 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 3 | 0.6 | 2026-09-04 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-09 | 1 | 2026-09-10 | 3 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-22 | 2026-10-01 | 50 | 14 | 12 |  |  | 26
132 | Content | Complete ASP |  | 2026-08-18 | content/hyperlink.aspx ¦ RadAjaxM | Pod 2 | Pod 1_Member3 | 2026-08-18 | 3 | 0 | 4 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 3 | 2026-08-27 | 1.5 | 2026-08-28 | 2026-08-28 | 1 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 1.5 | 2026-09-02 | 1.2 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 2026-09-07 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-08 | 3 | 0.6 | 2026-09-15 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-18 | 1 | 2026-09-21 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 42 | 8 | 6 |  |  | 14
121 | Communication | Complete ASP |  | 2026-08-10 | communication/webmail/webmailBox.aspx ¦ RadGr | Pod 2 | Pod 3_Member2 | 2026-08-10 | 3 | 0 | 1 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 3 | 2026-08-17 | 1.5 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1.5 | 2026-08-27 | 1.2 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 3 | 0.6 | 2026-09-15 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-18 | 1 | 2026-09-21 | 3 | 2026-09-24 | 2026-09-24 | 2026-09-25 | 2026-09-30 | 2026-10-01 | 50 |  | 12
122 | Communication | Complete ASP |  | 2026-08-10 | communication/webmail/settings.aspx ¦ RadAjax | Pod 2 | Pod 3_Member3 | 2026-08-10 | 3 | 0 | 2 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 3 | 2026-08-17 | 1.5 | 2026-08-18 | 2026-08-18 | 3 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-25 | 1.5 | 2026-08-27 | 1.2 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 3 | 0.6 | 2026-09-15 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-18 | 1 | 2026-09-21 | 3 | 2026-09-24 | 2026-09-24 | 2026-09-25 | 2026-09-30 | 2026-10-01 | 50 |  | 12
123 | Communication | Complete ASP |  | 2026-08-18 | communication/webmail/autoReplySettings.aspx | Pod 2 | Pod 2_Member3 | 2026-08-18 | 3 | 0 | 3 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 3 | 2026-08-27 | 1.5 | 2026-08-28 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1.5 | 2026-09-04 | 1.2 | 2026-09-07 | 3 | 2026-09-10 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 1 | 2026-09-15 | 2026-09-15 | 3 | 0.6 | 2026-09-15 | 2026-09-24 | Release 20 | 2026-10-01 | 2026-09-18 | 1 | 2026-09-21 | 3 | 2026-09-24 | 2026-09-24 | 2026-09-25 | 2026-09-30 | 2026-10-01 | 42 |  | 12
124 | Communication | Complete ASP |  | 2026-08-18 | communication/webmail/signatureSettings.aspx | Pod 2 | Pod 2_Member1 | 2026-08-18 | 3 | 0 | 4 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 3 | 2026-08-27 | 1.5 | 2026-08-28 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1.5 | 2026-09-04 | 1.2 | 2026-09-07 | 3 | 2026-09-10 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 1 | 2026-09-15 | 2026-09-15 | 3 | 0.6 | 2026-09-15 | 2026-09-24 | Release 20 | 2026-10-01 | 2026-09-18 | 1 | 2026-09-21 | 3 | 2026-09-24 | 2026-09-24 | 2026-09-25 | 2026-09-30 | 2026-10-01 | 42 | 6 | 12 |  |  | 18
129 | Content | Complete ASP |  | 2026-08-18 | content/captionedVideoItem.aspx ¦ | Pod 2 | Pod 1_Member1 | 2026-08-18 | 3 | 0 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 3 | 2026-08-27 | 1.5 | 2026-08-28 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1.5 | 2026-09-04 | 1.2 | 2026-09-07 | 3 | 2026-09-10 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 1 | 2026-09-15 | 2026-09-15 | 3 | 0.6 | 2026-09-15 | 2026-09-24 | Release 20 | 2026-10-01 | 2026-09-18 | 1 | 2026-09-21 | 3 | 2026-09-24 | 2026-09-24 | 2026-09-25 | 2026-09-30 | 2026-10-01 | 42 |  | 12
130 | Content | Complete ASP |  | 2026-08-18 | content/chrome/online/footer.aspx | Pod 2 | Pod 2_Member2 | 2026-08-18 | 3 | 0 | 2 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 3 | 2026-08-27 | 1.5 | 2026-08-28 | 2026-08-28 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 1.5 | 2026-09-04 | 1.2 | 2026-09-07 | 3 | 2026-09-10 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 1 | 2026-09-15 | 2026-09-15 | 3 | 0.6 | 2026-09-15 | 2026-09-24 | Release 20 | 2026-10-01 | 2026-09-18 | 1 | 2026-09-21 | 3 | 2026-09-24 | 2026-09-24 | 2026-09-25 | 2026-09-30 | 2026-10-01 | 42 |  | 12
131 | Content | Complete ASP |  | 2026-08-18 | content/elmItemInteractive.aspx ¦ | Pod 2 | Pod 1_Member2 | 2026-08-18 | 3 | 0 | 3 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 3 | 2026-08-27 | 1.5 | 2026-08-28 | 2026-08-28 | 1 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 1.5 | 2026-09-02 | 1.2 | 2026-09-03 | 1 | 2026-09-04 | 2026-09-04 | 2026-09-07 | 2026-09-07 | 1 | 2026-09-08 | 2026-09-08 | 3 | 0.6 | 2026-09-15 | 2026-09-10 | Release 19 | 2026-09-17 | 2026-09-18 | 0 | 2026-09-18 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-22 | 2026-09-25 | 2026-10-01 | 42 | 9 | 6
131 | Orderaware | React/ASP |  | 2026-08-18 | content/elmItemInteractive.aspx ¦ | Pod 2 | Pod 1_Member2 | 2026-08-18 | 10 | 0 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 5 | 2026-09-15 | 2026-09-15 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-17 | 5 | 2026-09-24 | 4 | 2026-09-30 | 1 | 2026-10-01 | 2026-10-01 | 2026-10-05 | 2026-10-05 | 1 | 2026-10-06 | 2026-10-06 | 3 | 2 | 0 | 2026-10-08 | Release 21 | 2026-10-15 | 1900-01-03 | 0 | 1900-01-03 | 1 | 1900-01-04 | 1900-01-04 | 1900-01-05 | 1900-01-10 | 1900-01-11 | -46255 | 6 | 6
130 | Orderaware | React/ASP |  | 2026-08-18 | content/chrome/online/footer.aspx | Pod 2 | Pod 2_Member2 | 2026-08-18 | 10 | 0 | 2 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 5 | 2026-09-15 | 2026-09-15 | 3 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-21 | 2026-09-21 | 5 | 2026-09-28 | 4 | 2026-10-05 | 3 | 2026-10-08 | 2026-10-08 | 2026-10-09 | 2026-10-09 | 1 | 2026-10-12 | 2026-10-12 | 3 | 2 | 0 | 2026-10-22 | Release 22 | 2026-10-29 | 1900-01-03 | 1 | 1900-01-04 | 3 | 1900-01-09 | 1900-01-09 | 1900-01-10 | 1900-01-15 | 1900-01-25 | -46241 |  | 12
131 | Orderaware | React/ASP |  | 2026-08-18 | content/elmItemInteractive.aspx ¦ | Pod 2 | Pod 1_Member2 | 2026-08-18 | 10 | 0 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 5 | 2026-09-15 | 2026-09-15 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-17 | 5 | 2026-09-24 | 4 | 2026-09-30 | 1 | 2026-10-01 | 2026-10-01 | 2026-10-05 | 2026-10-05 | 1 | 2026-10-06 | 2026-10-06 | 3 | 2 | 0 | 2026-10-08 | Release 21 | 2026-10-15 | 1900-01-03 | 0 | 1900-01-03 | 1 | 1900-01-04 | 1900-01-04 | 1900-01-05 | 1900-01-10 | 1900-01-11 | -46255 | 6 | 6
131 | Orderaware | React/ASP |  | 2026-08-18 | content/elmItemInteractive.aspx ¦ | Pod 2 | Pod 1_Member2 | 2026-08-18 | 10 | 0 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 3 | 2026-09-07 | 5 | 2026-09-15 | 2026-09-15 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-17 | 5 | 2026-09-24 | 4 | 2026-09-30 | 1 | 2026-10-01 | 2026-10-01 | 2026-10-05 | 2026-10-05 | 1 | 2026-10-06 | 2026-10-06 | 3 | 2 | 0 | 2026-10-08 | Release 21 | 2026-10-15 | 1900-01-03 | 0 | 1900-01-03 | 1 | 1900-01-04 | 1900-01-04 | 1900-01-05 | 1900-01-10 | 1900-01-11 | -46255 | 6 | 6
Formulas:
Start Date = [Module Target Start (Input)]
Co- Pilot Comment Closure Date = WORKDAY([Start Date]-1, [Dev + Integration Efforts]+[Sick/Leave (Input)], IndHolidays)
Unit Testing Closure Date = WORKDAY([Start Date]-1, [Dev + Integration Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Start Date]-1, [Dev + Integration Efforts]+[Sick/Leave (Input)], IndHolidays)
PR raised date = WORKDAY([Pearson Regression End Date], [Regression Issue Fix Days], IndHolidays)
PR Response receive Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
PR Response receive Date = WORKDAY([PR Raised Date], [PR Response Days], IndHolidays)
PR Issue Fix Date = WORKDAY([PR Response receive Date], [PR Review Comments Fix Days], IndHolidays)
PR Raised Date = WORKDAY([PR Issue Fix Date],0, IndHolidays)
PR Final Approval date = WORKDAY([PR Response receive Date], 0, IndHolidays)
TCR Deployment Date = WORKDAY([Code Merge Date (INT Ready)], 1, IndHolidays)
TCR QE Testing Start Date = WORKDAY([TCR Deployment Date], 0, IndHolidays)
TCR QE Testing End Date = WORKDAY([TCR QE Testing Start Date], [QE Testing Days (TCR)], IndHolidays)
PR Raise Date = WORKDAY([TCR QE Testing End Date], [Issue Fix Days], IndHolidays)
New PR Update (Re-deploy) Date = WORKDAY([PR Response receive Date], 0, IndHolidays)
Code Merge Date (INT Ready) = WORKDAY([New PR Update (Re-deploy) Date], 1, IndHolidays)
TCR QE Re-Testing Start Date = WORKDAY([Code Merge Date (INT Ready)], 0, IndHolidays)
TCR Bugs Closure Date = WORKDAY([TCR QE Re-Testing Start Date], [QE Re-Testing Days (TCR)], IndHolidays)
Code Freeze Date = [TCR Bugs Closure Date]
Pearson Regression Testing/UAT Date = MAX(IF(B2:B125=[Module], AK2:AK125))
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&[TCR Bugs Closure Date])
Code freeze date = Release cutoff Date = MINIFS(ReleaseTimeline!$A2:A27, ReleaseTimeline!$A2:A27, ">="&[Code Freeze Date])
Release Date = VLOOKUP([Code freeze date = Release cutoff Date],ReleaseTimeline!$A1:E27,3,FALSE)
Pearson Regression End Date = WORKDAY([Pearson Regression Testing/UAT Date], [Pearson Regression Testing], IndHolidays)
PR Approveal/Merge Date = WORKDAY([PR raised date], [PR Response Days], IndHolidays)
TCR/TEST Deployment = [PR Approveal/Merge Date]
Release Request Raise Date = WORKDAY([TCR/TEST Deployment], 1, IndHolidays)
Release Request Approved Date = WORKDAY([Release Request Raise Date], 3, IndHolidays)
Release Date (2-Wk Cycle) = CEILING([Release Request Approved Date]-DATE(2026,4,16), 14)+DATE(2026,4,16)

## ReleaseTimeline
Release Cutoff Date | Release# | Dates | Code Freeze | Regression Start Date
2026-01-01 | Release 1 | 2026-01-08 | 2026-01-01 | 2026-01-01
2026-01-15 | Release 2 | 2026-01-22 | 2026-01-15 | 2026-01-15
2026-01-29 | Release 3 | 2026-02-05 | 2026-01-29 | 2026-01-29
2026-02-12 | Release 4 | 2026-02-19 | 2026-02-12 | 2026-02-12
2026-02-26 | Release 5 | 2026-03-05 | 2026-02-26 | 2026-02-26
2026-03-12 | Release 6 | 2026-03-19 | 2026-03-12 | 2026-03-12
2026-03-26 | Release 7 | 2026-04-02 | 2026-03-26 | 2026-03-26
2026-04-09 | Release 8 | 2026-04-16 | 2026-04-09 | 2026-04-09
2026-04-23 | Release 9 | 2026-04-30 | 2026-04-23 | 2026-04-23
2026-05-07 | Release 10 | 2026-05-14 | 2026-05-07 | 2026-05-07
2026-05-21 | Release 11 | 2026-05-28 | 2026-05-21 | 2026-05-21
2026-06-04 | Release 12 | 2026-06-11 | 2026-06-04 | 2026-06-04
2026-06-18 | Release 13 | 2026-06-25 | 2026-06-18 | 2026-06-18
2026-07-02 | Release 14 | 2026-07-09 | 2026-07-02 | 2026-07-02
2026-07-16 | Release 15 | 2026-07-23 | 2026-07-16 | 2026-07-16
2026-07-30 | Release 16 | 2026-08-06 | 2026-07-30 | 2026-07-30
2026-08-13 | Release 17 | 2026-08-20 | 2026-08-13 | 2026-08-13
2026-08-27 | Release 18 | 2026-09-03 | 2026-08-27 | 2026-08-27
2026-09-10 | Release 19 | 2026-09-17 | 2026-09-10 | 2026-09-10
2026-09-24 | Release 20 | 2026-10-01 | 2026-09-24 | 2026-09-24
2026-10-08 | Release 21 | 2026-10-15 | 2026-10-08 | 2026-10-08
2026-10-22 | Release 22 | 2026-10-29 | 2026-10-22 | 2026-10-22
2026-11-05 | Release 23 | 2026-11-12 | 2026-11-05 | 2026-11-05
2026-11-19 | Release 24 | 2026-11-26 | 2026-11-19 | 2026-11-19
2026-12-03 | Release 25 | 2026-12-10 | 2026-12-03 | 2026-12-03
2026-12-17 | Release 26 | 2026-12-24 | 2026-12-17 | 2026-12-17
2026-12-31 | Release 27 | 2027-01-08 | 2026-12-31
2027-01-14 | Release 28 | 2027-01-22 | 2027-01-14
2027-01-28 | Release 29 | 2027-02-05 | 2027-01-28
2027-01-01 | Release 30 | 2027-02-19 | 2027-02-11
2027-02-25 | Release 31 | 2027-03-05 | 2027-02-25
2027-03-11 | Release 32 | 2027-03-19 | 2027-03-11
2027-01-02 | Release 33 | 2027-04-02 | 2027-03-25
2027-04-08 | Release 34 | 2027-04-16 | 2027-04-08
2027-04-22 | Release 35 | 2027-04-30 | 2027-04-22
2027-01-03 | Release 36 | 2027-05-14 | 2027-05-06
2027-05-20 | Release 37 | 2027-05-28 | 2027-05-20
Formulas:
Release Cutoff Date = [Code Freeze]
Code Freeze = [Dates]-7
Regression Start Date = [Code Freeze]